# SPIRE

| SUBJECT: | SPIRE Detector Selection PlanSPIRE Detector Selection Plan |
| --- | --- |
| PREPARED BY: | K.J. KingK.J. King |
| DOCUMENT No: | SPIRE/RAL/D/0028SPIRE/RAL/D/0028 |
| ISSUE: | .01.01 | Date: | 11th October 1998 |
| CHECKED BY: | …………………………………. | Date: | …………………………. |
| APPROVED BY: PI GSFC JPL SAp | …………………………………. …………………………………. …………………………………. …………………………………. | Date: | …………………………. …………………………. …………………………. …………………………. |

Distribution

| Project Team |  |
| --- | --- |
| M. J. Griffin | QMW |
| L. Vigroux | SAp |
| K.J. King | RAL |
| H. Moseley | GSFC |
| J. Roman | GSFC |
| J. Bock | JPL |
| W. Gray | JPL |
| P.A.R. Ade | QMW |
| P. Hargrave | QMW |
| P. André | SAp |
| J-L. Augueres | SAp |

# Change Record

| ISSUE | DATE |  |
| --- | --- | --- |
| .01 | 11th September 1998 | Initial Draft |

Table of Contents

1.	Introduction	8

2.	Array Development	8

2.1	CEA	8

2.1.1	Bolometer Development.	8

2.1.2	Array Testing and Evaluation.	9

2.2	JPL	9

2.3	GSFC	10

3.	Array Evaluation Facility	10

4.	Meetings	10

5.	Work Breakdown	11

5.1	WBS Index	11

6.	Schedule	22

6.1	Detector Selection Schedule	22

6.2	PUD Array Development Schedule	23

6.3	Feedhorn Array Development Schedule	24

6.4	CEA Detector Development Schedule	25

6.5	Evaluation Facility Schedule	26

6.6	Array Evaluation Schedule	27

7.	Milestones	29

# Figures

# Tables

# Glossary

| BACUS |  |
| --- | --- |
| PUD | Pop-Up Detector |
| SPIRE | Spectral and Photometric Imaging REceiver |

# References

# Applicable Documents

Reference Documents

# Introduction

Three institutes (SAp, JPL and GSFC) have development programmes in progress for different detector arrays suitable for use in the SPIRE institute. Following these programmes, each institute will provide an array to QMW to be evaluated against a set of performance criteria (a separate note describes the criteria to be applied). The evaluation report from QMW will form the basis for the decision on which array type to be carried forward into the manufacturing phase of the project, which will be made at a meeting in January 2000.

The selection of detector type will be made after the instrument Preliminary Design Review (June 1999) so all three groups must provide system design information input to the review to ensure that each option is consistant with the instrument system requirements.

This document describes the work to be carried out in the development programmes and the evaluation period and gives a schedule for these activities leading to the selection meeting.

# Array Development

## CEA

### Bolometer Development.

During the period 1997-8 bolometers are being developed using various manufacturing technologies, their properties are being measured and readout electronics tested. A summary of the progress so far is given below:

#### Bolometer Array Manufacture Technology

- heritage of silicon micro sensor machining (CEA-LETI),

- indium bump hybridisation (ISOCAM LW detector array),

- and compensated implanted thermometers (CEA-DRFMC, and other groups).

#### Thermometer performances in the 300mK-1K range:

Measured on thick (450 µm) substrate in 97, and on bolometer (5 µm) in 1998, compatible with  scientific requirements. New developments for thermometers planned for '99.

#### Thermal properties of bolometers at 300 mK:

- thermal conductance of micronic silicon beams plus metallic contacts and passivation layer measured for different geometry.

- Specific heat of bolometer components measured to determine the sensor heat capacity.

#### Absorption of sub-millimetre waves:

- Physical properties of envisaged metal absorber (TiN & WN) tested in final configuration at low temperature.

- 3D e-m code predictions checked for optical structures close to final bolometer arrangement.

#### Read out and MUX scheme:

An original read out scheme for these non-conventional bolometers (very high impedance) is currently checked, the thermal impact has been measured. The main advantage is an easy multiplexing scheme.

All these results are used for the design (started March '98) and manufacture (started June '98) of new arrays ( homogeneous pattern on 16 x16 pixels) with read out and MUX included, ready for SPIRE array evaluation process in fall 1999.

These inputs determine some pixel geometric constraint (thermal capacity, thermal conductance, size etc), other parameters like implantation dose or thermometer geometry are controlled by simultaneous manufacture of "splits". Improvements to the technology can occur in late steps of the process: metallization, passivation etc.

### Array Testing and Evaluation.

The main work during 98-99 on bolometer technology will be systematic testing of all the available arrays, differing from the metallic or absorption pattern, thermometer technology: mesa diffused or implanted thermometer, implantation density and geometry etc, to sort out the best specimen for evaluation process.

In parallel we started recently the mechanical and thermal interface design of the detector arrays.

This design, made fairly complex by the geometrical constraints of the 300 mK vs. 2K structures and the very low heat load acceptable on the 3He fridge, is strongly dependent of the measurements made on physical thermal models. Most results are consequence of recent measurements. Thermal and mechanical design can now only be developed on the basis of known properties.

Finally, the readout scheme proposed is also highly dependent of the bolometer behaviour: the characteristics of the lock in circuit will be adjusted to actual properties of the arrays.

## JPL

The intention is to fabricate, test and deliver prototype spider bolometer arrays to QMW for evaluation. Two types of bolometers will be provided: a single spider web bolometer  with a transition edge superconducting (TES) thermistor, and an array of 141 elements of which 61 are connected to a JFET readout box. The latter array will consist of spider web bolometers with neutron transmutation doped (NTD) germanium thermistors. Provision has been made in the schedule for two fabrication and test cycles for each of these deliveries.

The NTD Ge array will be delivered to QMW in a test dewar with a 3He refrigerator and a BACUS calibrator. Tests will have been performed to demonstrate the performance of the array prior to delivery.

The dewar and array will be accompanied by a person to assist in performing validation testing at QMW prior to detector array selection.

The dewar, refrigerator and calibrator will be part of the same procurement as the units obtained by QMW for validation testing.

A system design of the detector array, readout electronics and warm electronics functionality will also be provided and the instrument PDR will be supported.

## GSFC

TBW

# Array Evaluation Facility

TBW

# Meetings

Meetings will be held approximately every 3 months to assess the progress being made and to discuss the status of the development and its consequences for the instrument system design.

These meetings will be held:

| May 1998 | Saclay |
| --- | --- |
| September 1998 | GSFC |
| January 1999 | QMW |
| May 1999 | Caltech |
| September 1999 | Saclay |
| January 2000 | RAL (Selection Meeting) |

# Work Breakdown

## WBS Index

| WBS | Title | Responsible |
| --- | --- | --- |
|  | Pop-Up Detector Array Development | GSFC/NIST |
|  | Pop-Up Detector Array System Design | GSFC |
|  | Feedhorn Detector Arrays Development | JPL |
|  | Feedhorn Detector Arrays System Design | JPL |
|  | CEA Detector Arrays Selection | SAp |
|  | CEA Detector Arrays System Design | SAp |
|  | Array Evaluation | QMW |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 1 |
| Title: | Pop-Up Detector Array Development | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Detector Selection | Assigned to GSFC/NIST |
| Objectives: |  |  |
| Fabrication of a 4x8 Pop-Up Detector evaluation array evaluation with its mounting hardware and readout electronics. Test of the evaluation array prior to delivery to QMW for evaluation. Support the performance validation at QMW |
| Task Description: |  |  |
| Fabrication of a 4x8 Pop-Up Detector array Design and fabrication of array mounting hardware Fabrication of SQUIDS and Interconnects Assembly of evaluation array Test of evaluation array Support Detector performance validation at QMW |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 26 Nov 98 | He-3 refrigerator from QMW |  |
| M02 | 29 Jan 99 | Calibration Module delivery form QMW |  |
| M02 | 3 Feb 99 | Mounting hardware design ready |  |
| M03 | 4 May 99 | Mounting hardware available |  |
| M04 | 10 May 99 | 1x 8 PUDs delivered to GSFC |  |
| M05 | 18 May 99 | Fanouts delivered to GSFC |  |
| M06 | 31 May 99 | Interconnects delivered to GSFC |  |
| M07 | 18 Jun 99 | Evaluation array assembled |  |
| M08 | 2 Jun 99 | Electrical System ready |  |
| M09 | 6 Jul 99 | Cryogenic Dewar System ready |  |
| M10 | 1 Sep 99 | Delivery of evaluation array to QMW |  |
| Inputs: |  |  |
|  | Date | Item | From |
| I01 | 26 Nov 98 | He-3 refrigerator | QMW |
| I02 | 29 Jan 99 | Calibration Module | QMW |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 1 Sep 99 | Evaluation Array | QMW |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 1 |
| Title: | Pop-Up Detector Array System Design | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Preliminary Design review | Assigned to SAp |
| Objectives: |  |  |
| A system design of the detector array, readout electronics and warm electronics functionality will be provided and the instrument PDR will be supported. |
| Task Description: |  |  |
| Develop design and prepare PDR package |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 18 Jun 99 | Delivery of PDR Package |  |
| Inputs: |  |  |
|  | Date | Item | From |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 18 Jun 99 | PDR Package | SPIRE Project |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 2 |
| Title: | Feedhorn Detector Arrays Development | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Detector Selection | Assigned to JPL |
| Objectives: |  |  |
| To fabricate, test and deliver prototype spider bolometer arrays to QMW for evaluation for use in the SPIRE instrument to be flown on the FIRST mission. Two types of bolometers will be provided: a single spider web bolometer with a transition edge superconducting (TES) thermistor, and an array of 141 elements of which 61 are connected to a JFET readout box. The latter array will consist of spider web bolometers with neutron transmutation doped (NTD) germanium thermistors. Provision has been made in the schedule for two fabrication and test cycles for each of these deliveries. The NTD Ge array will be delivered to QMW in a test dewar with a 3He refrigerator and a BACUS calibrator. Tests will have been performed to demonstrate the performance of the array prior to delivery. The dewar and array will be accompanied by a person to assist in performing validation testing at QMW prior to detector array selection. The dewar, refrigerator and calibrator will be part of the same procurement as the units obtained by QMW for validation testing. |
| Task Description: |  |  |
| Fabricate, test and deliver a single TES spider Bolometer. Fabricate, test and demonstrate a 144-element NTD Ge BOLOCAM instrument operating at 1.3 (m. Fabricate, test and deliver a 144-element NTD Ge prototype SPIRE bolometer array with 61 elements connected to a JFET readout. Support detector performance validation at QMW |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 1 Oct 98 | Order JFET |  |
| M02 | 14 Oct 98 | Receive JFET dies |  |
| M03 | 16 Oct 98 | Order Load Resistor Module |  |
| M04 | 30 Oct 98 | Order Feedhorn Array Plates |  |
| M05 | 2 Nov 98 | Ship Ti/Nb TES Bolometer #1 to QMW |  |
| M06 | 26 Nov 98 | Receive Load Resistor Module |  |
| M07 | 15 Dec 98 | Receive Test Dewar and Refridgerator |  |
| M08 | 15 Jan 99 | Receive Feed horn Array Plates |  |
| M09 | 15 Jan 99 | Receive Calibrator |  |
| M10 | 11 Feb 99 | Ship Ti/Nb TES Bolometer #2 to QMW |  |
| M11 | 8 Jun 99 | Deliver SPIRE 61-Element Array #1 |  |
| M12 | 24 Aug 99 | Deliver SPIRE 61-Element Array #2 |  |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 2 of 2 |
| Title: | Feedhorn Detector Arrays Development | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Inputs: |  |  |
|  | Date | Item | From |
| I01 | 15 Dec 98 | Test Dewar | Precision Cryogenics |
| I02 | 26 Nov 98 | 3He Refridgerator | QMW |
| I03 | 29 Jan 99 | Calibration Module | QMW |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 11 Nov 98 | Ti/Nb TES Bolometer #1 (option) | QMW |
| O02 | 11 Feb 99 | Ti/Nb TES Bolometer #2 | QMW |
| O03 | 8 Jun 99 | NTD Ge Bolometer Array #1 | QMW |
| O04 | 24 Sep 99 | NTD Ge Bolometer Array #2 | QMW |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 1 |
| Title: | Feedhorn Arrays System Design | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Preliminary Design review | Assigned to JPL |
| Objectives: |  |  |
| A system design of the detector array, readout electronics and warm electronics functionality will be provided and the instrument PDR will be supported. |
| Task Description: |  |  |
| Develop design and prepare PDR package |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 7 Dec 98 | Provide RF Shielding Requirements to QMW |  |
| M02 | 1 Jan 99 | Provide preliminary Warm Electronics Requirements to SAp |  |
| M03 | 14 Jan 99 | Provide Focal Plane Support Structure Design to QMW |  |
| M04 | 14 Jan 99 | Receive revised RF Shielding requirements |  |
| M05 | 18 Jun 99 | Delivery of PDR Package |  |
| Inputs: |  |  |
|  | Date | Item | From |
| I01 | 14 Jan 99 | Revised RF Shielding Requirements | ESTEC |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 7 Dec 98 | RF Shielding Requirements | SPIRE Project |
| O02 | 1 Jan 99 | preliminary Warm Electronics Requirements | SAp |
| O03 | 14 Jan 99 | Focal Plane Support Structure Design | QMW |
| O04 | 18 Jun 99 | PDR Package | SPIRE Project |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 1 |
| Title: | CEA Detector Arrays Selection | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Delivery of final evaluation array to QMW | Assigned to SAp |
| Objectives: |  |  |
| To test the detector arrays delivered by LETI/SLIR by systematic testing of all the available arrays with differing metallic or absorption pattern, thermometer technology (mesa diffused or implanted thermometer), implantation density and geometry etc, to sort out the best specimen for further evaluation. To evaluate the static optical properties (response, noise density vs. background: NEP), and dynamic aspects (response time and total bandpass) of selected detector arrays. The tests will be carried out in the QMW laboratory on dedicated evaluation devices: optical cryostat (today) or BACUS early 1999. Support will be provided to QMW during these tests Eventually one array will be selected for evaluation as part of the detector selection process |
| Task Description: |  |  |
| Testing of arrays Development of Acquisition interface and system Design of BACUS interface Testing at QMW and selection of evaluation array Support to Evaluation of the Arrays at QMW |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 15 Oct 98 | Delivery of prototype detector to QMW |  |
| M02 | 1 Jan 99 | 1st Receipt of prototype arrays from LETI./SLIR |  |
| M03 | 1 Mar 99 | Ship 1st evaluation array to QMW |  |
| M04 | 1 Mar 99 | Delivery of Manual Switchbox to QMW |  |
| M05 | 3 May 99 | 2nd Receipt of prototype arrays from LETI/SLIR |  |
| M06 | 1 Jun 99 | Ship 2nd evaluation array to QMW |  |
| M07 | 1 Jun 99 | Delivery of Acquisition System to QMW |  |
| M08 | 1 Jul 99 | 3rd Receipt of prototype arrays from LETI/SLIR |  |
| M09 | 1 Sep 99 | Ship 3rd evaluation array to QMW |  |
| Inputs: |  |  |
|  | Date | Item | From |
| I01 | 1 Jan 99 | 1st prototype arrays | LETI/SLIR |
| I02 | 3 May 99 | 2nd prototype arrays | LETI/SLIR |
| I03 | 1 Jul 99 | 3rd prototype arrays | LETI/SLIR |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 15 Oct 98 | Prototype Detector | QMW |
| O02 | 1 Mar 99 | 1st Evaluation Array | QMW |
| O03 | 1 Mar 99 | Manual Switchbox | QMW |
| O04 | 1 Jun 99 | 2nd Evaluation Array | QMW |
| O05 | 1 Jun 99 | Acquisition System | QMW |
| O06 | 1 Sep 99 | 3rd Evaluation Array | QMW |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 1 |
| Title: | CEA Detector Array System Design | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Preliminary Design review | Assigned to SAp |
| Objectives: |  |  |
| A system design of the detector array, readout electronics and warm electronics functionality will be provided and the instrument PDR will be supported. |
| Task Description: |  |  |
| Develop design and prepare PDR package |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 18 Jun 99 | Delivery of PDR Package |  |
| Inputs: |  |  |
|  | Date | Item | From |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 18 Jun 99 | PDR Package | SPIRE Project |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 1 of 2 |
| Title: | Array Evaluation Facility | Issue: | .01 (draft) |
|  |  | Date: | 14 October 1998 |
| Start Event: End Event: | Detector Selection | Assigned to QMW |
| Objectives: |  |  |
| QMW will design and manufacture a detector calibration/evaluation facility to validate the performance characteristics of the JPL, GSFC and Sap detector arrays. These will be compared to the required performance criteria at a Detector Selection meeting |
| Task Description: |  |  |
| Design of calibration/evaluation facility Construction of calibration/evaluation facility Testing of calibration/evaluation facility Delivery of calibration/evaluation facility “copies” to array providers Testing and evaluation of candidate array technologies Provision of test reports to consortium/array selection team. |
| Milestones: |  |  |
|  | Date | Description |  |
| M01 | 16 Oct 98 | Mirrors to QMW |  |
| M02 | 30 Oct 98 | Calibration module stray light analysis results from RAL |  |
| M03 | 30 Oct 98 | Calibration module electrical interface specifications from QMW (document) |  |
| M04 | 6 Nov 98 | Final engineering drawings of calibration module to RAL |  |
| M05 | 18 Nov 98 | Connectors delivered |  |
| M06 | 26 Nov 98 | He-3 fridge tests complete |  |
| M07 | 26 Nov 98 | Delivery of US He-3 fridges & shields to GSFC & JPL |  |
| M08 | 27 Nov 98 | Filters complete |  |
| M09 | 18 Dec 98 | Cryostat to QMW |  |
| M10 | 24 Dec 98 | Illuminator arrays to QMW |  |
| M11 | 31 Dec 98 | Construction of calibration modules |  |
| M12 | 29 Jan 99 | Calibration module tests completed |  |
| M13 | 29 Jan 99 | Delivery of calibrated calibration modules to GSFC & JPL |  |
| M14 | 1 Sep 99 | Delivery of Pop-Up Detector Evaluation Array to QMW |  |
| M15 | 1 Sep 99 | Delivery of Feedhorn Evaluation Array to QMW |  |
| M16 | 1 Nov 99 | Delivery of CEA Evaluation Array to QMW |  |
| M17 | 31 Dec 99 | Evaluation of prototype detector arrays completed |  |

| SPIRE | Work Package Description | WP No: |  |
| --- | --- | --- | --- |
|  |  | Sheet: | 2 of 2 |
| Title: | Array Evaluation Facility | Issue: | .01 (draft) |
| Start Event: End Event: | Detector Selection | Assigned to QMW |
| Inputs: |  |  |
|  | Date | Item | From |
| I01 | 10 Oct 98 | Bolometer for characterisation of calibration module stray light environment | JPL |
| I02 | 16 Oct 98 | Mirrors | Symons Mirror Technology |
| I03 | 30 Oct 98 | Verification of stray light analysis for calibration module | RAL |
| I04 | 2 Nov 98 | He-3 fridge | Chase Research |
| I05 | 18 Nov 98 | Hermetic Connectors | Ultratech |
| I06 | 26 Nov 98 | He-3 fridge test results | QMW |
| I07 | 27 Nov 98 | Filters | QMW |
| I08 | 18 Dec 98 | Cryostat | Precision Cryogenics |
| I09 | 24 Dec 98 | Illuminator arrays | GSFC |
| I10 | 1 Sep 99 | Feedhorn Evaluation Array | JPL |
| I11 | 1 Sep 99 | Pop-Up Detector Evaluation Array | GSFC |
| I12 | 1 Nov 99 | CEA Detector Evaluation Array | SAp |
| Outputs: |  |  |
|  | Date | Item | To |
| O01 | 30 Oct 98 | Calibration module electrical interface specifications | GSFC, JPL |
| O02 | 6 Nov 98 | Final engineering drawings of calibration module | RAL |
| O03 | 26 Nov 98 | He-3 refrigerators | GSFC, JPL |
| O04 | 29 Jan 99 | Calibration Module Performance Report | GSFC, JPL |
| O05 | 29 Jan 99 | Calibrated Calibration Modules | GSFC, JPL |
| O06 | 31 Dec 99 | Array Evaluation Report | SPIRE |

# Schedule

## Detector Selection Schedule

## PUD Array Development Schedule

## Feedhorn Array Development Schedule

## CEA Detector Development Schedule

## Evaluation Facility Schedule

## Array Evaluation Schedule

# Milestones