SPIRE Warm Electronics Group Meeting #2.

May 6, 1999

CEN Saclay - SAp

Attendees:

IFSI: R.Cerulli, R.Orfei

LAS : D.Ferrand, D.Pouliquen

SAp : J-L.Auguères, C.Cara, L.Rodriguez

RAL : K.King

SO  : H.G.Floren

Distribution list:

Attendees + C.Cunningham, W.Gear, M.Griffin, B.Swinyard, L.Vigroux

+ F.Loubère, I.Perez, J.Herreros

0. Agenda of the meeting

9.30 Review of the agenda			            JLA      10'

9.40 Managerial issues

- Action review                                JLA      15'

- SPIRE Project info                            KK      15'

- Institute Progress report:

. IAC                                         JH       5'

. IFSI                                        RC       5'

. LAS                                         DP       5'

. SAp                                        JLA       5'

. SO (full status)                           HGF      10'

10.40 SPIRE System status                            LR/BS    20'

11.00 WE Quality Assurance.

- SPIRE QA Plan                               KK/GD     10'

- WE QA progress report                      FL(JLA)     5'

11.15 Coffee break

11.30 WE system issues.

- Review and discussion about the existing    JLA/CC    90'

and missing WE requirements

14.00 WE functional analysis.                           CC    90'

- Discussions on the Instrument status diagram.

- WE functionality to be fulfilled to meet
        the WE requirements.

16.20 Short term planning (building and discussions) JLA/KK   20'

16.40 DPU/SPU option status

- Outcomes of the last Steering Group meeting    KK     10'

- Other inputs since the last meeting:
        . IFSI and IAC comments.                       RC     10'
        . MMS CPU board: info collected so far,        CC     15'

possible impact on the SPIRE WE.

17.15 AOBs

17.30 End of meeting.

1. Review of the agenda.

- The DPU/SPU option status point has been added to the original proposal.

- No further comments.

2. Action review.

- WEG meeting #1 - Saclay - March 24-25, 1999

| Action 1 | KK |  | Open | to issue a note stating both objectives and expected inputs for the Sept. 99 PDR. |
| --- | --- | --- | --- | --- |

Not done yet. KK committed himself to produce the note at short notice.

| Action 2 | KK |  | Closed | to talk with the other project manager about design synchronisation of the different groups. |
| --- | --- | --- | --- | --- |

KK discussed with H.Bauer: PACS is working on no clear general requirements. The synchronisation of the designs is likely a vain hope. The action is therefore considered as closed.

| Action 3 | KK |  | Closed | to contact SO to asses the situation. |
| --- | --- | --- | --- | --- |

Closed. See SO reporting section hereafter.

| Action 4 | IAC/JH |  | Closed | to check the Model table figures for the SPU. |
| --- | --- | --- | --- | --- |

No inputs from IAC. Action considered as closed.

| Action 5 | System team |  | Open | to perform a risk analysis. |
| --- | --- | --- | --- | --- |

Still Open. A "Risk Analysis" item will be set up in the May 19 System Meeting agenda (LR).

| Action 6 | KK |  | Open | to boost the SPIRE QA activity. |
| --- | --- | --- | --- | --- |

KK confirmed that no QA specific activity is planned at this stage.

JLA pointed out that the SPIRE QA policy based on "laisser faire" is not suitable and that for the sake of the project, the QA team has to participate from the earliest stage. Groups like SAp are used to deal with QA but it is certainly NOT the case with other groups participating in SPIRE. The present QA document has to be adapted to SPIRE (not simply copied from a former project) and QA activities (like participation in the preparation of the SPIRE reviews) shall exists. Furthermore, QA has to be co-ordinated  the same way as it is for the Project Management.

KK agreed to reconsider the QA issue. The action is still considered as Open

| Action 7 | RAL/GD | asap | Open | Issue the SPIRE Quality Requirements |
| --- | --- | --- | --- | --- |

See comment on previous action. Action still Open.

| Action 8 | KK | asap | Deleted | Provide the list of documents to be produced for the PDR |
| --- | --- | --- | --- | --- |

Same as action 1. This action is deleted.

| Action 9 | SAp/FL | 04/99 | Open | Produce the first issue of the Warm Electronics Product Assurance Plan |
| --- | --- | --- | --- | --- |

Started but not completed. Delay due to the present uncertainties on the WE team organisation.

| Action 10 | SAp/FL | 05/99 | Open | Produce the first issue of the Warm Electronics Quality requirements. |
| --- | --- | --- | --- | --- |

Ditto Action 9.

| Action 11 | WE Inst. | asap | Closed | Appoint a Quality Manager (or correspondent) |
| --- | --- | --- | --- | --- |

The QA Managers are:

IFSI	: R.Orfei
	LAS	: D.Pouliquen
	SO	: H.G.Floren
	IAC	: J.Herreros
	SAp	: F.Loubère

| Action 12 | WE Inst. | 06/99 | Open | to produce their Product Assurance Plans. |
| --- | --- | --- | --- | --- |

| Action 13 | JLA |  | Closed | to complete and circulate the note on DPU/SPU vs. DPU options. |
| --- | --- | --- | --- | --- |

Done.

| Action 14 | System Team |  | Open | to produce redundancy requirements at system level. |
| --- | --- | --- | --- | --- |

Still Open. A "Redundancy Analysis" item will be set up in the May 19 System Meeting agenda (LR).

- SAp/IAC meeting - IAC - Nov. 16, 1998

| Action 1 | IAC/JH |  | Open | Draft an SPU Development Plan |
| --- | --- | --- | --- | --- |

In a waiting state due to the ongoing discussions on SPU/DPU architecture.

- Warm electronics & S/W working group splinter meeting (SPIRE Consortium Meeting - RAL - Dec. 1-2, 1998)

| Action 2 | BMS | 20/01/99 | Open | To respond the essential input request list. |
| --- | --- | --- | --- | --- |

Open. JLA/CC will re-issue the list to BS and KK.

KK pointed out that a Chopper Specification document exists.

| Action 3 | KJK | 15/12/99 | Open | To provide a Development Plan containing AIV information as well.. |
| --- | --- | --- | --- | --- |

A new draft of the IDP will be issued by KK by the end of May.

| Action 4 | SAP/LR | 15/01/99 | Closed | To draft a skeleton of the electronics specifications with the electronics requirements identified so far. |
| --- | --- | --- | --- | --- |

Closed. JLA presented a draft (see viewgraphs). This draft will be circulated for comments at short notice.

- SAp/IFSI meeting - IFSI - Feb. 16, 1999

| Action 1 | KJK | asap | Deleted | To provide asap a reasonably stable version of the SPIRE development plan (including schedule and a flow diagram). |
| --- | --- | --- | --- | --- |

Deleted. This still Open action is the same as the above Action 3.

| Action 2 | IFSI & SAp | 15/03/99 | Open | Comment the preliminary draft of the SPIRE Development Plan. |
| --- | --- | --- | --- | --- |

Awaiting for the completion of the above Action 3.

- CWG #4 - Feb. 10, 1999

| Action 3 | JLA | 20/05/99 | Open | SPIRE to confirm allocation of responsibilities for SPU h/w & s/w implementation. |
| --- | --- | --- | --- | --- |

It is likely that this action cannot be completed on time.

| Action 5 | IRC (*) | 06/05/99 | Open | Generate and Co-ordinate "requirements" on instrument commanding & verification. |
| --- | --- | --- | --- | --- |

A draft addressing very general issues has been circulated amid the WEG (no particular comments received yet).

| Action 7 | RC/JLA | 06/05/99 | Open | Define OBSW related milestones and activities till end 99. |
| --- | --- | --- | --- | --- |

It is likely that the OBSW activity will not be started by the end of the year.

| Action 8 | KK | 06/05/99 | Open | Provide comments to Appendix 1 of Mission Operation Scenario. |
| --- | --- | --- | --- | --- |

- CWG #3 - Feb. 3, 1999

| Action 3 | KK | 19/05/99 | Open | Provide plans for ILTs, indicating required deliveries (S/C simulator, CCE,...) |
| --- | --- | --- | --- | --- |

| Action 8 | KK | 30/04/99 | Open | Comment on PACS RTA requirements used for SCOS testing. |
| --- | --- | --- | --- | --- |

| Action 9 | KK | 05/03/99 | Open | To supply estimates of manpower available for RTA related activities. |
| --- | --- | --- | --- | --- |

- CWG #1 #2 - March 3, 1999

| Action 1 | RO | 25/05/99 | Open | Submit list of needed common parts. |
| --- | --- | --- | --- | --- |

CC will provide a list to ESA (Passvogel).

3. SPIRE project info (KK). (see meeting's Viewgraphs)

- Presentation of the short term schedule.

- Fax sent by ESA calling for Instrument Science Verification. For SPIRE, documentation should be handed out by mid August and the Review Board Meeting to take place on Sept. 10.
Comment expected by May 20th.

- Status:
- Development plan: Inputs from only 1 group.
- Inst. requirement document: No comment received so far.
- Qualification Plan: No comment received so far.



KK expressed concerns on the poor participation of the SPIRE groups in the elaboration of the SPIRE high level documents. He pointed out that these documents are part of the PDR documentation package.

- Presentation of the Meeting list (passed and ahead till the end of the year).
Remark: Peak Up mode issues will be addressed at he FIRST AOCS to Inst. I/F meeting.

4. PACS and SPIRE science co-ord. meeting. report (LR)

- It has been required that the Surveys could be performed as fast as possible. As a consequence, it is envisaged to increase the FOV size from 4x4 to 8×4 arc min.

- FTS FOV should not be modified.

- Extending the FTS range to shorter wavelength not accepted. However, strong pressures are remaining to extend the FTS capabilities toward 150 microns. This new feature will have heavy consequences on position accuracy and data rates. As a consequence: LVDT cannot be used any longer. Other solutions have to be investigated (0.1 micron needed). Further studies will be carried out in the coming months.

5. Institute Progress reports.

5.1 IFSI (RC). (see meeting's Viewgraphs)

- The main IFSI activity is the preparation for the ITT.
Specification have to be discussed and then issued. The ITT bears on the S/C interface and  CPU + Memory whereas the Instrument I/Fs are likely to be developed by IFSI.

- Description of the Low and high rate interfaces to the SPU (or DRCU):
KK : What happens if SPIRE don't agree with the interface 
     presented.
RC : IFSI is prepared to design dedicated interfaces if necessary.
JLA: Questioned about the internal communication reliability. The
     presented protocols do not include any error detection and/or 
     recovery. Error consequences have to be analysed in any 
     case.
CC : Low speed link could be OK but the problem is not so clear 
     with the High Speed link.

- A diagram showing the DPU board memory organisation has been presented as well.

5.2 LAS (DP).

- The preparation of the ITT is the main goal. DF worked out on various sketches but a lot of questions are still pending on the FTS mirror moving system requirements. As a consequence a lot of technical solutions are still thinkable.

- DF pointed out that FTS requirement could have impacts on AOCS requirements in turn.

- LAS/SAp discussions on FTS Electronics interface took place at the end of the meeting and are reported in a dedicated section hereafter.

5.3 SAp (JLA,CC).

The SAp activities regarding the WE are the following:

- Development of Test electronics for the detector evaluation (CEA).

- Review of incoming documents.

- Possible DRCU configuration against detector types.

5.4 SO (HGF).

- Presentation of SO s/w development experiences.

- Funding issue: depends on other projects. The simulator S/W will be developed by HGF.

- SO involvement: HGF stressed that SO cannot be involved in h/w development (even PC interfaces) and that SO participation will be limited to simulator s/w development.
It has been considered whether IFSI could provide the necessary h/w interface as they are likely needed for DPU interface testing.

- JLA : questioned about the reasons of the relative discretion of 
      SO on the project so far.
HGF : replied that SO was waiting from inputs from SPIRE to know 
      what SO are required to deal with.
JLA : pointed out that at this definition stage (as well as in the 
      further ones) an active participation of all the WE group
      members is highly desirable.

5.5 IAC

IAC was not represented at this meeting.

6. QA Activity (FL) (see meeting's Viewgraphs)

- JLA reported on QA activity in lieu of FL who was not available.

- The SAp expressed concerns on SPIRE QA activity (see the comments on the Action #6 of the previous meeting).

7. WE requirements (JLA) (see meeting's Viewgraphs)

- JLA presented the preliminary draft of the WE Requirement documents. These requirements are stemming from various existing high level documents but mainly from the draft of the Instrument Requirement Document recently issued by B.Swinyard.

- The WE preliminary draft will be circulated for comment.

Action #1 - JLA - asap.
   Circulate the preliminary draft of the WE Requirement Document.

- Main comments:

Switch on requirements: several possibilities are thinkable. For instance: the OBDH switch on the DPU (cold DPU redundancy to be considered), the DPU start the switching on of the various Instrument subsystems (ESA is providing several 28V independent lines).

Operation mode shall include all the observation modes plus some of the technological modes.

Some of the modes (like peaking up) could have to interact with the S/C. In this case, they could belong to a different category.

The "Real-Time" commanding mode has to be dropped but a "SAFE" mode is to be considered.

"Time Tagged" commands have no longer to be considered (directly handled at S/C level).

8. Products & Tests vs. Models (JLA)

- The table has been slightly updated. See attachment hereafter.

9. WE functional analysis (CC) (see meeting's Viewgraphs)

Due to Time shortage, not all the Viewgraphs prepared by CC could be presented. They all have been however bundled in the Viewgraph bunch.

- Presentation of an overall WE electronics functional diagrams.

- Presentation of an overall WE interface diagram.

10. DPU/SPU options.

- KK summarised the outcomes of the last steering group meeting on that subject (see the minutes issued by M.Griffin as well).

- Three Options are still considered:

A- the current baseline.
B- IFSI provide boards to IAC who is in charge to incorporate the  
   DPU functionality into the SPU (Comment (JLA): this option 
   suppose (among others) that the IFSI boards can handle enough 
   RAM). In this option the DPU disappears.
C- The SPU functionality are integrated in the DRCU by SAp. In 
   this case, the DPU remains as defined in the Baseline and IAC 
   no more contribute to the WE.

- CC provided information on an MMS board which has been developed in the framework of the "Columbus" project (among else) and which could be suitable for the DPU and/or the SPU (integrated or not to the DRCU).

This board is based on a SPARC chipset and is commercially available in a Mil-B version.

A meeting with MMS has been planned on May 7 at Saclay. Outcomes will be circulated within the WE group asap.

11. FTS Electronics interface.

- Discussions on FTS electronics interface between LAS (DP, DF) and SAp (CC, JLA) took place at the end of the meeting.

- The definition criteria are the following:
- The I/F shall be as simple as possible whereas being 
  capable to cope with most of the still open possibilities.
- Shall permit as far as possible to the LAS to carry out the 
  development almost without interaction with the rest of the WE
  (the realisation of this subsystem will be subcontracted).

- Considered solution:
Considering that the FTS moving system will be in any case driven by a set of values (i.e. a 40.000 point table) we came to the conclusion that:

- The values (16 bits TBC) will be provided by the DRCU (one by one on request (interrupt every ms. or so) or as a whole set.
- The values will be calculated onboard (or preloaded). The LAS will provide either the computation algorithm or the tables (or set of tables or whatever combination of the both).

This solution allows the LAS to develop and test independently the FTS mirror moving system using a DRCU simulator (a PC with a dedicated I/F board). Once the FTS moving subsystem tuned, the LAS will pass the information necessary to develop the driving s/w to the SAp. I/F testing should be simplified.

12. Next WEG meeting.

Given the already planned meeting schedule, the present workload and the uncertainties bearing on the WE architecture, a date could not be chosen for the next meeting.

Action List:

- WEG meeting #2 - Saclay - May 6, 1999

| Action 1 | JLA | asap | Open | Circulate the preliminary draft of the WE Requirement Document. |
| --- | --- | --- | --- | --- |

- WEG meeting #1 - Saclay - March 24-25, 1999

| Action 1 | KK |  | Open | to issue a note stating both objectives and expected inputs for the Sept. 99 PDR. |
| --- | --- | --- | --- | --- |
| Action 5 | System team |  | Open | to perform a risk analysis. |
| Action 6 | KK |  | Open | to boost the SPIRE QA activity. |
| Action 7 | RAL/GD | asap | Open | Issue the SPIRE Quality Requirements |
| Action 9 | SAp/FL | 04/99 | Open | Produce the first issue of the Warm Electronics Product Assurance Plan |
| Action 10 | SAp/FL | 05/99 | Open | Produce the first issue of the Warm Electronics Quality requirements. |
| Action 12 | WE Inst. | 06/99 | Open | to produce their Product Assurance Plans. |
| Action 14 | System Team |  | Open | to produce redundancy requirements at system level. |

- SAp/IAC meeting - IAC - Nov. 16, 1998

| Action 1 | IAC/JH |  | Open | Draft an SPU Development Plan |
| --- | --- | --- | --- | --- |

- Warm electronics & S/W working group splinter meeting (SPIRE Consortium Meeting - RAL - Dec. 1-2, 1998)

| Action 2 | BMS | 20/01/99 | Open | To respond the essential input request list. |
| --- | --- | --- | --- | --- |
| Action 3 | KJK | 15/12/99 | Open | To provide a Development Plan containing AIV information as well.. |

- SAp/IFSI meeting - IFSI - Feb. 16, 1999

| Action 2 | IFSI & SAp | 15/03/99 | Open | Comment the preliminary draft of the SPIRE Development Plan. |
| --- | --- | --- | --- | --- |

- CWG #4 - Feb. 10, 1999

| Action 3 | JLA | 20/05/99 | Open | SPIRE to confirm allocation of responsibilities for SPU h/w & s/w implementation. |
| --- | --- | --- | --- | --- |
| Action 5 | IRC (*) | 06/05/99 | Open | Generate and Co-ordinate "requirements" on instrument commanding & verification. |
| Action 7 | RC/JLA | 06/05/99 | Open | Define OBSW related milestones and activities till end 99. |
| Action 8 | KK | 06/05/99 | Open | Provide comments to Appendix 1 of Mission Operation Scenario. |

- CWG #3 - Feb. 3, 1999

| Action 3 | KK | 19/05/99 | Open | Provide plans for ILTs, indicating required deliveries (S/C simulator, CCE,...) |
| --- | --- | --- | --- | --- |
| Action 8 | KK | 30/04/99 | Open | Comment on PACS RTA requirements used for SCOS testing. |
| Action 9 | KK | 05/03/99 | Open | To supply estimates of manpower available for RTA related activities. |

- CWG #1 #2 - March 3, 1999

| Action 1 | RO | 25/05/99 | Open | Submit list of needed common parts. |
| --- | --- | --- | --- | --- |

Products & Tests vs. Models (1)

|  |  | Resp. | EM | AVM | CQM | PFM | FS | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WE UNITs |  |  |  |  |  |  |  |  |
| DPU |  |  |  |  |  |  |  |  |
|  | Electronics |  |  |  |  |  |  |  |
|  | CPU Board | IFSI | 1 | 1 | 2 | 2 | (2/3) | FS shared with other Inst. |
|  | Memory | IFSI | 1 | 1 | 2 | 2 | (2/3) |  |
|  | Power Supply | IFSI | 1 | 1 | 2 | 2 | (2/3) |  |
|  | Component Grade |  | Std | Std | Ext | Qual | Qual |  |
|  | Mechanics |  |  |  |  |  |  |  |
|  | DPU Box | IFSI | 1 | 1 | 1 | 1 | (1/2) | FS shared with other Inst. |
|  | Connectors | IFSI | X | X | X | X | X |  |
|  | S/W |  |  |  |  |  |  |  |
|  | LL s/w | IFSI | V0 | V1 | V2 | V flight | V flight |  |
|  | HL s/w | IFSI | V0 | V1 | V2 | V flight | V flight |  |
| SPU |  |  |  |  |  |  |  |  |
|  | H/W |  |  |  |  |  |  |  |
|  | CPU Board | IAC | 1 | 1 | 2 | 2 | 1 |  |
|  | Memory | IAC | xMo | xMo | 2*(xMo) | 2*(xMo) | xMo |  |
|  | Power Supply | IAC | 1 | 1 | 2 | 2 | 1 |  |
|  | Component Grade |  | Std | Std | Ext | Qual | Qual |  |
|  | Mechanics |  |  |  |  |  |  |  |
|  | SPU Box | IAC | 1? | 1 | 1 | 1 | (1/2) | FS shared with other Inst. |
|  | Connectors | IAC | X | X | X | X | X |  |
|  | S/W |  |  |  |  |  |  |  |
|  | LL s/w | IAC | V0? | V1? | V2? | V flight | V flight |  |
|  | HL s/w | SAp | V0? | V1? | V2? | V flight | V flight |  |
| DRCU |  |  |  |  |  |  |  |  |
|  | Electronics |  |  |  |  |  |  |  |
|  | Detector Readout | SAp | 1 | - | 1 | 1 | 1 |  |
|  | FTS Control | LAS | 1 | - | 2 | 2 | 1? |  |
|  | Cryo Control | SAp | 1 | - | 2 | 2 | 1? |  |
|  | Chopper Control | SAp | 1 | - | 2 | 2 | 1? |  |
|  | Calib. Source Control | SAp | 1 | - | 2 | 2 | 1? |  |
|  | H/K readout | SAp | 1 | - | 2 | 2 | 1? |  |
|  | Component Grade |  | Std | - | Mil | Qual | Qual |  |
|  | Mechanics |  |  |  |  |  |  |  |
|  | DRCU Box | SAp | 1 | - | 1 | 1 | 1 |  |
|  | Connectors | SAp | X | X | X | X | X |  |
| BAU |  |  |  |  |  |  |  |  |
|  | Electronics |  |  |  |  |  |  |  |
|  | Buffers | SAp | 1 |  | 1 | 1 | 1 |  |
|  | Temp. Regulation | SAp | 1 |  | 1 | 1 | 1 |  |
|  | Component Grade |  | Std |  | Mil | Qual | Qual |  |
|  | Mechanics |  |  |  |  |  |  |  |
|  | BAU Box | SAp | 1 | 2 | 2 | 2 | 1 |  |
|  | Connectors | SAp | X | X | X | X | X |  |
| Harness |  |  |  |  |  |  |  |  |
|  | DPU to SPU | SAp | 1 | 1 | 2 | 2 | 1 |  |
|  | SPU to DRCU | SAp | 1 | 1 | 2 | 2 | 1 |  |
|  | DRCU to BAU | SAp | 1 | - | 2 | 2 | 1 |  |

Products & Tests vs. Models (2)

|  |  | Resp. | EM | AVM | CQM | PFM | FS | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Simulators |  |  |  |  |  |  |  |  |
| FPU Simulator |  |  |  |  |  |  |  | Developed by CEA/SIG |
|  | Electronics | SAp | 1 |  |  | 1 |  |  |
|  | Mechanics | SAp | 1 |  |  | 1 |  |  |
| DRCU Simulator |  |  |  |  |  |  |  |  |
|  | H/W |  |  |  |  |  |  |  |
|  | Station | SO | 2 | 1 |  |  |  |  |
|  | Elect. Interface | SO | 2 | 1 |  |  |  |  |
|  | S/W |  |  |  |  |  |  |  |
|  | Simulation S/W | SO | V0 | V1 | V2 |  |  |  |
| Test Facilities |  |  |  |  |  |  |  |  |
| EGSE |  |  |  |  |  |  |  |  |
|  | Station | Can. | 4 |  |  |  |  |  |
|  | Elect. Interface | Can. | 4 |  |  |  |  |  |
| Local Test Unit |  |  |  |  |  |  |  | Developed by CEA/SIG |
|  | Station |  | 2 |  |  |  |  |  |
|  | Elect. Interface |  | 2 |  |  |  |  |  |
| Test Facility S/W |  |  |  |  |  |  |  |  |
|  | OBDH Interface Emulation | SIG | 1 |  |  |  |  | Local Test Unit |
|  | RTA Common | RAL | 1 |  |  |  |  |  |
|  | RTA Specific | RAL | 1 |  |  |  |  |  |
|  | QLA | RAL | 1 |  |  |  |  |  |
|  | Telecom. Generation Tool | RAL | 1 |  |  |  |  |  |
| Tests |  |  |  |  |  |  |  |  |
|  | EMC |  |  |  |  |  |  |  |
|  | Thermal Vacuum |  |  |  |  |  |  |  |
|  | Vibration |  |  |  |  |  |  |  |