## Mass (FOB)
Mass Budget FOB | V3.0 | 2001-03-15 |  | Custodian: | Colin Cunningham
All subsystems include fasteners & their harness in mass estimates, except detector boxes
Items | Respons-ible | Temp. K | Mass Estimate | Allocation | Difference | Contingency % | Inc Contingency
Mirrors | LAM | 4 | 1019 | 1020 | 1 | 10 | 1122
Mirrors | LAM | 2 | 348 | 350 | 2 | 10 | 385
Filters | QMW | 4 | 8 | 10 | 2 | 10 | 11
Filters | QMW | 2 | 539 | 540 | 1 | 20 | 648
Detectors | JPL | 2 | 1680 | 1800 | 120 | 0 | 1800
Thermal Straps | MSSL | 4 | 0 | 0 | 0 | 0 | 0
Thermal Straps | MSSL | 2 | 282 | 285 | 3 | 20 | 342
Cooler | CEA | 4 | 1400 | 1400 | 0 | 10 | 1540
Cooler Straps | MSSL | 2 | 235 | 235 | 0 | 20 | 282
Baffles | MSSL | 4 | 2420 | 2420 | 0 | 20 | 2904
Baffles | MSSL | 2 | 0 | 0 | 0 | 0 | 0
Calibration Source | QMW | 4 | 30 | 30 | 0 | 20 | 36
Detector Harness | JPL | 4 | 1275 | 1300 | 25 | 0 | 1300
BSM (& support) | ATC | 4 | 1100 | 1100 | 0 | 20 | 1320
Shutter | USK | 4 | 200 | 200 | 0 | 20 | 240
Non- bolometer RF Filters & Box | JPL | 4 | 1720 | 1720 | 0 | 0 | 1720
Cover | MSSL | 4 | 7640 | 7650 | 10 | 10 | 8415
Detector Box | MSSL | 2 | 1840 | 1850 | 10 | 10 | 2035
Mounts,clamps | MSSL |  | 1310 | 1310 | 0 | 10 | 1441
TOTAL |  |  | 23046 | 23220 | 174 |  | 25541
Mirrors | LAM | 4 | 1312 | 1320 | 8 | 10 | 1452
Filters | QMW | 4 | 65 | 65 | 0 | 10 | 71.5
Filters | QMW | 2 | 2 | 2 | 0 | 10 | 2.2
Detectors | JPL | 2 | 897 | 1200 | 303 | 0 | 1200
Baffles | MSSL | 4 | 0 | 0 | 0 | 0 | 0
Harness | JPL | 4 | 200 | 200 | 0 | 0 | 200
Mechanism | LAM | 4 | 1100 | 1100 | 0 | 20 | 1320
SMECp | LAM | 4 | 200 | 200 | 0 | 20 | 240
Cover | MSSL | 4 | 6880 | 6880 | 0 | 10 | 7568
Detector box | MSSL | 2 | 1350 | 1350 | 0 | 10 | 1485
Mounts,clamps | MSSL |  | 860 | 860 | 0 | 10 | 946
Calibration Source | QMW | 4 | 200 | 200 | 0 | 20 | 240
TOTAL |  |  | 13066 | 13377 | 311 |  | 14724.7
Optical Bench | MSSL | 4 | 8000 | 8000 | 0 | 10 | 8800
Mounting | MSSL | 4 | 540 | 540 | 0 | 10 | 594
RF seal | MSSL | 4 | 0 | 0 | 0 | 0 | 0
Cooler I/F | MSSL | 4 | 100 | 100 | 0 | 20 | 120
Strap Baffles | MSSL | 4 | 500 | 500 | 0 | 20 | 600
JFET I/F structure | MSSL | 4-11 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 9140 | 9140 | 0 |  | 10114
TOTAL FPU |  |  | 45252 | 45737 | 485 |  | 50379.7
Request to ESA (8/6/00) |  |  |  | 45000 |  | 20 | 54000
Offer by ESA (8/6/00) |  |  |  | 42000 |  | 20 | 50400
JFET Box | JPL | 11 | 6990 | 7000 | 10 | 10 | 7700
TOTAL FTB |  |  |  |  | 10 | 10 | 7700 |  | 0
Request to ESA (8/6/00) | [5 empty] | 6500 |  | 20 | 7800
Offer by ESA (8/6/00) | [5 empty] | 6000 |  | 20 | 7200
Note on A42: CRC: Not in detailed estimates:
Note on A43: CRC: not in detailed estimates
Note on A44: CRC: not in detailed estimates
Note on G4: CRC: in case of design change to telescope
Note on G17: CRC: Reduce to 20% after FEA
Note on G8: CRC: JPL hold contingency
Note on G16: CRC: JPL hold contingency
Note on D44: Colin Cunningham: Does this exist?
Note on D49: Colin Cunningham: Need updated structure estimates

## Detail (FOB)
Mass estimate | V3.0 | Bruce Swinyard & Colin Cunningham |  |  | 2001-03-15
Includes Structure estimates: v1.3
Mass estimate of new photometer spectrometer layout using mirror sizes+20% and aspect ratio of 6:1 for small mirrors and 12:1 for big ones.
Photometer Hardware:
Mirrors | Est. Mass | Temp
CM3 | 276 | 4
CM4 | 0 | 4
CM5 | 360 | 4
PM6 | 27 | 4
PM7 | 300 | 4
PM8 | 56 | 4
PM9 | 223 | 2
PM10 | 65 | 2
PM11 | 60 | 2 | 1367
Filters
CFIL-1 | 5 | 4
PFIL-2 | 3 | 4
PFIL-3 | 2 | 2
PDIC-1 | 287 | 2
PDIC-2 | 250 | 2
Detectors
3 arrays | 1680 | 2
Thermal Straps
4-K Deleted Item | 0 | 4
2-K structure Detector Boxes | 172 | 2
2-K cooler | 110 | 2
Cooler
Cooler | 1400 | 4 | Increased at interface review 28/11/00 to allow 6 litre
Thermal Straps (busbar) | 235 | 2
Baffles (common)
Baffles | 2420 | 4
Photometer Calibrator | 30 | 4
Harness
Array Harness 800 | 775 | 4
The rest of the common harness 500 | 500 | 4
BSM
BSM Mech and bracket | 1100 | 4
Shutter
Shutter mech and mount | 200 | 4
Rf Filters | 1720 | 4
Phot Structure
Cover | 7640 | 4
Detector Box | 1840 | 2
Mounts, Clamps | 1310
Total Phot. | 23046
23046
Spectrometer hardware:
Mirrors | Est. Mass | Temp
SM6 | 0 | 4
SM7 | 44 | 4
SM8A | 112 | 4
SM8B | 112 | 4
SM9A | 74 | 4
SM9B | 74
SM10A | 112 | 4
SM10B | 112
SCCA | 44 | 4
SCCB | 140 | 4
SM11A | 194 | 4
SM11B | 194 | 4
SM12A | 50 | 2
SM12B | 50 | 2
Filters
SFIL-2 | 1 | 4
SBS-1 | 32 | 4
SBS-2 | 32 | 4
SFIL-3S | 1 | 2
SFIL-3L | 1 | 2
Detectors
2 arrays | 897 | 2 |  | 2577
Baffles
2-K Baffles - none | 0 | 2
Harness
Array Harness 150 wires | 200 | 4
4
Mechanism
Structure | 600 | 4
Motor | 500 | 4
SMECp | 200 | 4 | Added at interface review 29/11/00
Calibration source
Source and mount | 200 | 4
Structure
Spec. Cover | 6880 | 4
Spec. detector box | 1350 | 2
Mounts, clamps | 860
Total Spect. | 13066
13066
Common Structure
Optical Bench | 8000 | 4
Mounting | 540 | 4
RF seal (or mesh?) | 250 | 4
Thermistors, conns, wires | 50
Total Common | 8840
8840
Total Hardware | 44952 |  |  |  | 4-K Mass |  | 2-K Mass
With cont. | 53942.4 |  |  | Phot 4K | 6140.2547 | Phot 2K | 3460.5088
|  |  |  | Spect 4K | 2478.3343 | Spect 2K | 1300
JFET Modules Phot | 4270 |  |  | Total HW 4K | 8618.5891 | Total HW 2K | 4760.5088
JFET Modules Spec | 1220
JFET Phot Structure | 1000
JFET Spec Structure | 500 |  |  | Total HW + Cover | 8618.5891 | Total HW +cover | 4760.5088
| 6990 |  |  | Total with cont. | 10342.3069 |  | 5712.6106
With cont | 8388
What we told ESA now including JFET Box | 40990
With cont | 49188
Structure Alloc. | -8232 |  | Total cold FPU no contingency | 36720
With cont | -5254.4 |  | Total cold FPU with contingency | 44064
Likely Structure+fasteners | 25000 |  | Cold FPU Likely total | 69952
Note on A35: CRC: Inserted
Note on A77: CRC: Added
Note on B17: Colin Cunningham: Email from Pete Hargrave 5/2/01
Note on B19: Colin Cunningham: Email PH 5/2/01
Note on B20: Colin Cunningham: EMAIl PH 5/2/01
Note on B21: Colin Cunningham: Email PH
Note on B22: Colin Cunningham: Email PH
Note on A19: Colin Cunningham: Was CFIL-2 Email PH 5/2/01
Note on A68: Colin Cunningham: New filter at Pupil on SOB Email PH 5/2/01
Note on A69: Colin Cunningham: was SBDI-1
Note on A70: Colin Cunningham: was SBDI-2
Note on B69: Colin Cunningham: Email PH 5/2/01
Note on B70: Colin Cunningham: Email PH 5/2/01
Note on B71: Colin Cunningham: Email PH 5/2/01
Note on B72: Colin Cunningham: Email PH 5/2/01
Note on B7: test2: Ref Mirror Spec LAM.PJT.SPI.SPT.200007 Ind 2
Note on B8: test2: Included in BSM
Note on B52: test2: Subject to change
Note on A65: test2: Not in Original Design
Note on A66: test2: Not in Original design
Note on B45: CRC 15/3/01: Updated estimates 1.3
Note on B97: CRC: My estimate
Note on B76: CRC 15/3/01: None
Note on B107: CRC: Guess
Note on B108: CRC: Guess
Note on B78: CRC: Guess:

## Mass (SVM)
Mass Budget SVM | V3.0 | All in grammes |  |  |  | Custodian: | Colin Cunningham
Items | Work-package | Respons-ible | Mass Estimate | Allocation | Difference | Contingency % | Inc Contingency
Digital Processing Unit | DPU | IFSI | 6621 | 10000 | 3379 | 20 | 12000 | Estimate from Renato on 22nd Feb 01
Detector Read-out & Control Unit | DRCU | CEA | 23000 | 18000 | -5000 | 20 | 21600 | Increased at Interface review to allow 2 boxes 28/11/00
Warm Interconnect Harness | WIH | CEA | 2000 | 2000 | 0 | 20 | 2400
TOTAL |  |  | 31621 | 30000 |  |  | 36000
Request to ESA (8/6/00) |  |  |  | 30000
Offer by ESA (8/6/00) |  |  |  | 30000
Note on E4: Colin Cunningham: Reduce to 7000?
Note on G4: Colin Cunningham: Reduce to 10%?

## Thermal Load (FOB)
Thermal Loads on FOB |  |  |  |  | V3.0 | From Sam Heys
[5 empty] | 21-03-01 | current estimates + comments included by Sam
Loads in mW
Stage | Item | Mode | Estimate | Allocation | Contingency | Inc Contingency
|  |  | Update |  | %
Level 2 | JFET Box | Standby | 49.5 | 33 | 50 | 49.5
|  | OFF | 0 | 0 | 0 | 0
|  | PHOT | 49.5 | 33 | 50 | 49.5
|  | SPEC | 14.1 | 9.4 | 50 | 14.1
|  | RECYCLE | 49.5 | 33 | 50 | 49.5
Level 1 | Wires | Standby | 1.339 | 1.1 | 20 | 1.32
|  | OFF | 0.649 | 1.1 | 20 | 1.32
|  | PHOT | 1.31 | 1.1 | 20 | 1.32
|  | SPEC | 0.767 | 1.1 | 20 | 1.32
|  | RECYCLE | -
| Radiation | Standby | 0.088 | 0.1 | 0 | 0.1
|  | OFF | 0.027 | 0.1 | 0 | 0.1
|  | PHOT | 0.088 | 0.1 | 0 | 0.1
|  | SPEC | 0.04 | 0.1 | 0 | 0.1
|  | RECYCLE | -
| Mechanisms & calibrators | Standby | 0 | 0 | 0 | 0
|  | OFF | 0 | 0 | 0 | 0
|  | PHOT | 4.1 | 4.1 | 0 | 4.1 | Calibrator | 0.1 | Mech | 4
|  | SPEC | 8.4 | 8.4 | 0 | 8.4 | Calibrator | 5 | Mech | 2.4 | BSM | 1
|  | RECYCLE | -
| Structure | Standby | 10.934 | 6 | 100 | 12
|  | OFF | 5.289 | 6 | 100 | 12
|  | PHOT | 10.689 | 6 | 100 | 12
|  | SPEC | 6.345 | 6 | 100 | 12
|  | RECYCLE | -
| Total | Standby | 12.361 | 7.2 | - | 13.42
|  | OFF | 5.965 | 7.2 | - | 13.42
|  | PHOT | 16.187 | 11.3 | - | 17.52
|  | SPEC | 15.552 | 15.6 | - | 21.82
|  | RECYCLE | -
| FIRST L1 Cryostat Strap Load | Standby | 9.063
|  | OFF | 4.116
|  | PHOT | 12.229
|  | SPEC | 11.951
|  | RECYCLE | 7.222 |  |  |  | 25 | ESA Budget (average for all inst over mission)
Level 0 | Wires | Standby | 0.452 | 0.1 | 100 | 0.2
|  | OFF | 0.253 | 0.1 | 100 | 0.2
|  | PHOT | 0.538 | 0.1 | 100 | 0.2
|  | SPEC | 0.486 | 0.1 | 100 | 0.2
|  | RECYCLE | -
| Dissipation - cooler | Standby | 0 | 5 | 0 | 5
|  | OFF | 0 | 5 | 0 | 5
|  | PHOT | 0.2 | 5 | 0 | 5
|  | SPEC | 0.2 | 5 | 0 | 5
|  | RECYCLE | 2.54 | 5 | 0 | 5
| Cooler Parasitics | Standby | 0.031 | 0 | 0 | 0
|  | OFF | 0.016 | 0 | 0 | 0
|  | PHOT | 0.038 | 0 | 0 | 0
|  | SPEC | 0.034 | 0 | 0 | 0
|  | RECYCLE | - | 0 | 0 | 0
| Cooler Switch supports | Standby | 0.61 | 1 | 20 | 1.2
|  | OFF | 0.37 | 1 | 20 | 1.2
|  | PHOT | 0.714 | 1 | 20 | 1.2
|  | SPEC | 0.661 | 1 | 20 | 1.2
|  | RECYCLE | -
| Strap Feed Throughs | Standby | 1.237 | 1.5 | 0 | 1.5
|  | OFF | 0.678 | 1.5 | 0 | 1.5
|  | PHOT | 1.496 | 1.5 | 0 | 1.5
|  | SPEC | 1.356 | 1.5 | 0 | 1.5
|  | RECYCLE | -
| Structure | Standby | 0.968 | 1.1 | 20 | 1.32
|  | OFF | 0.532 | 1.1 | 20 | 1.32
|  | PHOT | 1.172 | 1.1 | 20 | 1.32
|  | SPEC | 1.064 | 1.1 | 20 | 1.32
|  | RECYCLE | -
| Total | Standby | 3.298 | 8.7 | - | 9.22
|  | OFF | 1.849 | 8.7 | - | 9.22
|  | PHOT | 4.158 | 8.7 | - | 9.22
|  | SPEC | 3.801 | 8.7 | - | 9.22
|  | RECYCLE | -
| FIRST L0 Cryostat Strap Load | Standby | 3.298
|  | OFF | 1.849
|  | PHOT | 4.1372
|  | SPEC | 3.7809
|  | RECYCLE | 15.167 |  |  |  | 10 | ESA Budget (average for all inst over mission)
300 mK | Detector Modules-kevlar | PHOT | 4.46 | 8 | uW
|  | SPEC | 4.36 | 8 | uW
| Detector Modules-harness | PHOT | 3.2 |  | uW
|  | SPEC | 3.11 |  | uW
| Cooler Parasitics | PHOT | 11.64 | 12 | uW
|  | SPEC | 11.14 | 12 | uW
| Busbar Supports | PHOT | 1.51 | 2 | uW
|  | SPEC | 1.48 | 2 | uW
| Temperature Control Headroom | PHOT | 0 | 0 | uW
|  | SPEC | 0 | 0 | uW
| TOTAL | PHOT | 20.81 | 22 | uW
|  | SPEC | 20.09 | 22 | uW
Note on E24: CRC: add BSM in fixed position
Note on L24: CRC: BSM in fixed position
Note on D40: 130 Joules in 5 hours from start of cooler recycling.
Note on D48: Heat switch power
Note on D49: Heat switch power
Note on D50: Pump Heater = 200mW for 30mins, then 25mW for 30mins. Heat Switch = 0.2mW constant. Total energy in 48 hours= 440J. Average load over 48 hours = 2.54mW
Note on E50: test2: 860 Joules total per cycle
Note on E51: Harness and kevlar parasitics - included in 5mW budget.
Note on D78: value for nominal operations (not including cooler recycling loads)
Note on D79: value for nominal operations (not including cooler recycling loads)
Note on D80: 273 Joules total down FIRST L0 straps in 5 hours from start of recycling. See strap energy profile during this time. Note: this is less than 860 Joules in 48 hours specified for cooler since: -Cooler power in TMM based on pump heater power info from Lionel (200mW for 30mins, then 25mW for 30mins = 405J). -Much of this heat is conducted to 4K stage (through heat switch supports, harness and kevlar) when pump is at ~40K.
Note on E85: CRC: Assuming 4K level 1

## Dissipation SVM
Dissipation on SVM |  |  |  |  | V2.0
Needs completion: estimates and contingency
Dissipation in W
Unit | Item | Mode | Estimate | Allocation | Contingency | Inc Contingency
FSDRC | Detector Read-out and Control Unit | All | 67 | 71 | ?
FSDPU | Digital Processing Unit | All | 10 | 15 | ?
FSWIR | Warm Interconnect Harness | All |  | 0 | ?
TOTAL |  |  |  | 86
20%?

## Data Transmission
Data Transmission |  | V2.0
All in kbps
Function | Mode | Estimate | Allocation
DCU Science | Phot | 80
MCU Science | Phot | 11
SCU Science | Phot | 1.5
DPU Science | Phot | 1.1
Housekeeping | Phot | 2
Total |  | 95.6 | 100
DCU Science | Spec | 79
MCU Science | Spec | 15.8
SCU Science | Spec | 1.5
DPU Science | Spec | 1.1
Housekeeping | Spec | 2
Total |  | 99.4 | 100

## Noise Sources
Budget for syatems noise |  | Refered to signal at detector
Source | TBD
Photon noise | TBD | Split into sources?
Bolometer | TBD | Slplit into phonon, Johson etc
Load Resistors | TBD
Bias supply | TBD
Temperature fluctuations | TBD
JFET | TBD
RF | TBD
Microphonics | TBD
Preamp | TBD
LIA | TBD
A/D quantisation | TBD