# SPIRE

| SUBJECT: | SPIRE Major Milestone ListSPIRE Major Milestone List |
| --- | --- |
| PREPARED BY: | K.J. KingK.J. King |
| DOCUMENT No: | SPIRE-RAL-PRJ-000455SPIRE-RAL-PRJ-000455 |
| ISSUE: | 1.3 Draft11.3 Draft1 | Date: | 31st January 2002 |
| CHECKED BY: | …………………………………. | Date: | …………………………. |
| APPROVED BY: | …………………………………. | Date: | …………………………. |

Distribution

| Instrument Development Manager |  |
| --- | --- |
| Local Project managers |  |

# Change Record

| ISSUE | DATE |  |
| --- | --- | --- |
| Issue 1.0 | 17th July 2000 | Initial Issue for Delta PDR |
| Issue 1.1 (Draft1) | 2nd August 2000 | Includes milestones for revised model philosophy |
| Issue 1.2 Draft1 | 25th February 2001 | Updated Milestones following MSSL delivery schedule |
| Issue 1.2 Draft2 | 12th April 2001 | Updated following consolidation of Subsystem Schedules |
| Issue 1.3 Draft1 | 31st January 2002 | Updated following Subsystem DDRs |

# Glossary

| AVM | Avionics Model |
| --- | --- |
| BDA | Bolometer Detector Array(s) |
| BSM | Beam Steering Mirror |
| CQM | Cryogenic Qualification Model |
| DM | Development Model |
| DPU | Digital Processing Unit |
| DRCU | Detector Readout and Control Unit |
| EGSE | Electrical Ground Support Equipment |
| FS | Flight Spare (Model) |
| FTB | FET Box |
| FPU | Focal Plane Unit |
| MCU | Mechanisms Control Unit |
| OGSE | Optical Ground Support Equipment |
| PCAL | Photometer Calibrator |
| PFM | Proto-Flight Model |
| QM | Qualification Model |
| SCAL | Spectrometer Calibrator |
| SMEC | Spectrometer MEChanism |
| SPIRE | Spectral and Photometric Imaging REceiver |
| STM | Structural Thermal Model |
| TBD | To Be Determined |
| WE | Warm Electronics |
| WIH | Warm Interconnect Harness |

# References

# Introduction

This document provides a list of the Major SPIRE milestones. This includes all delivery dates to ESA, all internal review dates and all delivery dates between SPIRE Responsible Organisations.

Once agreed this document will be the controlling document for the SPIRE instrument schedule and will be updated in line with agreed changes to the schedule.

## Applicable Documents

## Reference Documents

| RD1 | Structure Subsystem Development Plan (SPIRE-MSS-PRJ-000426) Issue 1.2 |
| --- | --- |
| RD2 | SPIRE Mirrors and Alignment Tools Development Plan (SPIRE-LAM-PRJ-000474) Issue 3.0 |
| RD3 | SPIRE BSM Development Plan (SPIRE-ATC-PRJ-000466) v 5.0 |
| RD4 | Herschel-SPIRE Business agreement (SPIRE-UCF-PRJ-000822) Issue 2.0 |
| RD5 | Filters Subsystem Development Plan (SPIRE-UCF-PRJ-000453) Issue 2.0 |
| RD6 | Calibrators Subsystem Development Plan (SPIRE-UCF-PRJ-000467) Issue 1.0 |
| RD7 | Spectrometer Mirror Mechanism Subsystem Development Plan (SPIRE-LAM-PRJ-000476) 16th October 2001 |
| RD8 | SPIRE and PACS Sorption Coolers Development Plan, SBT/CT/2001-19 (SPIRE-SBT-PRJ-000468) Issue 3.1 |
| RD9 | SPIRE Shutter Development Plan (SPIRE-USK-PRJ-000475) Draft 0.2 |
| RD10 | DPU/ICU Subsystem Development Plan (SPIRE-IFS-PRJ-000469) Issue 1.3 |
| RD11 | Detector Readout Control Unit and Warm Interconnect Harness Development Plan (SPIRE-SAP-PRJ-000471) Issue 2.0 |
| RD12 | CEA Product Tree (Sap-SPIRE-JLA-xxxx-00) Issue 1.0, 14 Dec 2001 |
| RD13 | Development Plan for the DRCU Simulator (SPIRE-STK-PRJ-000470) 21 December 00 |
| RD14 | SPIRE AIV Facilities Development Plan (SPIRE-RAL-PRJ-000477) Issue 1.0 |

# Milestones

## Development programme

| Milestone | Responsible | Need Date | Planned Date | Margin (days) | Comments |
| --- | --- | --- | --- | --- | --- |
| Detector Array Selection | SPIRE |  | 01/02/00 |  | Complete |
| Delta PDR | SPIRE |  | 26/06/00 |  | Complete |
| BSM Simulink Model Delivery to LAM | ATC | 11/08/00 |  |  | Complete, TBC |
| BSM Analogue Board Design Delivery to LAM | ATC | 11/08/00 |  |  | Complete, TBC |
| Instrument Interface Review | SPIRE |  | 30/11/00 |  | Complete |
| ISVR | ESA |  | 30/11/00 |  | Complete |
| BSM Analogue Board Detailed Design Delivery to LAM | ATC | 01/01/01 |  |  | Complete, TBC |
| IIDR | ESA |  | 23/04/01 |  | Complete |
| Cooler Detailed Design Review | SPIRE |  | 17/05/01 |  | Complete |
| Mirrors Detailed Design Review | SPIRE |  | 10/07/01 |  | Complete |
| BSM Detailed Design Review | SPIRE |  | 30/07/ 01 |  | Complete |
| SMEC, MCU Detailed Design Review | SPIRE |  | 22/10/02 |  | Complete |
| Structure Detailed Design Review | SPIRE |  | 29/11/01 |  |  |
| DPU, OBS Detailed Design Review | SPIRE |  | 06/12/01 |  |  |
| Shutter Detailed Design Review | SPIRE |  | TBD |  | PDR held on 17/07/01 |
| BDAs, FTB Detailed Design Review | SPIRE |  |  |  | TBD |
| DRCU Detailed Design Review | SPIRE |  |  |  | TBD |
| Filters & Calibrators Detailed Design Review | SPIRE |  |  |  | TBD |
| AIV Facility Detailed Design Review | SPIRE |  |  |  | TBD |
| EGSE#1 Delivery to IFSI | RAL | 01/06/01 | 01/05/01 | 1 month | Complete |
| DRCU Simulator#1 Delivery to IFSI | SO | 09/11/01 | 01/06/01 |  |  |
| SMECm Simulator Delivery to SAp | LAM | 09/07/01 | 21/12/01 |  | (15/10/01) v20011015 |
| DM PCAL Delivery to ATC | Cardiff | ???????? | 22/04/02 | 5 weeks | (31/01/02) v3.0 |
| IBDR | ESA |  | 05/03/02 |  |  |
| Cold BB Delivery to RAL | Cardiff | TBD | 25/06/02 | TBD | (31/01/02) v3.0 |
| AIV Filters Delivery to RAL | Cardiff | TBD | 28/05/02 | TBD | (31/01/02) v3.0 |
| FTS Delivery to RAL | Cardiff | TBD |  |  | (31/01/02) v3.0– not in schedule |
| Reference Bolometer Delivery to RAL | Cardiff | TBD |  |  | (31/01/02) v3.0– not in schedule |

## STM Programme

| Milestone | Responsible | Need Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| Test Facility Available | RAL | 16/08/02 | 01/08/02 | 2 weeks | (01/10/01) Issue 3 Rev 6 |
| CQM Structure and MGSE Delivery to RAL | MSSL | 01/07/02 | 13/08/02 |  | (Jan02 Progress Report) |
| CQM Thermal Straps Delivery to RAL | MSSL | 01/07/02 | 13/09/02 |  | (26/11/01) |
| CQM Mirrors + OGSE Delivery to RAL | LAM | 01/07/02 | 01/07/02 | 3 weeks | (30/03/01) v20010330 |
| STM Filters, Dichroics, Beamsplitters and OGSE Delivery to RAL | Cardiff | 01/07/02 | 28/06/02 | TBD | (31/01/02) v3.0 |
| STM BSMm Delivery to RAL | ATC | 01/07/02 | 01/07/02 | 4 months | (10/09/01) Jul_01g |
| CQM BSMm Harness Delivery to RAL | ATC | 01/07/02 | 01/07/02 | 4 months | (10/09/01) Jul_01g |
| Optical Dummy SMECm Delivery to RAL | LAM | 01/07/02 | 01/07/02 | 5.5 months | (30/03/01) v20010330 - CCA tools |
| HOB Simulator Available | RAL | 01/07/02 | 05/03/02 | 4 months | (01/10/01) Issue 3 Rev 6 - 'Support Frame' |
| STM Cooler Delivery to RAL | Grenoble | 01/08/02 | 09/12/01 | 6 months | (31/10/01) Dev. Plan Issue3.1 |
| CQM Cooler Harness Delivery to RAL | SAp | 01/08/02 | TBD | TBD | Identified in Product Tree, but not in schedule |
| STM BDAs Delivery to RAL | JPL | 01/08/02 | 01/08/02 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| CQM BDAs Harness Delivery to RAL | JPL | 01/08/02 | 01/08/02 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| STM Shutter Delivery to RAL | USK | 01/08/02 | 28/02/02 | 5 months | (17/07/01) |
| CQM Shutter Harness Delivery to RAL | USK | 01/08/02 | 28/02/02 | 5 months | (17/07/01) TBC - not in schedule |
| STM SCAL Delivery to RAL | Cardiff | 01/08/02 | 25/07/02 | 6 weeks | (31/01/02) v3.0 |
| STM SCAL Harness Delivery to RAL | Cardiff | 01/08/02 | 25/07/02 | 6 weeks | (31/01/02) v3.0 Assumes STM includes harness (TBC) |
| STM SMECm Delivery to RAL | LAM | 01/08/02 | 01/08/02 | 1.5 months | (15/10/01) v20011015 |
| STM SMECm Harness Delivery | LAM | 01/08/02 | 01/08/02 | 1.5 months | (15/10/01) v20011015 |
| CQM FPU RF Filter Modules Delivery | JPL | 01/08/02 | 01/08/02 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| CQM Cooler Delivery to RAL | Grenoble | 01/09/02 | 30/04/02 | 4 months | (31/10/01) Dev. Plan Issue3.1 |

| Milestone | Responsible | Need Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| CQM FTB Enclosure Delivery to RAL | MSSL | 01/08/02 | 01/02/02 |  | (jan02 Progress Report) |
| STM JFET Modules Delivery to RAL | JPL | 01/08/02 | 01/08/02 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| STM FTB RF Filter Modules Delivery to RAL | JPL | 01/08/02 | 01/08/02 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| STM Interim Review |  |  | 24/12/02 |  |  |
| Cold Vibration Campaign Starts | ESA |  | 06/03/03 |  |  |
| STM Review |  |  | 01/05/03 |  |  |
| CQM Structure and FTBs available |  |  | 02/05/03 |  |  |

## CQM Programme

| Milestone | Responsible | Need Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| CQM Cold Filters Delivery to JPL | Cardiff | 01/02/02 | 01/02/02 | TBD | (31/01/02) v3.0 |
| CQM PCAL Delivery to ATC | Cardiff | 22/03/02 | 26/07/02 | TBD | (31/01/02) v3.0 |
| CQM BSMm Delivery to LAM | ATC | 30/07/02 | 23/08/02 |  | (10/09/01) Jul_01g |
| CQM Filters Dichroics and Beamsplitters Delivery to RAL | Cardiff | 11/01/03 | 21/02/03 | TBD | (31/01/02) v3.0 |
| CQM BDAs Delivery to RAL | JPL | 11/01/03 | 11/01/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| CQM SMECm Delivery to RAL | LAM | 11/01/03 | 11/01/03 | 3.months | (15/10/01) v20011015 |
| CQM SCAL Delivery to RAL | Cardiff | 11/01/03 | 10/01/03 | 4 weeks | (31/01/02) v3.0 |
| CQM Shutter Delivery to RAL | USK | 11/01/03 | 11/10/02 | 3 months | (17/07/01) |
| CQM BSMm Delivery to RAL | LAM | 11/01/03 | 11/01/03 | 3 months | (15/10/01) v20011015 |
| CQM JFET Modules Delivered to RAL | JPL | 01/02/03 | 11/01/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| QM1 MCU delivery to SAp | LAM | 01/09/02 | 30/07/02 | 1 month | (15/10/01) v20011015 |
| DRCU-FPU Test Harness Delivery to SAp | RAL | 12/06/02 |  |  | To be purchased by SAp |
| AVM DPU Delivery to RAL | IFSI | 01/06/02 | 16/04/02 | 1.5 months | (18/10/01) |
| DRCU Simulator#2 Delivery to RAL | SO | 01/06/02 | 01/06/02 | TBD | (21/12/00) SO-2000-12-21 |
| EGSE#2 Available | RAL | 01/06/02 | 01/06/02 |  |  |
| QM1 DRCU Delivery to RAL | SAp | 01/12/02 | 03/03/03 |  | (28/01/02) S020128 |
| QM1 WIH Delivery to RAL | SAp | 01/12/02 | 03/03/03 |  | (28/01/02) S020128 |
| FPU Simulator#1 Delivery to RAL | SAp | 01/12/02 | 01/11/02 | 1 month | (10/01/01) v1.0 |
| EGSE#3 Available | RAL | 01/12/02 | 01/12/02 |  |  |
| CQM Test Readiness Review |  |  | 05/06/03 |  |  |
| CQM Interim Review |  |  | 08/07/03 |  |  |
| PFM BDA (SSW) Delivery to RAL | JPL | 01/04/03 | 01/04/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| Critical Design Review |  |  | 11/09/03 |  |  |
| CQM Delivery to ESA | RAL | 01/04/03 | 29/09/03 |  | Realistic Delivery Date 1st Dec 03 |

## AVM Programme

| Milestone | Responsible | Need Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| EGSE#4 Available | RAL | 01/02/03 | 01/09/02 |  |  |
| DRCU Simulator#3 Delivery to RAL | SO | 01/02/03 | TBD | TBD | (21/12/00) SO-2000-12-21 - not in schedule |
| AVM Delivery to ESA | RAL | 01/04/03 | 09/05/03 |  | Realistic Delivery Date 1st Jul 03 |

## QM Warm Electronics Programme

| Milestone | Responsible | Required Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| QM2 MCU Delivery to SAp | LAM | 01/11/02 | 27/12/02 |  | (15/10/01) v20011015 |
| QM DPU Delivery to RAL | IFSI | 01/02/03 | 03/01/03 | 1 month | (18/10/01) |
| QM2 DRCU Delivery to RAL | SAp | 01/06/03 | 05/01/04 |  | (28/01/02) S020128 |
| QM2 WIH Delivery to RAL | SAp | 01/06/03 | 05/01/04 |  | (28/01/02) S020128 |
| FPU Simulator#2 Delivery to RAL | SAp | 01/06/03 |  |  | (19/01/01) v1.0 Not in plan, Date, Margin TBD |
| WE Critical Design Review |  |  | 04/02/04 |  |  |

## PFM Programme

| Milestone | Responsible | Need Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| PFM Cold Filters Delivery to JPL | Cardiff | 03/02/03 | 03/02/03 | TBD | (31/01/02) v3.0 |
| PFM PCAL Delivery to ATC | Cardiff | 14/05/03 | 04/09/03 | TBD | (31/01/02) v3.0 |
| PFM BSMm Delivery to LAM | ATC | 15/07/03 | 25/08/03 |  | (10/09/01) Jul_01g |
| PFM Structure Delivery to RAL | MSSL | 15/07/03 | 10/06/03 | 3 weeks | (Jan02 Progress Report) |
| PFM Thermal Straps Delivery to RAL | MSSL | 15/07/03 | 11/08/03 | 3 weeks | (26/11/01) |
| PFM Mirrors Delivery to RAL | LAM | 15/07/03 | 01/08/03 | 3 months | (30/03/01) v20010330 |
| PFM Filters Dichroics and Beamsplitters Delivery to RAL | Cardiff | 01/08/03 | 22/07/03 | TBD | (31/01/02) v3.0 |
| PFM BSMm Delivery to RAL | LAM | 01/10/03 | 01/10/03 | 3 weeks | (15/10/01) v20011015 |
| PFM Cooler Delivery to RAL | Grenoble | 01/08/03 | 31/12/02 | 8 months | (31/10/01) Dev. Plan Issue3.1 |
| PFM BDAs Delivery to RAL | JPL | 01/10/03 | 01/10/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| PFM Shutter Delivery to RAL | USK | 01/10/03 | 28/04/03 | 5 months | (17/07/01) |
| PFM SCAL Delivery to RAL | Cardiff | 01/10/03 | 27/11/03 | TBD | (31/01/02) v3.0 |
| PFM SMECm Delivery to RAL | LAM | 01/10/03 | 01/10/03 | 3 weeks | (15/10/01) v20011015 |
| PFM FPU RF Filter Modules Delivery to RAL | JPL | 22/10/03 | 22/10/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| PFM FTB Enclosure Delivery to RAL | MSSL | 22/10/03 | 01/10/02 | 12 months | (Jan02 Progress Report) |
| PFM JFET Modules Delivered to RAL | JPL | 22/10/03 | 22/10/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| PFM FTB RF Filter Modules Delivery to RAL | JPL | 22/10/03 | 22/10/03 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| PFM DPU Delivery to RAL | IFSI | 01/03/04 | 05/03/04 |  | (18/10/01) |
| PFM MCU Delivery to SAp | LAM | 07/08/03 | 15/08/03 |  | (15/10/01) v20011015 |
| PFM DRCU Delivery to RAL | SAp | 16/03/04 | 30/07/04 |  | (28/01/02) S020128 |
| PFM WIH Delivery to RAL | SAp | 16/03/04 | 30/07/04 |  | (28/01/02) S020128 |
| Delivery of PFM FPU to Cold Vibration Facility | RAL |  | 06/04/04 |  |  |
| Delivery of Cold-Vibrated PFM FPU to RAL | RAL |  | 04/05/04 |  |  |
| PFM Test Readiness Review |  |  | 26/02/04 |  |  |
| PFM Delivery to ESA | RAL | 01/06/04 | 29/10/04 |  | Realistic Delivery Date 31st Dec 04 |

## FS Programme

| Milestone | Responsible | Need Date | Planned Date | Margin | Comments |
| --- | --- | --- | --- | --- | --- |
| FS Cold Filters Delivery to JPL | Cardiff | TBD | 03/02/03 | TBD | (31/01/02) v3.0 |
| FS PCAL Delivery to ATC | Cardiff | 01/01/04 | 18/12/03 | 1 week | (31/01/02) v3.0 |
| FS BSMm Delivery to LAM | ATC | 22/01/04 | 10/11/04 |  | (10/09/01) Jul_01g |
| Return of CQM from ESA | ESA | 01/06/04 |  |  |  |
| FS Structure Available for Integration | MSSL | 10/01/05 | 06/01/04 | 12 months | (Jan02 Progress Report) |
| FS Thermal Straps for Integration | MSSL | 10/01/05 | 10/11/03 | 1 week | (26/11/01) |
| FS Mirrors Delivery to RAL | LAM | 10/01/05 | 10/11/04 | 18 months |  |
| FS BDAs Delivery to RAL | JPL | 10/01/05 | 10/01/05 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| FS Filters Dichroics and Beamsplitters Delivery to RAL | Cardiff | 10/01/05 | 10/01/05 | TBD | (31/01/02) v3.0 |
| FS SCAL Delivery to RAL | Cardiff | 10/01/05 | 28/09/04 | 8 weeks | (31/01/02) v3.0 |
| FS SMECm Delivery to RAL | LAM | 10/01/05 | 10/01/05 | 10months | (15/10/01) v20011015 |
| FS BSMm Delivery to RAL | LAM | 10/01/05 | 10/01/05 | 10 months | (15/10/01) v20011015 |
| FS Cooler Delivery to RAL | Grenoble | 10/01/05 | 01/09/03 | 16 months | (31/10/01) Dev. Plan Issue3.1 Only one cooler for SPIRE & PACS |
| FS Shutter Delivery to RAL | USK | 10/01/05 | 01/11/04 | 2 months | (15/06/2000) Issue 0.2 D |
| FS FTB Enclosure Delivery to RAL | MSSL | 10/01/05 |  |  | (19/03/01) Issue 1.2 Not in schedule, Date TBC, Margin TBD Refurbished from CQM |
| FS JFET Modules Delivery to RAL | JPL | 10/01/05 | 10/01/05 | TBD | (06/09/01) Business Agreement Issue 2.0 |
| FS MCU Delivery to SAp | LAM | TBD | 16/01/04 |  | (15/10/01) v20011015 |
| FS DRCU Delivery to RAL | SAp | 10/01/05 |  |  | Date TBD |
| FS WIH Delivery to RAL | SAp | 10/01/05 |  |  | Date TBD |
| Delivery of FS FPU to Cold Vibration Facility | RAL |  | 10/07/05 |  |  |
| Delivery of Cold-Vibrated FS FPU to RAL | RAL |  | 10/08/05 |  |  |
| FS Test Readiness Review |  |  | 06/06/05 |  |  |
| FS Available to ESA | RAL | 01/07/05 | 29/11/05 |  | Realistic Date 1st Jan 06 |