Filters

Subsystem Development Plan

Document Ref.: SPIRE-QMW-PRJ-000473

Issue: 2.0

Prepared by: Alex Ellery

Pete Hargrave

Carole Tucker

Last Modified on: 11 January 2001

Approved by:

Distribution list

| SPIRE Project |  | Ken King |  |
| --- | --- | --- | --- |
|  |  | Colin Cunnigham |  |
|  |  | Bruce Swinyard |  |
|  |  | Matt Griffin |  |
| QMW Team |  | Peter Ade |  |
|  |  | Peter Hargrave |  |
|  |  | Alex Ellery |  |
|  |  | Raul Hermoso |  |
|  |  | Carole Tucker |  |
|  |  | Vic Haynes |  |
|  |  | Josie Budd |  |

Update history

| Date | Version | Remarks |
| --- | --- | --- |
| 26 April 2000 | Draft 1.0 | First draft. No detailed design available. |
| 14 July 2000 | Issue 1.0 | First issue |
| 11 January 2001 | Issue 2.0 | Heavily revised plan based on new model philosophy |

Table of Contents

1.	Scope	5

2.	Documents	5

2.1.	Applicable documents	5

2.2.	Reference documents	5

2.3.	Glossary	5

3.	Subsystem Description	6

3.1.	Requirements	9

3.2.	Interfaces	9

3.3.	Deliverables	9

4.	Constraints	10

4.1.	Technical constraints	10

4.2.	System constraints	11

4.2.1.	Filter system requirements	11

4.3.	Calendar constraints	13

5.	Work Description	13

5.1.	Model philosophy	13

5.2.	Organisation	14

5.2.1 QMW Organisation	15

5.3.	Preliminary design phase	15

5.3.1.	Filter development	15

CFIL1 – Hot pressed LPE filter	15

PFIL2 and PFIL3 - Hot pressed LPE filters	16

PDIC1 – Low pass dichroic	16

PDIC2 - Low pass dichroic	16

PFIL4-S,M,L – LPE/HPE hot pressed filters	17

PFIL5-S,M,L – LPE hot pressed filters	17

SFIL2 - Hot pressed LPE filter	17

SBS1,2 – Spectrometer beam dividers	17

SFIL3-S,L – Hot pressed LPE filters	17

SFIL4-S,L-1,2 - LPE/HPE hot pressed filters	17

SFIL5-S,L – Hot pressed LPE filters	18

5.3.2.	Filter testing	18

5.4.	Procurement of long lead-time components	18

5.5.	Detailed design phase	18

5.6.	CQM manufacture & test	19

5.7.	PFM & FS manufacture & test	19

6.	Risk analysis	19

7.	Verification plan	21

7.1.	Prototype filters	22

7.2.	CQM filters	22

7.3.	PFM filters	22

7.4.   FS filters	23

8.	Development calendar & schedule	23

9.	Filters sub-system schedule	24

# Scope

This document describes the development plan for the FIRST/SPIRE instrument optical filters subsystem.

# Documents

## Applicable documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| AD1 | SPIRE Filters subsystem specification | P. Hargrave | SPIRE-PRJ-000454 | 14 June 2000 |
| AD2 | SPIRE FPU PDR viewgraphs | P.Ade, C.Tucker, M.Griffin, P.Hargrave |  | 7-9 July 1999 |

## Reference documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| RD1 | Instrument Requirements Document | B.M.Swinyard | SPIRE-RAL-PRJ-000034 Issue 0.30 | May 2000 |
| RD2 | SPIRE Instrument development plan | K. King |  |  |

## Glossary

| AD | Applicable Document | JPL | Jet Propulsion Laboratory |
| --- | --- | --- | --- |
| CDR | Critical Design Review |  |  |
| CoG | Centre of Gravity | LPE | Low Pass Edge |
| CQM | Cryogenic Qualification Model | MCA | Minimum Clear Aperture |
| DDR | Detailed Design Review | MGSE | Mechanical Ground Support Equipment |
| DM | Development Model | MSSL | Mullard Space Science Laboratory |
| DRCU | Digital Read-out and Control Unit | NA | Not Applicable |
| EGSE | Electrical Ground Support Equipment | O/d | Outside diameter |
| FIRST | Far InfraRed Space Telescope | OGSE | Optical Ground Support Equipment |
| FPU | Focal Plane Unit | PFM | ProtoFlight Model |
| FS | Flight Spare model | RAL | Rutherford Appleton Laboratory |
| FTS | Fourier Transform Spectrometer | RD | Reference Document |
| GSFC | Goddard Space and Flight Center | SPIRE | Spectral and Photometric Imaging Receiver |
| HPE | High Pass Edge | TBC | To Be Confirmed |
| I/d | Inside diameter | TBD | To Be Defined |
|  |  | WE | Warm Electronics |

# Subsystem Description

A full description of the filter subsystem is contained in document [AD1]. Figures 1 and 2, and tables 1 and 2 give a summary of the SPIRE filtering scheme.

The filters will be:

- Designed by QMW.

- Manufactured by QMW

- Qualified/accepted and calibrated under QMW responsibility, mainly at QMW, with RAL assisting with cryovibration tests. The qualification/acceptance program includes thermal cycling and warm and cold vibrations. The calibration program verifies the performance requirements.

- Transported to RAL under QMW responsibility.

- Integrated at RAL in the SPIRE FPU Structure under TBD (QMW/RAL/MSSL) responsibility.

- The SPIRE WE and the SPIRE FPU are integrated under RAL responsibility and undergo the project calibration program under RAL responsibility.

- SPIRE is delivered to ESA under RAL responsibility.

- SPIRE is integrated in the FIRST satellite under ESA responsibility.

- SPIRE CQM is to undergo the ESA cryoqualification program under ESA responsibility.

- SPIRE PFM is to undergo the ESA Acceptance program.

- SPIRE FS is prepared in the event of SPIRE PFM failure.

Figure 1 Photometer optics and filter locations

Table 1 List of photometer filters and dichroics

| Specifications of photometer filters and dichroics |
| --- |
| Component ID | Temp (K) | Location | Type | Edges (cm-1) | Minimum clear aperture (mm) | Comments |
| CFIL1 | 4 | Over entrance to 4-K box | Edge filter | 10% 105 50% 100 90% 95 | 70 x 150 (Beam footprint on CIPM is 54 x 132) | Exact position TBD |
| PFIL2 | 4 | Above CIPM (M3) | Edge filter | 10% 84 50% 80 90% 76 | 70 x 150 | Exact position TBD |
| PFIL3 | 2 | Pupil between POFR2 and POFR3 | Edge filter | 10% 74 50% 70 90% 66 | 45 dia. (Pupil is 41 x 44 inc. 20% oversize) |  |
| PDIC1 | 2 | After POFR3 | Low Pass Dichroic | 10% 40 50% 37 90% 34 | 90 dia. TBC | Transmits long ( |
| PDIC2 | 2 | After PDIC1 | Low Pass Dichroic | 10% 27 50% 25 90% 23 | 90 dia. TBC | Transmits long ( |
| PFIL4S | 0.3 | At SW array | Low pass edge High pass edge | 53 38 | 40 dia. (Field is 19 x 38) |  |
| PFIL4M | 0.3 | At MW array | Low pass edge High pass edge | 36 25.7 | 40 dia. |  |
| PFIL4L | 0.3 | At LW array | Low pass edge High pass edge | 24 17 (if necessary) | 40 dia. |  |
| PFIL5S | 0.3 | At SW array | Edge filter | 10% 70 50% 66 90% 62 | 40 dia. |  |
| PFIL5M | 0.3 | At MW array | Edge filter | 10% 46 50% 43 90% 40 | 40 dia. |  |
| PFIL5L | 0.3 | At LW array | Edge filter | 10% 27 50% 26 90% 25 | 40 dia. |  |

Figure 2 Spectrometer optics and filtering scheme

Table 2 List of spectrometer filters and beam dividers

| Specifications of FTS filters and beam dividers |
| --- |
| Component ID | Temp (K) | Location | Type | Edges (cm-1) | Clear aperture (mm) | Comments |
| CFIL1 | 4 | On entrance to 4-K box | Edge filter | 10% 105 50% 100 90% 95 | 70 x 150 (Beam footprint on CIPM is 54 x 132) | Shared with photometer |
| SFIL2 | 4 | Above M3 | Edge filter | 10% 84 50% 80 90% 76 | 70 x 150 | Shared with photometer |
| SBS1 | 4 | After SIRM | Beam divider | 15 to 60 >90% 4RT | 36 dia. |  |
| SBS2 | 4 | After SDCM-A or -B | Beam divider | 15 to 60 >90% 4RT | 36 dia |  |
| SFIL3S SFIL3L | 2 | After SCAM-A or SCAM-B | Edge filter | 10% 74 50% 70 90% 66 | 40 dia. |  |
| SFIL4S1,2 | 0.3 | At SW array | Low pass edge High pass edge | 50 33 | 15 |  |
| SFIL4L1,2 | 0.3 | At LW array | Low pass edge High pass edge | 33 None? | 15 |  |
| SFIL5S | 0.3 | At SW array | Edge | 10% 70 50% 66 90% 62 | 15 |  |
| SFIL5L | 0.3 | At LW array | Edge | 10% 46 50% 43 90% 40 | 15 |  |

The first filter in the chain, situated on the 4-K box, should reflect back to the sky as much unwanted high frequency radiation as possible. Filters on lower temperature shields should then reject radiation from higher temperature boxes and shields.

Strategic placement of filters will enable us to:

- Define the spectral passbands.

- Minimise the thermal loading on the 3He fridge, 2-K,  and 4-K stages by rejecting short wavelength thermal energy.

- Minimise stray light getting to the detectors.

- Maximise the in-band spectral transmission.

## Requirements

See 4.1 (technical constraints)

## Interfaces

SPIRE-ICD-1.1/1.2.1 Structure-Filters (13th June 2000) – filter mounts

## Deliverables

In the table below, the dates in black are those imposed by the project, and the green/red dates are estimated delivery dates. Green indicates an early/on-schedule delivery, while red indicates a possible late delivery.

Table 3 List of deliverables for each instrument model

| Item | STM | CQM | PFM | FS |
| --- | --- | --- | --- | --- |
| RAL Filters | 01/07/02 | 01/10/02 | 01/10/03 | 10/11/04 |
|  |  | 20/02/02 | 15/05/03 | 14/05/04 |
| JPL 300mK Filters |  | TBD | TBD | TDB |

The filter sets to be delivered to RAL and JPL.

| Model | Flight representativity | Difference with flight | Deliverables |
| --- | --- | --- | --- |
| CQM | 100% (TBC) | None (TBC) | 1 set |
| PFM | 100% | None | 1 set |
| FS | 100% | None | 1 set |

No special equipment is required for integration and alignment.

No simulators required.

No special tooling required.

Documentation to be delivered: Test reports

PA/QA documentation

# Constraints

## Technical constraints

The main performance specifications are shown in table 3. Please note that these figures are for information only. Full details are contained in document [AD1].

Table 4 Performance requirements for the filter subsystem

| IRD-PHOT-R01 | Nominal pass band 250 mm, 350 mm and 500 mm (TBC) (/(( = 3 |
| --- | --- |
| IRD-SPEC-R01 | Wavelength range Band A = 200-300mm, 33-50cm-1 (TBC) Band B = 300-670mm, 15-33cm-1 (TBC) |
| IRD-OPTP-05 | Overall optical efficiency: Greater than 0.27 |
| IRD-OPTP-R07 | Out of band radiation: Requirement TBD until telescope optical properties defined |

The main technical constraints are:

- SPIRE lifetime in orbit = 4.25 years

- Operating temperature = 0.3 K - 4 K

- Total mass of all filters = TBD kg including 20% margin

- Filter CoG position = TBD – list of all filters

- Filter Volume = TBD mm3 - list

- Level of radiation = TBD

- Vibration level = TBD at 4K

- Shock level = TBD at 4K

- Cleanliness = 100,000 or better (TBD)

## System constraints

### Filter system requirements

| Requirement ID | Description | Value |
| --- | --- | --- |
| IRD-STRC-R03 | Items requiring support from 4K common structure | Photometer filters All spectrometer optics Beam splitters |
| IRD-STRC-R04 | Optics & associated subsystem alignment | The common structure shall be capable of maintaining the alignment of the photometer and spectrometer optics and associated components (eg. Filters) to within the specifications given in RD7 both at room temperature and during cryogenic operation |
| IRD-STRP-R01 | Items requiring support | The photometer 2K structure shall support: photometer 2K optics, dichroics and filters. |
| IRD-STRP-R02 | Optics & Filters alignment | The 2K photometer structure shall be capable of maintaining the alignment of the photometer 2K optics; filters and dichroics to within the requirements set out in RD7 at room temperature and during cryogenic operation |
| IRD-STRS-R01 | Items requiring support | The spectrometer 2K structure shall support: Cold Stop filters, Fold mirrors |
| IRD-OPTP-R05 | Throughput | The throughput of the photometer mirrors, filters, dichroics and baffles shall be greater than 0.27 (TBC) over the instrument waveband. This includes losses due to manufacturing defects, surface finish and alignment tolerances. |
| IRD-OPTP-R07 | Out of band radiation | The end to end filtering of the photometer shall control the out of band radiation to be no more than 10-3 for 40cm-1 to 200cm-1 10-6 for 200cm-1 to 1000cm-1 10-9 for 1000cm-1 to 100000cm-1 of the in-band telescope background radiation. |
| IRD-OPTS-R05 | Theoretical throughput | The theoretical throughput of the spectrometer mirrors, filters, beam splitters and baffles individually shall be greater than 0.9 (TBC) over the 2.6 arcmin FOV at 250(m including all losses due to alignment, mirror quality, etc. |
| IRD-OPTS-R08 | Out of band radiation | The end-to-end filtering of the spectrometer shall control the out of band radiation to be no more than 10-3 for 40cm-1 to 200cm-1 10-6 for 200cm-1 to 1000cm-1 10-9 for 1000cm-1 to 100000cm-1 of the inband telescope background radiation. |

## Calendar constraints

The main SPIRE project milestones are [RD2]:

| PDR | November 2000 |
| --- | --- |
| DDR |  |
| CQM filters delivery to RAL | 1 Oct 2002 |
| CQM filters delivery to JPL | TBD |
| CDR | 3 Feb 2003 |
| SPIRE CQM delivery to ESA |  |
| PFM filters delivery to RAL | 1 Oct 2003 |
| PFM filters delivery to JPL | TBD |
| SPIRE PFM delivery to ESA |  |
| FS filters delivery to RAL | 10 Nov 2004 |
| FS filters delivery to JPL | TBD |
| SPIRE FS delivery to ESA |  |
| FIRST launch | 2007 |

# Work Description

## Model philosophy

The model philosophy is compliant with the SPIRE project.

The following models will be produced:-

- Filter DM – several devices will be built and evaluated to produce a developmental model (DM) which will be tested and form the basis of our CQM design

- Filter STM – this will be thermally and structurally representative of the flight filters.

- Filter CQM – these will be provided for incorporation into SPIRE for CQM testing

- Filter PFM – This is the flight device

- Filter FS – This is the flight spare

## Organisation

QMW is responsible for the filter subsystem. This involves the design, manufacture and testing of all filters, dichroics and beam dividers for each instrument model.

RAL will assist with cryo-vibration tests.

MSSL is responsible for the structure to which the filters are integrated.

JPL are responsible for the structure to which the 300mK filters are integrated as part of the detector array modules.

Figure 1 Organisation of the filter subsystem

### 5.2.1 QMW Organisation

## Preliminary design phase

The PDR freezes the technical specifications/requirements, while the interfaces are frozen at the interface review.

### Filter development

The final design of the instrument structure and optics has a significant impact on the design of some filter components. Some ring-mounted components may need to be manufactured to non-standard sizes. Small dimension filter version of these large, non-standard dimensioned filters may be prototyped. If the actual non-standard filters require prototyping, before QMW re-tools and prototyping of these components can begin, the instrument structure and optics design needs to be finalised. This section lists each filter component to be produced by QMW, and gives details of any factors affecting its design and manufacture.

#### CFIL1 – Hot pressed LPE filter

The original location for CFIL-1 was over the entrance to the 11-K box but the 11-K box is no longer being implemented on SPIRE. It is therefore proposed to mount CFIL-1 over the aperture to the 4K box, intercepting the input beam at 4-K. The size of beam to be intercepted is dependent upon the position within the 4-K box. The smallest MCA will result from placing the filters at a beam waist, in this case the telescope focal plane. The implications of placing filter components here need to be investigated, and will be discussed at a splinter meeting around the time of the PDR, along with other options for modifying the structure.

QMW is waiting for the SPIRE structural model (CAD file) with the integrated optical beams from RAL, which will enable us to determine the filter sizes needed. This obviously depends upon the final position of these filters in the optical train.

These filters present a small schedule risk, as it is almost certain that the MCA needed will be greater than 110mm diameter, which is the largest set of lithographic masters that QMW have. To produce these large filters (possibly up to 150mm diameter), QMW will have to procure new masters. It is not anticipated that manufacture of these components will present a problem, as we have press tools which can handle up to 170mm diameter, although these components will need to be thoroughly prototyped and checked for de-lamination after thermal cycling. We may also require a new sample chamber for the FTS (at present 120mm x 140mm cross-section) if the filter sizes exceed 140mm in diameter.

#### PFIL2 and PFIL3 - Hot pressed LPE filters

This item will be directly mounted to the structure with a clamping ring, and will not present a development problem/risk.

#### PDIC1 – Low pass dichroic

PDIC1 will be a hot pressed, dielectric gap or air gap component (TBC). However, this has to be flat (spec. TBD), and therefore ring mounted. Space restrictions in the instrument dictate that a ring of 80mm i/d, and 95mm o/d is needed, with a maximum thickness of 11mm (TBC). This is not one of the QMW standard ring sizes, and so QMW will need to re-tool to produce rings of this size. Before this can happen, QMW need final confirmation of the ring size. There is therefore a slight schedule risk relating to the re-tooling process.

#### PDIC2 - Low pass dichroic

PDIC2 will also be a hot pressed, dielectric gap or air gap component (TBC). As the present SPIRE structure is drawn, a ring of 72mm i/d, and 85mm o/d is needed. Again, this is a non-standard ring size. However, it may be possible to accommodate a ring of 75mm i/d, 90mm o/d, as this is a standard size. This will greatly help reduce delay and cost. We are working with MSSL to resolve this issue.

#### PFIL4-S,M,L – LPE/HPE hot pressed filters

These were baselined as combinations of two hot pressed filters to define the pass bands. However, the selection of the feedhorn option now means that the feedhorn waveguide may serve as a sufficient HPE filter. This will be discussed with JPL in early May.

These items will be directly mounted to the array modules, and will not present a development problem/risk.

#### PFIL5-S,M,L – LPE hot pressed filters

These items will be directly mounted to the array modules, and will not present a development problem/risk.

#### SFIL2 - Hot pressed LPE filter

This item will be directly mounted to the structure with a clamping ring, and will not present a development problem/risk.

#### SBS1,2 – Spectrometer beam dividers

As drawn, these components have to be 38mm i/d and 46mm o/d. These are non-standard sizes, and re-tooling will be necessary. QMW needs final confirmation of sizes before re-tooling and prototyping.

Prototype hot-press beam dividers are running on the SPIRE prototype FTS in the QMW lab, and perform very well. However, they have not yet undergone qualification tests. Additionally, these components need to be checked for microphonic effects.

These components present a small development risk.

#### SFIL3-S,L – Hot pressed LPE filters

These filters present no development problem/risk. However, as drawn in the SPIRE CAD model, there is provision for a mounting lip of only 1.5mm to the structure. This is not sufficient and has to be resolved. QMW is working with MSSL on this issue.

#### SFIL4-S,L-1,2 - LPE/HPE hot pressed filters

These were baselined as combinations of two hot pressed filter assemblies to define the pass bands. However, the selection of the feedhorn option now means that the feedhorn waveguide may serve as a sufficient HPE filter. This will be discussed with JPL in early May.

These items will be directly mounted to the array modules, and will not present a development problem/risk.

#### SFIL5-S,L – Hot pressed LPE filters

These items will be directly mounted to the array modules, and will not present a development problem/risk.

### Filter testing

All prototype devices will undergo the following tests as a minimum:-

- Thermal tests

  - Device temperature vs power to SOB??/structure (i.e. thermal conductance of supports & wires from heated element to 4K)

  - Thermal time constants

- Electrical tests

  - Impedance vs device temperature

  - Device temperature vs applied power

- Mechanical tests

  - Resonant frequency (warm)

- Photometric tests

  - Emitted in-band power vs applied power

More rigorous tests will be implemented, which include all of the above as well as repeated thermal cycling and accelerated lifetime tests.

## Procurement of long lead-time components

Once a preliminary design has evolved, long lead-time items will be procured – these include new masters for non-standard sized filters (TBD).

Note – need to get list of CPP items to Ken

## Detailed design phase

The detailed design will encompass all the functions and interfaces of the filter subsystem.

The detailed design will be presented at the Detailed Design Review. The DDR must have taken place before CQM manufacture can begin.

The design verification tests include:-

- Verification of the basic mechanical parameters (Mass, stiffness, resonant frequencies).

- Performance verification. Qualification tests .

## CQM manufacture & test

The DDR must have happened before CQM manufacture can begin. To verify the design, a complete qualification and lifetests are to be conducted.

At least two models for each of the filters are necessary. The two models are the development model (DM) and the cryogenic qualification model (CQM). The Filter DM is deliverable in part and the Filter CQM is deliverable.

The DM models are used to qualify the design and conduct lifetests.

The CQM models are to be qualified but do not undergo lifetests.

The DM and the CQM include all the functions of the flight design, except redundancy (TBD).

The design verification tests include:-

- Verification of the basic mechanical parameters (Mass, stiffness, resonance frequencies).

- Performance verification.

- Qualification tests.

- Lifetests.

After the CQM Filter delivery, the SPIRE CQM is tested at project level.

The results of the qualification tests are to be presented at the SPIRE CDR which is the start point of the PFM and FS manufacture.

Then, the SPIRE CQM is delivered to ESA for cryogenic tests of the FIRST FPU.

## PFM & FS manufacture & test

Following the lifetests and SPIRE CQM tests, some modifications may have to be implemented in the design.

The design changes are to be implemented in the flight design and be validated using the DM.

CFIL-1 will be provided for the STM for warm/cold vibration tests and thermal cycling tests. This component will also comprise the CQM and FS CFIL-1 filter.

The PFM Filters are then manufactured and undergo the acceptance tests and performance verification.

It may be possible to use the CQM filters as the FS filters – this depends on ESA that the return delivery of the CQM arrives on time (baseline). There is the possibility for manufacturing a new set of FS filters if the CQM filters are not returned to QMW without significant impact on the schedule. The FS filters undergo the acceptance tests and performance verification after the PFM delivery.

# Risk analysis

There is minimal risk associated with the production of the edge and ND filters. These are standard filter types that are routinely produced by QMW for ground, airborne and space experiments. In terms of performance, the filter stacks will be undergoing qualification for BLAST thereby increasing confidence in their functionality. There is a risk associated with production throughput of filters with respect to other programmes which requires careful coordination to ensure no schedule impacts to SPIRE.

There is no provision for filter component redundancy on SPIRE. Loss of edge or ND filters would change the background power on the detector arrays, as well as changing the power loading on the various temperature stages.

The items that would constitute a single point failure are: -

- Dichroics – loss of a dichroic would compromise at least two photometer arrays, depending on the failure mode

- Beam splitters – loss of a beam splitter would cause the loss of the FTS

| Risk | Likelihood | Impact | Preventative Action | Notes |
| --- | --- | --- | --- | --- |
| Beam splitter qualification failure | Low | Re-design of spectrometer | None | Prototype beam splitters have been built, and perform well on the SPIRE FTS optical test bed at QMW. However these have not yet been subjected to any qualification test. |
| Dichroic qualification failure | Low | Re-design photometer optics | None | Prototype dichroics are to built. They have yet to be subjected to any qualification tests (BLAST will provide this). |
| CFIL-1 qualification failure | Low | Need to re-locate filters to intercept a smaller beam cross section. May affect instrument thermal balance and stray light environment | None | This filter has a higher than usual development risk associated with them as they are larger than any manufactured by QMW in the past. New lithographic masters need to be ordered. Furthermore, being the first filter common to both photometer and spectrometer, it represents a single point failure mode. |

# Verification plan

The verification plan must be compliant with the project verification plan [AD2, RD1] and must fulfil the filter development needs.

300K vibrations are conducted at QMW/RAL (TBD).

Cryovibrations are conducted at RAL (TBC).

Vacuum cycles, soak cycles, thermal cycles are conducted at QMW.

Lifetime tests are conducted at QMW.

EMI/EMC tests are conducted at TBD.

Microphonics tests are conducted at TBD.

Performance tests are conducted at QMW.

In the tables below,

| X = | a real test is conducted |
| --- | --- |
| A = | an analysis is conducted |
| NA = | Non applicable |

## Prototype filters

|  |  | Components |
| --- | --- | --- |
| Mass measurement | X | All |
| CoG measurement |  |  |
| Vibrations 300K | X | All |
| Vibrations 4K | X | All |
| Thermal/Vacuum cycle | X | All |
| Radiation tolerance | A(**) | All |
| Microphonics | X | SBS1, SBS2 |
| Spectral measurements | X | All |

(*) : EMI/EMC tests are to be conducted on the PFM only if design changes have occurred.

(**) : The radiation tolerance is verified by analysis only, taking into account the materials involved.

## CQM filters

|  |  | Components |
| --- | --- | --- |
| Mass measurement | X | All |
| CoG measurement |  |  |
| Vibrations 300K | X | All |
| Vibrations 4K | X | All |
| Thermal/Vacuum cycle | X | All |
| Radiation tolerance | A(**) | All |
| Microphonics | X | SBS1, SBS2 |
| Spectral measurements | X | All |

(*) : As EMI/EMC is verified on the CQM, no further verification are conducted on the subsequent models.

(**) : The radiation tolerance is verified by analysis only, taking into account the materials involved.

## PFM filters

|  |  | Components |
| --- | --- | --- |
| Mass measurement | X | All |
| CoG measurement |  |  |
| Vibrations 300K | X | All |
| Vibrations 4K | X | All |
| Thermal/Vacuum cycle | X | All |
| Radiation tolerance | A(**) | All |
| Microphonics | X | SBS1, SBS2 |
| Spectral measurements | X | All |

(**) : The radiation tolerance is verified by analysis only, taking into account the materials involved and experience of previous space missions

## 7.4.   FS filters

|  |  | Components |
| --- | --- | --- |
| Mass measurement | X | All |
| CoG measurement |  |  |
| Vibrations 300K | X | All |
| Vibrations 4K | X | All |
| Thermal/Vacuum cycle | X | All |
| Radiation tolerance | A(**) | All |
| Microphonics | X | SBS1, SBS2 |
| Spectral measurements | X | All |

(**) : The radiation tolerance is verified by analysis only, taking into account the materials involved and experience of previous space missions

# Development calendar & schedule

The major project milestones pertinent to the calibrators sub-system are:-

| Detailed design available | ?? |
| --- | --- |
| CQM Prototyping | 7 Feb 2001–12 Jun 2001 |
| CQM Manufacture | 13 Jun 2001–27 Nov 2001 |
| CQM Modif, qualification & calibration | 5 Sep 2001-19 Feb 2002 |
| CQM delivery to RAL | 20 Feb 2002 |
| PFM Manufacture | 8 Aug 2002–22 Jan 2003 |
| PFM Acceptance & calibration | 28 Nov 2002–14 May 2003 |
| PFM delivery to RAL | 15 May 2003 |
| FS manufacture | 8 Aug 2003–22 Jan 2004 |
| FS Acceptance & calibration | 28 Nov 2003–13 May 2004 |
| FS delivery to RAL | 14th May 2004 |

Detailed planning is outlined in filter SPIRE_QMW_ALL_v1.3.mpp

# Filters sub-system schedule

The schedule shown is realistic, with a lot of margin built into estimated task durations. However, it should be noted that this is extracted from the overall QMW SPIRE schedule (SPIRE_QMW_ALL_v1.3.mpp), which at present has a lot of tasks running in parallel. QMW need to go through this schedule and allocate resources to tasks, which may cause the filter schedule to change slightly to accommodate other tasks, but the delivery dates shouldn’t be affected to any great degree. This document will be updated once the resource allocation exercise has taken place.

# Text boxes

Draft

For approval