| L.A.M. FRE 2243 | FIRST SPIRE | Ref : LAM.PJT.SPI.NOT.200006 Ind 1 Author : D.Pouliquen | Page : 1 / 10 Date : 13 June 2000 |
| --- | --- | --- | --- |
| SPIRE Mirrors and Alignment tools Development Plan |  |

Distribution List :

| RAL | ColinCunningham | X | Ken J. King | X |
| --- | --- | --- | --- | --- |
|  | Bruce M. Swinyard | X |  |  |
| MSSL | Berend Winters | X |  |  |
| CNES | Yvan Blanc | X | Martine Joubert | X |
| CEA-Sap | Jean-Louis Auguères |  |  |  |
| DESPA | Guy Michel |  |  |  |
| GSFC | Don. E. Jennings |  |  |  |
| LAM | Armand Artinian |  | Jean-Paul Baluteau | X |
|  | Claude Colin |  | Pascal Dargent | X |
|  | Kjetil Dohlen | X | Didier Ferrand | X |
|  | Michel Jevaud |  | Patrick Levacher | X |
|  | Alain Origné | X | Dominique Pouliquen | X |

_________________________________________________________________________________

LABORATOIRE   D'ASTROPHYSIQUE de  MARSEILLE  -  CNRS    BP 8   13376  MARSEILLE Cedex 12 FRANCE

Tél : (33) +4 91 05 59 00   -   Fax : (33) +4 91 05 69 59

Update

| Date | Indice | Remarks |
| --- | --- | --- |
| 20 May 2000 | Draft 0 | Creation of the document |
| 26 May 2000 | Draft 1 | Mirrors STM added Mirror list added M5 drawing added |
| 13 June 2000 | 1 | No change except document upgraded from draft status |

| Host system | Windows 95 |
| --- | --- |
| Word Processor | Microsoft Word 97 |
| File | C:\Document\LAM_PJT\FIRST\SPIRE\Projet\Dvlpt\LAM.PJT.SPI.NOT.20000601_Mirroirs_Dvlpt.doc |

Table of contents

1.	Scope of the document	4

2.	Documents	4

2.1.	Applicable documents	4

2.2.	Reference documents	4

2.3.	Glossary	4

3.	Description of the mirrors	4

4.	Constraints	6

4.1.	Development constraints	6

4.1.1.	Technical constraints	6

4.1.2.	Organisation	6

4.1.3.	Calendar constraints	7

4.2.	Risk analysis	7

4.3.	Redundancy	7

5.	Work description	7

5.1.	Development and model philosophy	7

5.1.1.	Preliminary Design (Phase B)	7

5.1.2.	Detailed design and CQM/PFM mirrors manufacture (Phase C/D)	7

5.1.3.	Flight design modifications and PFM/FS manufacture	8

5.2.	Verification plan	8

5.3.	Ground associated equipment	8

5.3.1.	Simulators	8

5.3.2.	Alignment Tools	8

5.3.3.	Additional equipment	9

5.3.4.	STructural Model (STM)	9

6.	Development calendar	9

7.	Description of deliverables	10

7.1.	Mirrors Deliverable models	10

7.2.	Alignment tools	10

7.3.	Associated documentation	10

# Scope of the document

This document describes the development plan of the FIRST/SPIRE Optics subsystem and of the different tools necessary for the development of the mirrors and for the alignment of the optics in the structure..

The development plan is based on the applicable documents cited in §2.

The format of this document is compliant with the CNES instructions applicable at LAM [AD3].

# Documents

## Applicable documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| AD1 | SPIRE Mirrors Specification | K.Dohlen and D.Pouliquen | LAM.PJT.SPI.SPT.200007 Ind 1 | 22 May 2000 |
| AD2 | SPIRE Optical Alignment Plan | K.Dohlen and A.Origné | LOOM.KD.SPIRE.2000.001-1 | 3 Jan 2000 |
| AD3 | SPIRE Development plan | K.King | TBU |  |
| AD4 | Guide pour les projets scientifiques | CNES | DTS/AQ/QP 98-083 | June 1998 |

## Reference documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| RD1 | Intrument Requirements Document | B.M.Swinyard | SPIRE-RAL-PRJ-000034 Iss .21 | 30 Nov 1999 |
| RD2 | Instrument Development Plan | K.King | SPIRE WE Review viewgraphs | 6 Dec 1999 |

## Glossary

| AD | Applicable Document | MSSL | Mullard Space Science Laboratory |
| --- | --- | --- | --- |
| BSM | Beam Steering Mirror | NA | Not Applicable |
| CDR | Critical Design Review | PDR | Preliminary Design Review |
| CNES | Centre National des Etudes Spatiales | PFM | Prototype Flight Model |
| CoG | Center of Gravity | RAL | Rutherford Appleton Laboratory |
| CQM | Cryogenic Qualification Model | RD | Reference Document |
| DDR | Detailed Design Review | SPIRE | Spectral and Photometric Imaging REceiver |
| FIRST | Far InfraRed Submillimeter Telescope | STM | Structural Model |
| FPU | Focal Plane Unit | TBC | To Be Confirmed |
| FS | Flight Spare model | TBD | To Be Defined |
| LAM | Laboratoire d'Astrophysique de Marseille | TBU | To Be Updated |
|  |  | TBW | To Be Written |

# Description of the mirrors

The design of the mirrors is the same as the one used for ISO-LWS.

The mirrors are made in Aluminium 6061.

They all have a standard interface with the structure, i.e. an M8 screw and a pin.

Each mirror is machined in a single block of aluminium (diamond cutting). The screw part of the attachment exerts pressure only on the shoulder part of the mirror, avoiding deformation of the optical surface.

The mount of each mirror is located on the optical bench by means of a pin.

This pin ensures that in case of dismounting of the mirror it will be mounted again in its correct position.

During the integration of the mirrors in the SPIRE structure, the mirrors are mounted on brackets which are provided by MSSL.

The table below gives the list of the mirrors with their provisional dimensions and mass.

| Subass'y | Mirror | Shape | Dimensions (mm) | Number of parts | Mass (kg) | Total Mass (kg) |
| --- | --- | --- | --- | --- | --- | --- |
| Fore optics | M3 | Rect | 132x54 | 1 | 0.183 |  |
|  | M4 | Ell. | 15x16 | 1 | 0.021 |  |
|  | M5 | Rect | 161x85 | 1 | 0.360 | 0.564 |
| Photometer | M6p | Rect | 46x27 | 1 | 0.027 |  |
|  | M7p | Rect | 118x101 | 1 | 0.300 |  |
|  | M8p | Circle |  | 1 | 0.056 |  |
|  | M9p | Cricle |  | 1 | 0.223 |  |
|  | F1 | Rect | 78x40 | 1 | 0.065 |  |
|  | F3 | Rect | 56x53 | 1 | 0.060 | 0.731 |
| Spectrometer | M6s | Rect | 51x27 | 1 | 0.029 |  |
|  | M7s | Rect | 40x57 | 1 | 0.044 |  |
|  | M8s | Circle |  | 2 | 0.112 |  |
|  | M9s | Circle |  | 2 | 0.074 |  |
|  | CC face1 | Rect | 40x40 | 2 | 0.044 |  |
|  | CC face2 | Rect | 30x62 | 2 | 0.070 |  |
|  | CC face3 | Rect | 30x62 | 2 | 0.070 |  |
|  | M10s | Circle |  | 2 | 0.112 |  |
|  | M11s | Circle |  | 2 | 0.194 |  |
|  | M12s | Ell | 21x16 | 2 | 0.050 | 0.799 |
| Total |  |  |  | 27 |  | 2.094 |

The figure below gives a drawing of the M5 mirror, which is the heaviest one.

# Constraints

## Development constraints

### Technical constraints

Note : the figures hereafter are for information only. The applicable figures are in [AD1] which refers to [RD1]

The main specifications are:

- Infrared reflectivity > 0.99

- Surface roughness = 2µm. (for alignment purpose in the visible light range)

- Material = Aluminium 6061

- SPIRE lifetime on orbit = 4.25 years

- Operating temperature = 4K

- Mirrors mass = TBD

- Cleanliness = Class 100 (TBC)

During its lifetime,  the mirrors are :

- designed under LAM responsibility.

- manufactured under LAM responsibility, (subontract in the industry).

- controlled at LAM responsibility

- transported to RAL under LAM responsibility.

- integrated at RAL in the SPIRE FPU Structure under joint RAL, MSSL and LAM responsibility.

Once integrated, the mirrors will follow the life of the SPIRE-FPU:

- The SPIRE-FPU is to undergo the project qualification/acceptance program under RAL responsibility.

- SPIRE is delivered to ESA under RAL responsibility.

- SPIRE is integrated in the FIRST satellite under ESA responsibility.

- SPIRE CQM is to undergo the ESA test program under ESA responsibility.

- SPIRE PFM is to undergo the ESA Acceptance program.

- On the launch pad, before launching, the SPIRE FPU is cooled down to its operating temperature and launched cold.

- SPIRE FS is prepared in the event of a SPIRE PFM failure.

### Organisation

LAM is responsible for the mirrors, except the BSM mirror, and for the alignment tools.

LAM designs the tools and manufacture them part at LAM, part in the industry.

MSSL is responsible for the structure inside which the Optics is integrated.

RAL is responsible for the SPIRE experiment.

### Calendar constraints

The main SPIRE project rendez-vous are [RD2]:

| Milestone | Date |
| --- | --- |
| PDR | Jun 2000 |
| DDR | Oct 2000 |
| LAM delivers the MM mirrors to MSSL | Jan 2002 |
| LAM delivers the CQM mirrors and the alignment tools to RAL | Apr 2002 |
| CDR | Apr 2003 |
| LAM delivers the PFM and FS mirrors and the alignment tools to RAL (If no modification, delivery could take place immediately after CDR) | Apr 2004 |
| FIRST launch | 2007 |

## Risk analysis

Due to the fact that no coating is applied to the mirrors, no risk has been identified.

## Redundancy

This part is not applicable to the optics subsystem.

# Work description

## Development and model philosophy

The model philosophy is compliant with the SPIRE project requirements and meets the LAM development needs.

### Preliminary Design (Phase B)

The optical design is made. The alignment plan is written. The optics specifications are written.

A mirror mockup is built and tested in vibrations to ensure that no deformation of the mirror happens.

The interfaces with SPIRE Structure are defined during this step.

The preliminary design is presented at the Preliminary Design Review which freezes the technical specifications and the interfaces.

### Detailed design and CQM/PFM mirrors manufacture (Phase C/D)

A set of test mirrors is manufactured by different industrials to check their ability to manufacture aluminium mirror with the adequat diffusion caracteristics. The mirrors are tested on the Mirror Diffusion Bench.

Following these measurements,

- an ITT is emitted by LAM for the procurement of all the mirrors for both the CQM and the PFM mirrors and for the CCA Tool and the Apex Tool. No mirror set is planned for the FS as the FS mirrors are supposed to be the CQM mirrors. Once received, the tools and the CQM mirrors optical characteristics are controlled (3D measurements and interferometry). Their masses are measured along with the CoG of the heaviest ones. The CQM mirrors are then baked-out, thermally cycled and controlled again.  The PFM mirrors endure then the same treatment.

- At the same time, the Position Sensing Device (PSD) is ordered in its cryogenic version (estimated delay = 6 months). The PSD Control Bench is designed and optical components ordered along the design, manufacture and bake out of the PSD Tool mounting. Once eevrything is received, the PSD tool is assembled, controlled on the PSD Control Bench, thermally cycled (3 cycles), and controlled again.

- At the same time, the diffusion measure are fed into the optical simulator (ZEMAX software) and the complete alignment procedure is simulated. This simulation specifies the MAT supplementary lens and checks that the tools reticules will be seen with the correct precision and sensitivity.

The MAT supplementary lens is then ordered while the supplementary lens mechanical mounting is designed and manufactured. Once the lens is received, the assembly is integrated and controlled on the MAT Control Bench.

At the same time, the different tools are now to be specified. To do so, a set of each tools is ordered along with a lenses set to simulate the instrument. The detector tool (D-Tool) is mechanically designed, manufactured and baked out.

When received, the instrument simulator and the MAT are assembled on the Tools Bench and each appropiate tool is then selected.

After the Optics-CQM and the tools delivery, the SPIRE CQM is integrated, aligned and tested at project level.

The results of the qualification tests are to be presented at the SPIRE CDR which is the start point of the modifications of the optics and the alignement tools.

Then, the SPIRE CQM is delivered to ESA for cryogenic tests of the FIRST payload.

### Flight design modifications and PFM/FS manufacture

Following the SPIRE CQM tests, some modifications may have to be implemented in the design.

In this case, the design changes are implemented in the flight design, the modified mirrors are subcontracted to the industry (2 identical sets, one for the PFM and one for the FS) while the alignment tools modifications are handled by LAM.

If no modification is needed, no activity happens as the PFM mirrors have already been manufactured, controlled, etc… and as the FS mirrors are the CQM mirrors (as it is the case for the SPIRE structure)

## Verification plan

- All the mirrors are measured at 300 K w.r.t. their individual optical specifications. This measurement is done in visible light.

- The interfaces of all the mirrors are controlled (3D)

- The CoG of the <big> mirrors is measured. These mirrors are tested in vibration at 300 K with a mock up of the typical mechanical interface with the structure and measured afterwards (visible light)

- The mass of each mirror is measured.

- All the mirrors are baked out (48 hours / 80°C, TBC)

- All the mirrors are now handled under class 100 cleanliness (TBC).

- All the mirrors are cycled between 300 K and 20 K (Number of cycles = TBD) 
and measured afterwards (visible light)

- No lifetime tests are to be conducted as there is no coating.

These operations are conducted at LAM.

These operations are done for both the CQM set and the PFM set.

## Ground associated equipment

The tables hereafter sum up the ground equipement needed for the development of the mirrors and for the alignment of SPIRE.

### Simulators

| Simulator | Used for… | Functions |
| --- | --- | --- |
| Alignement Simulator | …the detailed specifications of the alignment tools ... the verification of the alignement procedure | Replaces the hardware Allows to virtually place the alignement tools according tp the procedure Simulates what will be seen through the MAT |

### Alignment Tools

The alignment tools are deliverable.

As the alignment tools are to be integrated in the SPIRE structure, their interfaces are controlled and they are baked-out, and handled afterwards under Class 100 (TBC) cleanliness conditions.

The PSD-Tool is also thermally cycled and checked at cryogenic temperature as it is to be used also at cryogenic temperature.

| Tool | Functions | Description | Note |
| --- | --- | --- | --- |
| MAT | Used to check the position of the reticule on the alignement tools |  | Used at room temperature only |
| Apex Tool | Used to check the position of each pirror Apex in the SPIRE structure. | An aluminium flat mirror with a central reticule whose plane is at the real mirror Apex distance from the interface plane with the SPIRE structure. | Used at room temperature only |
| 3D Tool | Used to check the position of each mirror interface with the SPIRE structure. | An auminium monobloc piece associating a disk and a sphere. | Used at room temperature only |
| D Tool | Acts as a source in the place of the detectors. | A plate containing central and peripheral sources. Each source is individually lightable. | Used at room temperature only. |
| CCA Tool | Replaces SMECm during the spectrometer alignment. | Corner cubes mirrors placed at the ZPD position (TBC) | Used at room temperature only. |
| CS-Tool | Materializes the cold stop location | A glass plate with central reticule | Used at room temperature only |
| O-Tool | Materializes the SPIRE object plane | A glass plate with central and peropheral reticules | Used at room temperature only |
| M2-Tool | Materializes the telescope pupil (M2) | A glass plate with central and peripheral reticules | Used at room temperature only |
| PSD-Tool | Used to check the position of the incoming beam on the entrance plane of the detectors. |  | Used at room and croygenic temperature. |

### Additional equipment

The additional equipment are the benches used in the development.

This equipment is not deliverable.

| Bench | Used to… | Note |
| --- | --- | --- |
| Diffusion Bench | … characterize the diffusion of Aluminium mirrors | This test prepares the ITT. |
| PSD Control Bench | … verify check the PSD | Some parts are used when testing the PSD Tool at cryogenic temperature. |
| MAT Control Bench | … control the supplementary lens and its mounting on the MAT | The optical mounting consists in a set of lenses which projects the image of a reticule behind the position of the MAT. |
| Tools Bench | … to specify in details the caracteristics of the DTool, the CSTool, the Otool and the M2Tool … to prepare the detailed alignment procedures |  |

### STructural Model (STM)

For the purpose of the SPIRE Structure development, a set of STM mirrors is delivered to MSSL.

These are not really mirrors but mass dummies whose CoG and inertia are within 5% of the real mirrors mass. The shape is to be simimlar to the real mirrors. No requirement is made on the surface as no optical test is to be conducted on this model.

These mirrors will be integrated in the SPIRE CQM Structure, along with STM of various critical subsystems, for the structure to sustain 300K vibrations to check the interface vibrations levels of the critical subsystems.

# Development calendar

| Hardware | Operations | Note | Dates |
| --- | --- | --- | --- |
| Diffusion measurement | Procurement and measurement | Beginning = PDR | Jul - Dec 2000 |
| Alignment tools | Design, manufacture, controls |  | Dec 2000 - Oct 2001 |
| CQM and PFM mirrors | ITT |  | Dec 2000 - Dec 2001 |
| STM mirrors | Design, manufacture, bakeout |  | Oct - Dec 2001 |
| STM mirrors | Delivery to MSSL |  | Jan 2002 |
| CQM mirrors | Controls and tests |  | Dec 2001 - Mar 2002 |
| CQM mirrors | Delivery to RAL |  | Apr 2002 |
| PFM mirrors | Control and tests |  | Mar 2002 - Jun 2002 |
| PFM mirrors | Delivery to RAL | If no modification needed (checked during CDR) | Apr 2003 |
| PFM and FS modified mirrors | Modification, design, manufacture, controls and tests | Beginning = CDR | Apr 2003 - Dec 2003 |
| PFM and FS modified mirrors | Delivery to RAL |  | From Jan 2004 |

See file Mirrors_Devplan_20000601.mpp for details.

# Description of deliverables

## Mirrors Deliverable models

| Model | Flight representativity | Difference with flight | Deliverables | Delivered to |
| --- | --- | --- | --- | --- |
| MM | Mass and CoG | Geometry | 1 set | MSSL |
| CQM | 100% | None | 1 set | RAL |
| PFM | 100% | None | 1 set | RAL |
| FS | 100% | None | 1 set of the modified mirrors w.r.t. CQM | RAL |

## Alignment tools

The alignment tools are delivered to RAL

One set will be delivered with the mirrors CQM. If no modification is needed, no further set will be delivered.

## Associated documentation

The documentation is TBD.