| HERSCHEL - SPIRE Spectrometer Mirror Mechanism subsystem development plan File : lam.pjt.spi.not.20000110_smec_development_plan.doc |  |
| --- | --- |

| Prepared by : | Date : |
| --- | --- |
| Dominique Pouliquen e-mail:dominique.pouliquen@astrsp-mrs.fr | 16 Oct 2001 |
| Checked by : | Date : |

Distribution List

| RAL | Ken J. King | X | Bruce M. Swinyard | X |
| --- | --- | --- | --- | --- |
| ATC | Colin Cunningham | X | Ian Pain | X |
| CEA-Sap | Jean-Louis Auguères | X | Christophe Cara |  |
| CNES | Yvan Blanc |  | Martine Joubert |  |
| DESPA | Guy Michel |  |  |  |
| GSFC | Don. E. Jennings | X | David Walser |  |
| LAM | Bruno Travers |  | Jean-Paul Baluteau |  |
|  | Claude Colin |  | Pascal Dargent | X |
|  | Kjetil Dohlen | X | Didier Ferrand | X |
|  | Michel Jevaud | X | Patrick Levacher | X |
|  | Alain Origné |  | Dominique Pouliquen | X |

# Document change record

| Date | Indice | Remarks |
| --- | --- | --- |
| 3 Feb 2000 | 1 | Creation of the document |
| 11 Feb 2000 | 2 | Distributed to the project |
| 1 May 2000 | 3 | Distribution List revised LAS changed into LAM One more model : STM added Mechanical scheme added MCU concept added |
| 24 May 2000 | 4 | BSM included Dates revised |
| 6 June 2000 | 5 | CDR date updated |
| 20 June 2000 | 6 | BSM dates included Documentation planning included in the associated mpp file |
| 20 Dec 2000 | 7 | Design description suppressed, see reference document SMECp suppressed, included in SMECm SMECm model philosophy revised (non vibrable CQM) MCU model philosophy revised (EM suppressed) Dates revised |
| 3 April 2001 | 8 | FIRST changed with HERSCHEL Dates revised |
| 10 April 2001 | 9 | More precisions on STQM Inconsistencies corrected on the LVDT topic |
| 16 Oct 2001 | 10 | Milestone dates corrected |

# Glossary

AD	Applicable Document

AVM	Avionic Model

BOL	Begin Of Life

BSM	Beam Steering Mirror

BSMm	BSM cryogenic mechanism

CEA-Sap	Commissariat à l'Energie Atomique, Service d’Astrophysique

CDR	Critical Design Review

CNES	Centre National des Etudes Spatiales

CoG	Center of Gravity

CQM	Cryogenic Qualification Model

DDR	Detailed Design Review

DESPA	Département des Etudes SPAtiales

DM	Development Model

DPU	Digital Processing Unit

DRCU	Digital Read-out and Control Unit

DSP	Digital Signal Processor

EGSE	Electrical Ground Support Equipment

EOL	End Of Life

ESA	European Space Agency

FPU	Focal Plane Unit

FS	Flight Spare model

FTS	Fourier Transform Spectrometer

GSFC	Goddard Space and Flight Center

H/K	House Keeping

H/W	Hardware

I/F	Interface

LAM	Laboratoire d'Astrophysique de Marseille

MAC	Multi Axis Controller

MCU	Mechanism Control Unit

MGSE	Mechanical Ground Support Equipment

MM	Mechanical Model

MSSL	Mullard Space Science Laboratory

NA	Not Applicable

OGSE	Optical Ground Support Equipment

PDR	Preliminary Design Review

PFM	Prototype Flight Model

RAL	Rutherford Appleton Laboratory

RD	Reference Document

SA

S/C	Spacecraft

S/W	Software

SMEC	Spectrometer mirror MEChanism

SMECm	SMEC cryogenic mechanism

SPIRE	Spectral and Photometric Imaging REceiver

TBC	To Be Confirmed

TBD	To Be Defined

TBU	To Be Updated

TBW	To Be Written

TC	TeleCommands

TM	TeleMetry

WE	Warm Electronics

ZPD	Zero Path Difference

# Table of contents

1.	Scope of the document	5

2.	Documents	5

2.1.	Applicable documents	5

2.2.	Reference documents	5

3.	Description of the spectrometer mirror mechanism subsystem	5

4.	Constraints	6

4.1.	Development constraints	6

4.1.1.	Technical constraints	6

4.1.2.	Organisation	7

4.1.3.	Calendar constraints	8

4.2.	Risk analysis	9

4.3.	Redundancy	9

5.	Work description	10

5.1.	Development and model philosophy	10

5.1.1.	Preliminary Design	10

5.1.2.	Procurement of long delay components	10

5.1.3.	SMEC and MCU development	10

5.1.3.1.	To the SMECm PFM	10

5.1.3.2.	To the MCU PFM	12

5.1.3.3.	To the MCU software PFM	13

5.2.	Verification	13

5.2.1.	SMECm	14

5.2.2.	MCU	14

5.2.3.	SMEC	15

5.2.4.	BSM	15

5.3.	Ground associated equipment	15

5.3.1.	Simulators	15

5.3.2.	Tools	16

5.3.3.	Additional equipment	16

6.	Development calendar	17

7.	Description of deliverables	19

7.1.	Deliverable models	19

7.1.1.	MCU models	19

7.1.2.	SMECm models	19

7.2.	Associated equipment	19

7.3.	Associated documentation	19

# Scope of the document

This document describes the development plan of the HERSCHEL/SPIRE Spectrometer mirror mechanism subsystem.

The development plan is based on the applicable and reference documents listed in §2.

The format of this document is compliant with the CNES instructions applicable at LAM [AD3].

# Documents

## Applicable documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| AD1 | SPIRE Spectrometer Mirror Mechanism Subsystem Specification | D.Pouliquen | LAS.PJT.SPI.SPT.200002 Ind 8 | 12 Oct 2001 |
| AD2 | SPIRE Development plan | K.King | SPIRE-RAL-PRJ-000035 1.1D | 12 Apr 2001 |
| AD3 | Guide pour les projets scientifiques | CNES | DTS/AQ/QP 98-083 | June 1998 |
| AD4 | SPIRE BSM Development plan | C.Cunningham | ? | 13 June 2000 |
| AD5 | SPIRE product assurance plan | G.Douglas | SPIRE-RAL-PRJ-000017 Iss 1.1 | 11 Apr 2001 |

## Reference documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| RD1 | Intrument Requirements Document | B.M.Swinyard | SPIRE-RAL-PRJ-000034 Iss 1.0 | 23 Nov 2000 |
| RD2 | SPIRE Major Milestone List | K.J.King | SPIRE-RAL-PRJ-000455 Iss 1.2 Draft 2 | 12 Apr 2001 |
| RD3 | SMECm design description | D.Pouliquen | LAM.PJT.SPI.NOT.200008 Ind 4 | 16 Oct 2001 |
| RD4 | MCU Design description | D.Ferrand | LAM.ELE.SPI.000619 Iss 3 | 20 Sep 2001 |
| RD5 | SPIRE Mirrors and alignment tools development plan | D.Pouliquen | LAM.PJT.SPI.NOT.200006 Ind 3 | 30 Mar 2001 |

# Description of the spectrometer mirror mechanism subsystem

The function of the Spectrometer mirror MEChanism subsystem (SMEC) is to move the SPIRE FTS corner cubes along a linear trajectory, at a given speed within given tolerances.

The critical performances of SMEC [AD1] are the mirror velocity and its stability, the mirror movement around its travel axis and the required accuracy of the mirror position measurements.

The SMEC is made of 2 main parts :

- The cryogenic mechanism (SMECm), which includes the mechanical part of the mechanism, the actuator, the position sensor and its preamplifier, the ZPD position sensors, the launch latches, the temperature sensors, the cryoharness. The SMECm is integrated in the SPIRE FPU Structure.

- The Mechanisms Control Unit  (MCU) , which includes the MAC board for the control of the mechanisms and the interface FPGAs the analog boards for the SMECm and the BSMm and the backplane board. The MCU is integrated in the SPIRE DRCU Unit.

# See RD3 and RD4 for details

# Constraints

## Development constraints

### Technical constraints

Note : the figures hereafter are for information only. The relevant figures are in [RD3] and [RD4]

The main performances specifications are:

- The mirror travel is +/-3.2 mm, -3.2/35.2 mm is a goal.

- The mirror speed is nominally 0.5 mm/s with a 0.01mm/s rms stability filtered with the detector filter on the travel over a 24 hours period. The mirror velocity shall be within 10 µ/s r.m.s. within a band width of 0.03 to 25 Hz over the ±3.2 mm range and within TBD outside this range.

- The speed value should be selectable from 0.2 to 1mm/s, up to 2mm/s is desirable.

- The mirrors tilt along travel axis < 10 arcminutes and decenter < 0.5 mm

- The measurement specification of the accuracy of the mirror position is 0.1µm over a 6.4mm travel, 0.3µm elsewhere.

- The measurement resolution of the mirror position is 0.5µm over the complete travel.

The main technical characteristics are :

- SPIRE lifetime on orbit = 4.25 years

- SPIRE spectrometer lifetime on orbit = 9 months

- SMECm operating temperature = 4K

- SMECm power = less than 2.4 mW, mean consumption along the whole mission

- SMECm mass = 1.65 kg including preamplifier and excluding 10% margin, mirrors and harness.

- SMECm level of radiations = 3.5 krad

- SMECm quasi static level : 25 g along X (launch direction), 14 g along Y and 14 g along Z

- SMECm sine vibrations level : 40 g along X, 25g along Y and 25 along Z

- SMECm random vibrations level = 10.2 g RMS along X (launch direction), 11.3g RMS along Y and 9.9 gRMS along Z

- SMECm shock level = TBD at 4K

- SMECm cleanliness = class 1000

- MCU level of radiations = 12 krad

- MCU vibrations levels = TBD

- Format of the MCU electronic cards = double Europe

- MCU Cleanliness = TBD

During its lifetime,

The SMECm is :

- transported to RAL under LAM responsibility.

- integrated at RAL in the SPIRE FPU Structure under joint RAL, MSSL and LAM responsibility.

The SPIRE-FPU is to undergo the project qualification/acceptance program under RAL responsibility.

The MCU is:

- designed under LAM responsibility.

- manufactured under LAM responsibility, part at LAM, part in the industry.

- qualified / accepted under LAM responsibility, part at LAM, part at CEA-SAp. The qualification / acceptance program includes thermal cycling, warm vibrations, EMI-EMC, tests with the SMECm, the BSMm and their associated boards.

- transported to CEA-Sap under LAM responsibility.

- integrated at CEA-Sap in the SPIRE DRCU under CEA-Sap responsibility.

The SPIRE-DRCU is to undergo the project qualification/acceptance program under CEA-Sap responsibility.

The SPIRE DRCU and the SPIRE FPU are integrated under RAL responsibility and undergo the project calibration program under RAL responsibility.

SPIRE is delivered to ESA under RAL responsibility.

SPIRE is integrated in the HERSCHEL satellite under ESA responsibility.

SPIRE CQM is to undergo the ESA test program under ESA responsibility.

SPIRE PFM is to undergo the ESA Acceptance program.

On the launch pad, before launching, the SPIRE FPU is cooled down to its operating temperature and launched cold.

SPIRE FS is prepared in the event of SPIRE PFM failure.

### Organisation

LAM is responsible for providing the SPIRE project with the SMECm and the MCU which comprises the MAC board, the SMEC board, the BSM board and the backplane board.

# The LAM responsibility covers :

- fulfillment of the performance requirements of the SMEC subsystem (SMECm+MAC+SMEC analog board).

- fulfillment of the technical requirements at the MCU level fulfillment of the technical requirements at the SMECm level.

- fulfillment of the interface requirements MCU – DPU, MCU – DRCU, MCU – BSMm and SMECm – Structure and optics.

- development, manufacture and qualification / acceptance of the SMECm and MCU.

- implementation of the UKATC electronic principles on the BSMm analog board in the MCU.

- implementation of the UKATC BSMm control algorithms.

- delivery of the SMECm and MCU models, their associated simulators, tools and documentation to RAL.

# LAM is not responsible for

- the performance requirements for the SMEC subsystem. This is a SPIRE system team responsibility.

- the temperature sensor choice. This is a SPIRE system  team responsibility.

- the temperature sensors measurement. This is a CEA-Sap responsibility.

- the principles of the BSMm analog board. This is a UKATC responsibility.

- the BSMm development, manufacturing and qualification / acceptance. This is a UKATC responsiblity.

- the BSM end to end performances. This is a UKATC responsibility.

- the BSMm control algorithms. This is a UKATC responsibility.

Under LAM responsibility, DESPA is responsible for the optical encoder feasibility, up to a PFM-like prototype. LAM is in charge of the qualification processes, manufacture and test of the optical encoder models and their integration in the SMEC.

CEA-Sap is responsible for the DRCU mechanical box inside which the MCU is integrated.

MSSL is responsible for the SPIRE structure inside which the SMECm is integrated.

IFSI is responsible of the DPU with which the MCU on board software will communicate.

### Calendar constraints

The main SPIRE milestones are [RD2]:

| Milestone | Date |
| --- | --- |
| PDR | Jun 2000 |
| UKATC delivers BSM Simulink model to LAM |  |
| Interface and system review | 27 Nov 2000 |
| CNES End of phase A review | 9 Jan -15 Feb 2001 |
| DDR - BSM & SMEC | 24 Apr 2001 |
| UKATC delivers analog board detailed design to LAM | Jan 2001 |
| LAM delivers the SMECm Simulator to CEA-SAp | Feb 2001 |
| UKATC delivers BSM DM to LAM | Mar 2001 |
| ESA delivers QM electronic components | Mar 2002 |
| LAM delivers the SMECm STM to RAL | Aug 2002 |
| LAM delivers the MCU-QM1 to CEA-SAp | Sep 2002 |
| LAM delivers the MCU-QM2 to CEA-SAp | Nov 2002 |
| UKATC delivers BSMm-CQM to LAM | Jul 2002 |
| ESA delivers last PFM electronic components | Oct 2002 |
| STM interim review (after 300K vibrations) | Oct 2002 |
| LAM delivers SMECm and BSMm CQM to RAL | Jan 2003 |
| WE CDR | Jul 2003 |
| RAL delivers SPIRE CQM to ESA | Apr 2003 |
| LAM delivers the MCU-PFM to CEA-SAp | Aug 2003 |
| UKATC delivers BSM-PFM to LAM | Jul 2003 |
| LAM delivers SMECm and BSMm PFM to RAL | Oct 2003 |
| UKATC delivers BSMm-FS to LAM | Jan 2004 |
| RAL delivers SPIRE PFM to ESA | Jun 2004 |
| LAM delivers SMECm and BSMm FS to RAL | Jan 2005 |
| RAL delivers SPIRE FS to ESA | Nov 2005 |
| HERSCHEL launch | 2007 |

## Risk analysis

In this document, the risk analysis concerns only the risks for this development plan not to be completed on time or not to ne completed at all.

| Risk | Type | Impact | Preventive action | Note |
| --- | --- | --- | --- | --- |
| HERSCHEL Microvibrations level and spectrum | Technical | Problem meeting performance requirements | Know the level and spectrum ASAP | This level has a direct impact on the speed stability. Must be included during design Should include the transfer function of the SPIRE structure. |
| Optical encoder = source of straylight | Technical | Problem for the FTS to meet the performance requirements | None (from LAM point of view) | Baffles will have to be added around the optical encoder => increase of mass, how to prove the efficiency before the CQM? |
| Optical encoder qualification failure | Technical | Delay in design Problem meeting performance requirements | None | If it turns out that it is not possible to qualify the optical encoder for the flight, a new position sensor will have to be found and a delay in the delivery dates will occur. This delay is due to the fact that LAM cannot provide the manpower and the budget that would be necessary to conduct the development of a baseline solution along with a back-up solution. As the optical encoder is the only one that meets the performance specifications, inevitably, the new one will not meet all of them and a trade-off will have to be made at system level. A candidate is an LVDT based solution. |
| The flex pivots do not bear the launch conditions | Technical | Feasability |  | To be tested with the STM. In case of problem on the STM, an alternate STM will be provided. |
| Flex Pivot problems (parasitic resonances, life tests) | Technical | Delay, Power consumption increase | Provision for different types of pivots | Replace flex pivots by more rigid pivots. => increase in power consumption + redesign the actuator (peak current limitation) |
| Administrative delays | Planning | Delivery dates | None | These delays are completly independant of LAM goodwill. Concerns mainly the MCU |

## Redundancy

The redundancy philosophy adopted for SPIRE is to duplicate every part that would be a single point failure.

The MCU incorporates two complete sets of MAC cards with identical functions and the SMEC and BSM analog boards are fully redundant.

The SMECm incorporates two optical encoders components in one optical system and two actuator coils.

The SMECm temperature sensors are duplicated.

The SMECm is equipped with 2 redundant LVDT for ZPD measurement.

The redundancy philosophy is to build two functionnally independent MCU’s, plugged to two electrically independent ciircuits on the cryogenic mechanisms and to two independent power supplies. No crossswitching of components is implemented at SMEC level. The switch from one assembly to the other is made at the DRCU level.

The redundancy for the SMECm launch latch is under discussion / progress.

# Work description

## Development and model philosophy

The model philosophy is compliant with the SPIRE project requirements and meets the LAM development needs.

### Preliminary Design

The mechanical design is based on the GSFC design. The first resonance frequencies and the mass are verified by tests.

An actuator type is chosen.

The optical encoder is a critical part and a qualification program has to be established. To establish a start point for the qualification program, a series of cryogenic tests is conducted to check the survivability of the encoder and to measure its output signal at cryogenic temperature.

The tests leads to the position sensor preamplifier specifications and the establishment of the list of components to be used for the flight in the optical encoder. These components include optical, electronic and mechanic ones.

The control loop design is verified by simulation and with a DSPACE system associated with mechanical mockups. The speed range and  the speed stability are verified. The position accuracy is checked with a reference LASER source. The prototype #1 is equiped with an actuator and the ground version of the SMECm PFM optical encoder and its stiffness is similar to the one expected on SMECm PFM.

The typical tests are defined. The typical tests are to be used through the life of the subsystem to check that it stays within the specifications. The typical tests are to be applied to the mechanism, the preamplifier and the warm electronic.

The interfaces with SPIRE WE are defined during this step.

The preliminary design is presented at the Preliminary Design Review. The PDR freezes the technical specifications and the interfaces.

### Procurement of long delay electronic components

Once the preliminary design has been validated by the PDR, the activities for procurement of long delay components is initiated. These are the electronic components to be mounted on the MCU, the SMECm PFM and FS and whose procurement will be made through ESA.

The optical encoder electronic components are procured. Those one cannot find in flight grade are individually tested. The tests are to demonstrate that these components are suitable for the flight. They consist in warm tests for accelerated aging and cold tests. Radiation tests or analysis are conducted.

### SMEC and MCU development

The development of  the MCU and of the SMECm will follow parallel paths.

Due to planning constraints, the MCU’s being delivered to CEA-SAp well in advance w.r.t. to the delivery of the SMECm’s to RAL, there will never be a complete deliverable integrated SMEC subsytem at LAM.

The only exception will be the SMECm CQM + MCU QM1. This is needed to discover all possible problems when mating the MCU with the mechanism. The planning does not allow to extend that verification to the SMECm CQM + BSMm CQM.

To circumvent that difficulty, all the deliverable SMECm’s will be tested allways with a unique non deliverable MCU model and all the deliverable MCU models will be tested with the SMECm and BSMm simulator..

Thanks to the MCU design solution (DSP based), there will be no analog adjustements to be performed on the various MCU’s to match them with the relevant SMECm model. The match will be done through a set of parameters which will be used through the DPU and identified as the CQM parameters, the PFM parameters and the FS parameters.

#### To the SMECm PFM

Detailed mechanical design

The mechanical design is based on the GSFC prototype design.

The detailed mechanical design encompasses the launch latch design and the flex pivot selection (manufacturer, type)

- Structure : the structure is defined and manufactured at LAM

- Launch latch : A commercial launch latch is bought to be tested at 300K and LN2 at LAM. A study is subcontracted in the industry to check the performances and reduce the peak current. The magnets are then purchased and the windings manufactured in the industry. It will be mounted in the SMECm-STM. As the SMECm-STM will have some kind of EGSE, it will be possible to activate the launch latch for real integrated tests.

- Flex pivots : A study is conducted to prove that flex pivots are compatible with the structure design and the launch vibrations conditions. Modified pivots could have to be used. They will be purchased after selection of a manufacturer.

- Sensor position : a development model has been developed by DESPA. Commercial components have been purchased to build a prototype of the PFM (dimensions, redundancy, power, mass). This prototype is being prepared for cryo tests. As soon as the tests have been successfully passed, three models are built at LAM to be integrated in the SMECm-DM, the SMECm-CQM and the SMECm-STQM.

- ZPD sensors : two redundant LVDT's are used for this function.

- Actuator : The SMECm prototypes have been fitted with a commercial actuator. Its power consumption is within specifications but the peak current is too high and its dimensions are slightly too large. The flight actuator is a modified version. A study is subcontracted in the industry. As for the launch latches, magnets are purchased in the industry and the windings realised in the industry too.

- Thermal sensors : the sensors type is defined by the system team.

Launch vibrations (STM deliverable then back to LAM and STQM, non deliverable)

Once the mechanical design is finished, a SMECm STM is built. It will be used to verify that the design can survive the launch. This STM will have no active components. These components will be replaced with equivalent mass dummies. But, as the SPIRE STM (subsystems STM’s mounted in the CQM structure) will be used to check the SPIRE FPU thermal modelisation, heaters will be mounted to be able to simulate the power dissipations.

The vibrations will be made at 300K at the LAM vibration facility, up to calculated qualification levels provided by MSSL.

At this point, design modifications are envisioned.

After that, cryogenic flex pivots will be mounted and a 300K vibration test at low level (signature test) will be performed to check that the change of pivots has not affected the mechanical behaviour of the mechanism.

A heater for thermal dissipation simulation will be mounted.

Then the STM will be delivered to RAL to be integrated into the CQM SPIRE structure.

In case of delays in this development, to avoid delaying the SPIRE STM tests, the SMECm STM pivots could be replaced with Teflon rods of apporximately the same behaviour. This configuration is tested at 300K, warm vibrations prior to delivery to RAL.

Once integrated, the SPIRE structure will be warm vibrated, then cold vibrated and thermally tested. During these vibrations, the structure / SMECm interface levels will be measured.

As soon as the results of these tests are available, the SMECm STM is dismounted from the SPIRE structure and shipped back to LAM.

At LAM, the mass dummies will be replaced with non redundant active components (one actuator, one set of position sensors) to become a « STQM » i.e. a full qualification model. This model will be warm vibrated at the LAM vibration facility at the levels measured during the 300K vibrations of the SPIRE structure and then cryovibrated at RAL at the levels measured during the cryovibrations of the SPIRE structure. The STQM is not a deliverable model.

During this development, vibrations include sine, random and shocks.

Then the design will be declared good for launch.

Lifetests (DM, non deliverable)

As soon as the first 300K vibrations have been performed on the SMECm STM and design modification identified and done, a SMECm DM will be built. This model will be used to demonstrate that the components are able to withstand the lifetime on orbit. For that the DM will be a mechanical copy of the STM and equipped with cryogenic flex pivots, an actuator, the position sensors and temperature sensors. It will be driven by MCU MI3 (see MCU paragraph). It will sustain the lifetests, i.e. about 2.6 months at various travel values with the max 5 mm/s speed, at 20K.

It will not be subjected to vibrations.

Microvibrations impact will be evaluated on this model, the ones emitted by the mechanism and those to which the model is susceptible.(level and spectrum)

Then the design will be declared good for the on orbit life.

The SMECm CQM (deliverable)

The SMECm CQM is a cryogenic model which has no vibration capability (due to planning constraints.).

It is equipped with functional components but with no redundancy. As for the DM, it will be built after the first SMECm STM 300K warm vibrations to be as near as possible to the final mechanical design. It will incorporate a launch latch for functional tests and transportation purpose.

It will be full functional, i.e. fully compliant with the performance,  electrical and thermal requirements and with the mechanical interfaces. Microvibration behaviour will be checked.

It will be tested at LAM with MCU MI4 (see MCU paragraph). The tests will include 20K tests at LAM to tune the control parameters.

Provision has been made in the planning to allow for 20K tests at LAM with the BSMm CQM to check the compatibility of both mechanisms in the cryogenic environment with the MCU.

The SMECm PFM (deliverable)

The SMECm PFM will be built as soon as the mechanical design has been declared mechanically good for the launch and for the on orbit life.

It will sustain the classical path of a PFM, acceptance vibration tests (both warm at LAM and cold at RAL) , thermal cycles at LAM, performance tests at LAM including microvibrations, etc…

Povision has been made for joint tests with the BSMm but that operation could be skipped if the CQM tests have shown no problem.

The SMECm FS (deliverable)

The SMECm-FS could be the SMECm-CQM refurbished to flight level. This is still TBC as it depends on ESA that the back delivery of the CQM arrives on time and on the amount of modifications. For the moment, it is planned to manufacture a full new SMECm-FS. In any case, most of the components would have to be replaced as they would have sustained the qualification program. In consequence, it is planned to build a completly new SMECm model.

The SMECm FS is a copy of the SMECm PFM and will follow the same history.

#### To the MCU PFM

Detailed electrical design

The detailed design encompasses all the functions of the subsystem. A working version of the on-board software is written.

For that purpose, one development model MCU is built at LAM, which is functionnal, not geometrically correct, fitted with commercial components and witout redundancy. It is used to verify the principles.

The MCU QM1 (deliverable)

A QM1 set of cards is built at LAM. It is functionnally correct without redundancy. It has not to fit in the PFM allocated volume/surface, is fitted with commercial components. At LAM, it will be used to operate the SMECm CQM.  There will not be time enough to have it operate both SMECm and BSMm mechanisms at LAM. So, it will be delivered to CEA-SAp before and tested along with the DRCU box at CEA-Sap, then delivered to RAL to operate the SPIRE CQM. The QM1 will stay at RAL once the SPIRE CQM has been delivered to ESA. The MCU QM1 will have maximum flexibility (donwloading of software, electronic options implemented) to be able to check all possible configurations.

The MI’s (Modèle d’Identification in french) (MI4 deliverable TBC, the others not)

Three MI’s (Modèle d’Identification in french) will be subcontracted in the industry, which are copies of the QM1 and which will be used as follows (there is no number 1, this being QM1)

- MI2 : kept by the LAM electronic service so that they always have a model to test the software

- MI3 : will be used for the LAM tests on the deliverable mechanisms models

- MI4 : could be delivered to UKATC to allow them to operate the BSMm’s with a representative MCU (The need has to be confirmed by UKATC)

The QM1 flexibility will be retained.

The MCU QM2 (deliverable)

This model will be subcontracted to the industry.

This model will be the real qualification model for the MCU electronic and will sustain the relevant tests (thermal, vibrations, EMC). The components are flight like components, redundancy is implemented. MCU QM2 will be integrated in the DRCU QM2 box at CEA-Sap for CEA-Sap to qualify the complete DRCU box.

Prior to delivery to CEA-Sap, the MCU QM2 will be tested at LAM with mechanisms simulators.

The MCU PFM (deliverable)

This model is a copy of the MCU QM2 with flight components.

It will be subcontracted to the industry.

It will follow the same path (with acceptance levels), be integrated in the DRCU PFM box and so on.

The MCU FS (deliverable)

This model is a copy of the MCU PFM.

It will be subcontracted to the industry.

It will follow the same path and will be delivered to CEA-Sap if needed, as spare parts for the PFM.

#### To the MCU software PFM

The software development will follow the ESA OBS specification (ESA PSS5 ) applicable to the MCU software.

The software development will be made on the DSP evaluation board.

Preliminary design = function and tasks list.

Detailed design = algorithm specification.

Coding

Unitary tests = elementary function tests with test report.

Integrated software tests :

comparison between the DSPACE based control performance and the DSP based control software.

Telecommands software qualification based on commands scenarii.

Integration of the software on the MCU DSP, with the boot program and the memory mapping.

Redo the tests, beginning with the unitary tests.

The first version of the MCU software will be loaded int he MCU QM1 DSP.

## Verification

The verification plan must be compliant with the project verification plan [AD2, RD1] and must fulfill the SMEC development needs.

In the tables below,

| T = | a real test or measure is performed |
| --- | --- |
| A = | an analysis is performed |
| NA = | Non applicable |

Basic performances (functional test) are controlled during environmental testings. This control is based upon the typical test  (yet to be defined) and always performed following the same procedure.

- 300K vibrations are conducted at LAM.

- Vacuum cycles, soak cycles, thermal cycles (temperature between 20K and 80°C) are conducted at LAM.

- 20K Lifetime tests are conducted at LAM.

- 20K Performance tests are conducted at LAM.

- EMI/EMC tests are conducted in the industry (at INTESPACE, TBC).

- Microphonics tests are conducted at SPIRE level.

- 4K vibrations are conducted at RAL

- Functional 4K tests are conducted at RAL.

### SMECm

|  | SMECm-DM | SMECm-STM | SMECm-STQM (8) | SMECm-CQM | SMECm-PFM | SMECm-FS |
| --- | --- | --- | --- | --- | --- | --- |
| Interface control | T | T | T | T | T | T |
| Mass, CoG, Stiffness mesasurement | T | T | T | T | T | T |
| Carriage tilts measurement | T | T | T | T | T | T |
| Travel measurement | T | T(4) | T | T | T | T |
| Launch latch test | T | T | T | T | T | T |
| Microvibrations | T(7) | NA | NA | T(7) | T(7) | T(7) |
| Vibrations 300K | NA | T | T | NA | T | T |
| Vibrations 4K | NA | T | T | NA | T | T |
| Power Consumption measurement | T | T(5) | T | T | T | T |
| Thermal/Vacuum cycle | T | NA | NA | T | T | T |
| Functional 4K test | NA | NA | T(6) | T(9) | T(9) | NA |
| Bakeout | T | T | NA | T | T | T |
| Lifetime | T | NA | NA | NA | NA | NA |
| Radiation tolerance | NA | NA | NA | A(2) | A(2) | A(2) |
| Microphonics | NA | NA | NA | A(3) | A(3) | A(3) |
| EMI / EMC | NA | NA | NA | A(1) | A(1) | A(1) |

(1) : At subsystem level, only EMI/EMC analysis can be performed.

(2) : The radiation tolerance is verified by analysis only, taking into account the materials involved.

(3) : At subsystem level, only an analysis is to be performed. Real microphonic tests are to be done at the SPIRE FPU level.

(4) : Done to check that the possible travel is the expected one. No real actuator implemented.

(5) : Measurement of the power dissipated in a heater simulating the real actuator.

(6) : Done during 4K vibrations campaign.

(7) : Not yet defined

(8) : Not a new model : STQM = STM + position sensor + actuator

(9) : Done on the PFM during 4K vibrations campaign.

### MCU

|  | MCU-MI’s | MCU-QM1 | MCU-QM2 | MCU-PFM | MCU-FS |
| --- | --- | --- | --- | --- | --- |
| Interface control | T | T | T | T | T |
| Power Consumption measurement | T | T | T | T | T |
| Vibrations 300K | NA | NA | T | T | T |
| Soak/Cycle | NA | NA | T | T | T |
| Radiation tolerance | A(1) | A(1) | A(1) | A(1) | A(1) |
| Thermal Range | A | NA | T | T | T |
| Thermal stability | A | NA | T | T | T |
| EMI / EMC | A | A | A | A | A |

- : The radiation tolerance is verified by analysis only, taking into account the materials and the components involved.

- : the EMI/EMC tests are to be conducted at the DRCU level.

### SMEC

SMEC = SMECm + MCU Evaluation board for the DM or QM1 for the CQM, or MI3 for the PFM and FS.

At the SMECm subsystem level, the performances are thoroughly verified.

They are checked at 300K and 20K at LAM and at 4K at RAL (TBC).

| In every operational modes, | SMEC-DM | SMEC-STQM | SMEC-CQM | SMEC-PFM | SMEC-FS |
| --- | --- | --- | --- | --- | --- |
| Travel range | T | T | T | T | T |
| Speed range | T | T | T | T | T |
| Speed stability | T | T | T | T | T |
| Position measurement accuracy | T | T | T | T | T |
| Mirror movement (tilts) | T | T | T | T | T |
| Travel/Speed calibration | NA | NA | T | T | T |
| Power consumption | T | T | T | T | T |

### BSM

For the BSM board, the verification is included in the MCU verification.

The verification of the BSMm is done first at UKATC (see the BSM development plan) and with SMEC once integrated with the MCU. At this level, the verification will consist in adjusting the control loop parameters.

## Ground associated equipment

The ground equipments are used to develop and test one item without the presence of the others.

Only the equipements needed for SMEC development are listed.

The simulators replace one or more items.

The tools are used to operate, check or integrate an item.

Most simulators are PC based as it is the most flexible and economical solution.

All the simulators and tools  are needed since all subsystems are to be tested at approximately the same time.

### Simulators

| Simulator | Used for… | Functions | Deliverable |
| --- | --- | --- | --- |
| DRCU / DPU EGSE | …the control and monitoring of the MCU during tests and commissionning | Replaces DRCU and the DPU Receives position data, synchro signals and temperature signals. Simulates Interfaces: Serial, Parallel, Analog and Synch. Bus Supplies power. Sends commands. | No |
| SMECm and BSMm Simulator | …MCU development and testing and …post DRCU / MCU integration testing. | Replaces SMECm Receives actuator current values. Simulates the main parameters of the real SMECm : resonance frequencies, stiffness, noises, electrical behaviour. Delivers simulated thermometer values and simulated preamplified optical encoder signals | Three will be produced , one for LAM and two deliverables, one for CEA-Sap and one for UKATC. |

### Tools

| Tool | Used for … | Functions |
| --- | --- | --- |
| CCA Tool | … the alignment of SPIRE mirrors | Replaces SMECm during the alignment. Note that this tool appears in the SPIRE mirrors and alignment tools development plan. It is not mentioned any further here. |
| SMECm EGSE | … SMECm development and testing | Replaces MCU. Receives commands : travel range, speed value. Is able to control and monitor SMECm Sends actuator current analog values, powers the temperature sensors and the optical encoder Receives and processes temperature, actuator current, synchro signals and preamplified or non-preamplified position measurements. Sums up the operational time. |
| SMECm AT | …mirror cinematic checking and …mirror alignment w.r.t. SMECm baseplate | Measures travel range, mirror position, mirror tilt around travel axis w.r.t. the fixations points of the SMECm in the SPIRE structure.. |
| SMECm OGSE | …SMECm alignment in SPIRE spectrometer structure | Allows SMECm position control and adjustement inside SPIRE spectrometer structure. Will be avoided if it is proved that mechanical tolerances are OK with optical tolerances. |
| SMECm MGSE | …SMECm Integration in the SPIRE spectrometer structure or in any test equipment | Allows SMECm handling during its integration in a structure. |
| MCU STM | … DRCU level vibrations and thermal tests | Replaces the MCU cards in case of problem, avoiding halting the DRCU qualification or acceptance program. Only cards plus masses in lieu of the components. CoG representative. Power dissipation representative (heaters) |

### Additional equipment

A mechanical box identical to the MCU part of the DRCU box is to be built. This will allow the integration procedure verification at LAM and the mechanical tests on the MCU to be conducted at LAM.

# Development calendar

SMECm calendar

|  |  | Dates | Comments |
| --- | --- | --- | --- |
| GSFC Prototype 2 | Tests at RAL | Mar 2001 | Performances OK => design and control software OK for the science. |
| Flex pivots | Design study | Mar - Jun 2001 | Feasability of the SMECm + pivots concept Adaptation of standard pivots |
|  | ITT | Jun - Dec 2001 |  |
| STM program | Manufacture | Oct 2001 - mar 2002 | Vibration campaign with modifs in between 300K. If ITT avoided, campaign with BE System |
|  | Vibrations tests | Apr - May 2002 | Still 300K |
|  | Delivery | From May 2002 | 3 months margin. Could be used for a vibration tests in a STQM like configuration and/or for a cryovibrations campaign? |
|  | Back delivery RAL to LAM | Feb 2003 |  |
|  | STQM configuration & tests | Feb - Apr 2003 | On time for CDR with a 1 month margin Could possibly be done before STM delivery |
| Actuator & launch latches | Development & manufacture | Apr 2001 - Feb 2002 | 6 actuators and 12 launch latches for the CQM, DM, PFM, FS and 2 redundancies. |
| CQM program | Flex pivots procurement | Feb - May 2002 |  |
|  | Manufacture & tests | Jan - Aug 2002 | Excluding vibrations |
|  | Association with BSMm CQM & tests | Sep - Oct 2002 | Verifies the software with real models. |
|  | Delivery | Fom Oct 2002 | 2.5 months margin |
| DM program | Flex pivots procurement | May - Jul 2002 | Excluding vibrations |
|  | Manufacture, controls & life tests | Jan 2001 - Feb 2003 | On time for the CDR 4 months margin |
| PFM program | Design modif | Oct - Dec 2002 | Following STM interim review |
|  | Manufacture, controls and acceptance tests | Jan 2002 - Jul 2003 | Begins after STM interim review. Including CryoVibrations FS manufactured with PFM |
|  | Association with BSMm PFM and tests | Aug - Sep 2003 | Could be avoided? (already done on CQM) |
|  | Delivery | From Sep 2003 | <1 month margin. To increase the margin, start the PFM when delivering the STM and do not conduct common tests with the BSMm |
| FS program | controls and acceptance test | Oct 2003 - Jan 2004 | Often waits for the PFM Including CryoVibrations |
|  | Association with BSMm PFM and tests | Jan - Mar 2004 | Could be avoided? (already done on CQM) |
|  | Delivery | From Mar 2004 | 8 months margin |

# MCU Calendar

|  |  | Dates | Notes |
| --- | --- | --- | --- |
| Dvlpt | Electrical model and DSP evaluation board | Jun 2000 - Aug 2001 |  |
|  | CEA-SAp delivers to LAM the definitive card dimensions | May 2001 | Needed for the ITT |
| QM1 | Manufacture, tests, software | Jan 2001 - Mar 2002 |  |
|  | Tested with SMECm-CQM | Apr - Jul 2002 |  |
|  | QM1 delivery to CEA | Jul 2002 | 1 month late w.r.t. milestone. We must test the QM1 with the SMECm CQM (and it would be better to test it also with the BSMm) |
| MI's | Manufacture | Mar - Jul 2002 |  |
|  | MI4 delivery to UKATC | Jul 2002 | The UKATC need is TBC |
|  | MI3 available for SMECm+BSMm CQM tests | Jul 2002 |  |
|  | ITT for the QM2, PFM and FS | Sep 2001 - Apr 2002 |  |
| Qualif electronic components | Delivery from ESA | 15 Oct 2001 |  |
| QM2 | Manufacture and tests | Apr - Dec 2002 | LAM + industry |
|  | Delivery to CEA-Sap | From End Dec 2002 | 2 months late We must be sure that everything is Ok with the QM1 before manufacturing the QM2 |
| Flight electronic components | Delivery from ESA | 15 Oct 2002 |  |
| PFM | Manufacture and tests | Nov 2002 - Aug 2003 | Waits for QM2 declared OK No way to wait for the CDR |
|  | Delivery to CEA | From Jul 2003 | 1 month late |
| FS | Manufacture and tests | Mar 2003 - Jan 2004 | Waits for the PFM to be completed |
|  | Delivery to CEA | From Jan 2004 | No need date |

Detailed planning in file SMEC_DevpPlan_20011015.mpp.

# Description of deliverables

## Deliverable models

### MCU models

| Model | Flight representativity | Difference with flight | Deliverables | Delivered to |
| --- | --- | --- | --- | --- |
| QM1 | Dimensions, interface, functions | No redundancy, flight equivalent components | 1 | CEA-SAp |
| QM2 | Dimensions, interface, functions, redundancy | Flight equivalent components | 1 | CEA-Sap |
| PFM | 100% | None | 1 | CEA-Sap |
| FS | 100% | None | 1 | CEA-SAp |

### SMECm models

LAM will deliver the BSMm at the same time as the SMECm models (Not applicable to the STM)

| Model | Flight representativity | Difference with flight | Deliverables | Delivered to |
| --- | --- | --- | --- | --- |
| STM | Mass, CoG, Stiffnesses | No active components, only mass dummies | 1 | RAL |
| CQM | 100%, except… | … no redundancy, only mass dummies and non vibrable | 1 | RAL |
| PFM | 100% | None | 1 | RAL |
| FS | 100% | None | 1 | RAL |

## Associated equipment

The associated equipment is for integration and  alignement.

| Model | Use/Function | Associated with | Deliverable |
| --- | --- | --- | --- |
| MCU SIM | Controls the MCU/DRCU interfaces Simulates the MCU as seen from the DRCU | Any SPIRE WE model | 1 to CEA-SAp |
| MECm SIM | Simulates the electrical interfaces of the SMECm and BSMm during MCU integration into DRCU | Any deliverable MCU | 1 to CEA-SAp, 1 to RAL |
| SMECm EGSE | SMECm control and monitor during integration and before and after transportation | Any deliverable SMECm | 1 to RAL |
| SMECm MGSE | SMECm integration in the SPIRE Structure | Any deliverable SMECm | 1 to MSSL (for the STM) and 3 to RAL (1 with the CQM, 1 with the PFM, 1 with the FS) |
| SMECm OGSE | SMECm alignment after integration in SPIRE structure | Any deliverable SMECm | 1 to RAL |

The CCA tool is deliverable, listed in the optics and alignement tools deliverables.

## Associated documentation

The documentation to be delivered to RAL is defined in AD5.