SPIRE

| SUBJECT: | SPIRE AIV Facility Milestone PlanSPIRE AIV Facility Milestone Plan |
| --- | --- |
| PREPARED BY: | D.L.SmithD.L.Smith |
| DOCUMENT No: | SPIRE-RAL-DOC-000???SPIRE-RAL-DOC-000527 |
| ISSUE: | 0.10.3 | Date: | 19-March-2001 |
| Approval: |  |  |
|  | P. Hargrave (QMW) | Date |

| Approval: |  |  |
| --- | --- | --- |
|  | B. Swinyard (RAL) | Date |

| Approval: |  |  |
| --- | --- | --- |
|  | K. King (RAL) | Date |

Distribution

| RAL | Ken King |
| --- | --- |
|  | Bruce Swinyard |
| QMW | Alex Ellery |
|  | Peter Hargrave Matt Griffin |

# Change Record

| ISSUE | DATE |  |
| --- | --- | --- |
| 0.1 |  |  |
| 0.2 |  |  |
| 0.3 | 19-March-2001 | Draft Baseline Plan |

# References

# Applicable Documents

| AD1 | SPIRE-RAL-PRJ-000455 Issue 1.0 - SPIRE Major Milestone List |
| --- | --- |
| AD2 | SPIRE-RAL-DOC-000477 Issue 0.1 – SPIRE Test Facility Development Plan |

Reference Documents

| RD1 | SPIRE-RAL-PRJ-000463 Issue 1.2Draft – SPIRE Test Facility Requirements Specification |
| --- | --- |

# Introduction

This document lists the high level milestones for the SPIRE AIV Facilities, including the cryolab, cryostat, calibration equipment, AIT clean rooms and cold vibration facility.  The list also contains the major SPIRE milestones that constrain the AIV facilities schedule.

# Milestone List

| Milestone | Ref. | Resp. | Baseline | Current | Actual |
| --- | --- | --- | --- | --- | --- |
| SPIRE Project Milestones |
| SPIRE STM Program Starts | AD1 | RAL | 01/08/02 | 01/08/02 |  |
| SPIRE EGSE Delivered | AD1 | RAL | 01/02/02 | 01/02/02 |  |
| SPIRE CQM Program Starts | AD1 | RAL | 01/02/03 | 01/02/03 |  |
| SPIRE PFM Program Starts | AD1 | RAL | 01/06/03 | 01/06/03 |  |
| AIV Facility Milestones |
| Cryostat Design Complete | AD2 | RAL | 31/12/00 | 31/12/00 | 08/01/01 |
| Cryostat Manufactured | AD2 | RAL | 01/11/01 | 01/11/01 |  |
| Cryostat Integrated | AD2 | RAL | 30/01/02 | 30/01/02 |  |
| Cryostat Commissioned | AD2 | RAL | 01/04/02 | 01/04/02 |  |
| Cryoharness Delivered | AD2 | RAL | 01/03/02 | 01/03/02 |  |
| Cryolab Available | AD2 | RAL | 01/07/01 | 01/07/01 |  |
| Telescope Simulator Delivered | AD2 | RAL | 21/12/01 | 21/12/01 |  |
| TFCS Cryostat Monitoring | AD2 | RAL | 31/12/01 | 31/12/01 |  |
| TFCS Complete | AD2 | RAL | 30/04/02 | 30/04/02 |  |
| FTS Delivered | AD2 | QMW | 01/03/02 | 01/03/02 |  |
| Cold BB Delivered | AD2 | QMW | 02/12/01 | 02/12/01 |  |
| Reference Detector | AD2 | QMW | 30/10/01 | 30/10/01 |  |
| Hot BB Delivered | AD2 | RAL | 01/03/02 | 01/03/02 |  |
| FIR Laser | AD2 | RAL | 08/06/01 | 08/06/01 |  |
| Beam Monitor | AD2 | TBD | 01/03/02 | 01/03/02 |  |
| Clean Rooms |  | RAL | 31/07/02 | 31/07/02 |  |
| Inspection Facility |  | RAL | 31/07/02 | 31/07/02 |  |
| Vibration Facility |  | RAL | 01/08/02 | 01/08/02 |  |
| Bakeout Chamber |  | RAL | 01/08/02 | 01/08/02 |  |