# Staffing

Neal Todd has left IC. Matthew Graham has replaced him on a temporary basis until a permanent replacement is expected in October. Giovanni Bisaglia has “given up his collaboration”. A replacement is being sought from the Italian part of the consortium.

# Meetings and their Conclusions

| Date | Location | Meeting | Comments |
| --- | --- | --- | --- |
| 12/02/2001 13/02/2001 | RAL | QLA workshop | To identify requirements on the QLA. |
| 29/03/2001 | ESTEC | CSDT#3 |  |

# Activities

## General

- Work is progressing on the ICC work packages.

- The ICC Use Cases are being completed.

- Installation and testing of SCOS-2000 is in progress.

- Versant has been installed under Solaris 2.6 and is working.

- QLA requirements are in preparation.

## Training

None this month.

## Work during month on HCSS activities

| WP | Days Worked (month) | Days Worked (total) | Days Planned (Total) | Comments |
| --- | --- | --- | --- | --- |
| 22410.EP2 ILT system | 1.0 | 4.0 | 40 | Added this month |
| 22420.EP2 ILT integration |  |  | 30 |  |
| 22430.EP2 HGSSE | 1.0 | 4.0 | 15 | Added this month |
| 22440.EP2 System Eng |  |  | 15 | Added this month |
| 24250.EP2 Data frame |  |  | 20 |  |
| 24370.EP2 SPIRE IA | 0.5 | 2.0 | 50 | Added this month |
| 24510.EP2 RTA I/F AA | 2.0 | 3.0 | 50 |  |
| 24520.EP2 RTA I/F pro | 0.5 | 0.5 | 50 |  |
| 24530.EP2 RTA I/F imp |  |  | 70 |  |
| 24610.EP2 TC History AA |  |  | 30 |  |
| 24620.EP2 TC History pro |  |  | 30 |  |
| 24630.EP2 TC History imp |  |  | 70 |  |
| 25500.EP2 Consultancy |  |  | 5 |  |
| 27000.EP2 Coordination |  |  | 15 |  |
| 29000.EP2 Review | 1.5 | 6.0 |  | CSDT#3, 1.5 days from last report moved to w/p 24370 |
| 2B000.EP2 Contingency |  |  |  |  |

# Critical Areas, Concerns, Upcoming Events

## Critical Areas

As it is unclear which ICC tasks after HCSS 0.1 are part of a common development it is difficult to determine the SPIRE contribution to the HCSS from 2002. This is causing a delay in the SIP.

## Concerns

The loss of Giovanni Bisaglia means that the staffing is less then anticipated until a replacement is found.

There is still no agreed date to attend the Versant training course. It would be advantageous to attend this course as soon as possible.

## Upcoming Events

| Date | Location | Event | Comments |
| --- | --- | --- | --- |
| 05 April | IC | RTA meeting | For HCSS development |
| 24 April | SRON | CSDT#4 |  |
| 25-26 April | IC | SPIRE ICC requirements review |  |
| 30 May | ESTEC | CSDT#5 |  |

KJK, SG, 30th Mar 2001