# SPIRE-QMW-MAG-000614

# Note IIDR Preparation Plan and draft agenda
27 March 2001

Matt Griffin

- KJK to monitor document provision and arrange for electronic distribution

- Distribution to ESA by placing on Livelink

- Gordon Stacey needs access to docs. Either through authorised access to Livelink or ftp site

- Otto Bauer has access to Livelink ?

List of documents to be issued for the review

| No. | Title | Responsible | Status |
| --- | --- | --- | --- |
| 1 | Design Description Document | DG BMS MJG | DG, BMS, MJG working on it. DG = custodian. MJG parts to be done by April 6. Final version to be approved by BMS for distribution April 13 |
| 2 | IID-B | JD BMS | BMS and JD updating MJG to revise Chapter 4 by Thursday Draft version or information to go into chap 5. to ESA (for Alcatel) by March 29. Tidy version by April 6th Other Chapters need reading and checking |
| 3 | Verification Requirements | BMS | Ready for release on 29 March |
| 4 | AIV Plan |  | Ready for release on 29 March goes together with AVM Reqs; STM Reqs and CQM reqs. |
| 5 | FPU Integration Plan | BW | BW to send draft to JD by March 30. To be reviewed by JD and BMS for issue on Apr. 13 |
| 6 | Alignment Plan | BMS | Will be issued March. 29 |
| 7 | Product Tree | KJK | To be updated for issue April 13 |
| 8 | WBS | KJK | To be updated for issue April 13 |
| 9 | Milestone List | KJK | Has been issued. LAM compatibility to be confirmed. KJK to finalise for April 13 |
| 10 | Master schedule | KJK | KJK to produce boiled-down version for April 13 |
| 11 | Dev. Plan. Overview | KJK | Draft to be ready for review by BMS/MJG by April 5 |
| 12 | Subsystem Development Plans | KJK | To be included in appropriate form in April 13 distribution |
| 13 | PA Plan |  | Has been updated as per ESA and KJK comments. To be issued on April 13. |
| 14 | Configuration Control Plan |  | Dave Kelsh has produced a draft. BMS/JD to approve. Doc. To be issued April 13 |
| 15 | Management Plan |  | MJG has produced semi-revised version for CNES review. KJK to update for final review. To be issued April 13 if possible. |
| 16 | GSE Several docs needed here? Looks like damage-limitation needed | BMS/KJK | BMS to prompt Berend on MGSE OGSE is in Alignment Plan EGSE - we can copy what PACS have done adding SPIRE-specific features AIV req. doc exists needs review |
| 16 | OBS URD | KJK | Already exists. Include in set for April 13 distribution. |
| 17 | SRD | MJG | Same version as in Nov. - MJG to check if any updates needed. Distribution April 13 |
| 18 | IRD | BMS | Same version as in Nov. - BMS to check if any updates needed. Distribution April 13 |

| 19 | OMD |  | Same version as in Nov. - MJG to check if any updates needed. Distribution April 13 |
| --- | --- | --- | --- |
| 20 | SSSDs for: FTS BSM Cooler BDAs Calibrators Optics Structure DRCU DPU | BMS/KJK/JD | To be reviewed appropriately. Docs. as issued should be in two categories - those which are signed off and those which are drafts for information. |
| 21 | Key ICDs | BMS/JD/BW | To be clarified. |
|  | To be provided on best efforts basis |
| 22 | Technical notes and papers |  | MJG Toledo paper KD SPIE optics paper MC SPIE diffraction analysis paper BMS SPIE FTS paper TR Stray light model Cooler? |
| 23 | Test Reports |  | BMS to compile Detectors: Jamie's draft detector paper?. Adam's test report from detector selection meeting. Info on JFETS? Cooler: TRP report Calibrators: Report on PCAL and SCAL from QMW FTS: Need something on this - BMS to chase LAM on getting test report compilation. Should include MCU test report BSM: MJG to ask Ian Pain Structure: ? Warm electronics: ? |

Documents to be sent to ESA on March 29:

- Verification Requirements Document

- AIV plan

- Alignment Plan

- DDD table of contents

- Draft agenda for the IIDR

SPIRE IIDR		RAL, 23, 24 April 2001     	   	Agenda