300mK Straps

Subsystem Development Plan

Document Ref.: SPIRE-QMW-PRJ-000629

Issue: 2.0

Prepared by: Pete Hargrave

Last Modified on: 12 February 2001

Approved by:

Distribution list

Update history

| Date | Version | Remarks |
| --- | --- | --- |
| 8/01/01 | Draft 1.0 | Creation of document |

Table of Contents

1.	Scope	4

2.	Documents	4

2.1.	Applicable documents TBW	4

2.2.	Reference documents TBW	4

2.3.	Glossary TBW	4

3.	Subsystem Description	4

3.1.	Block diagram	7

4.	Organisation	7

5.	Deliverables	8

6.	Constraints	9

6.1.	Technical constraints	9

6.1.1.	300mK strap performance requirements	9

6.2.	System constraints	9

6.2.1.	300mK straps system requirements	10

6.3.	Calendar constraints	10

7.	Work Description	10

7.1.	Model philosophy	10

7.2.	Preliminary design phase	11

7.2.1.	Materials testing	12

7.2.2.	Interface study	12

7.2.3.	Modeling	12

7.2.4.	Prototyping	12

7.2.5.	Testing	12

7.3.	Procurement of long lead-time components	13

7.4.	Detailed design phase	13

7.5.	STM/CQM manufacture & test	13

7.6.	PFM & FS manufacture & test	14

7.7.	Work flow	14

8.	Risk analysis	16

9.	Verification plan –To Be Updated	17

10.	Development calendar & schedule	18

11.	300mK straps sub-system schedule	20

# Scope

This document describes the development plan for the FIRST/SPIRE 300mK straps subsystem.

It is a preliminary version, which will be updated as the design matures.

# Documents

## Applicable documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| AD1 | 300mK Straps Subsystem Specification Document | To be written |  |  |
| AD2 |  |  |  |  |
| AD3 |  |  |  |  |

## Reference documents TBW

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| RD1 | Instrument Requirements Document | B.M.Swinyard | SPIRE-RAL-PRJ-000034 Issue 0.30 | May 2000 |
| RD2 | Instrument development plan | K.J.King |  |  |

## Glossary TBW

| AD Applicable Document | FS Flight Spare |
| --- | --- |
| ATC Astronomy Technology Centre | FTS Fourier Transform Spectrometer |
| BDA Bolometer Detector Array |  |
| CBB Cryogenic Black Body |  |
|  | LAS Laboratoire d’Astronomie Spatiale |
| CDR Critical Design Review | MGSE Mechanical Ground Support Equipment |
|  | MSSL Mullard Space Science Laboratory |
| CoG Centre of Gravity | NA Not Applicable |
| CQM Cryogenic Qualification Model | OGSE Optical Ground Support Equipment |
| DDR Detailed Design Review | PCAL Photometer CALibrator |
|  | PFM ProtoFlight Model |
| DM Development Model | RAL Rutherford Appleton Laboratory |
| DRCU Digital Read-out and Control Unit | RD Reference Document |
| EGSE Electrical Ground Support Equipment | SCAL Spectrometer CALibrator |
| FIRST Far InfraRed Space Telescope | WE Warm Electronics |
| FPU Focal Plane Unit |  |

# Subsystem Description

Updated sketches/drawings from JC/BW needed

The 300mK straps subsystem comprises all thermal straps between the 3He cooler head and the BDAs, all supports for these straps (which should provide a high degree of thermal isolation from the 2K structure), and all light baffles (used where the straps go from a 4K environment to a 2K environment).

A conceptual design for the light baffles is shown in figure (1). These are used to prevent 4K radiation from entering the 2K boxes, and also provide thermally isolated mechanical suspension for the straps.

Figure 1

The conceptual design for the photometer straps is shown in figures (2) and (3). The photometer straps are suspended from the 2K structure, and run along the walls of the 2K photometer box. The suspension of these straps must provide excellent thermal isolation from the 2K structure, whilst retaining high mechanical strength.

Figure 2

Updated drawing needed – Kevlar suspension

Figure 3

Updated drawing needed – Kevlar suspension

## Block diagram

Figure 4 Block diagram of 300mK strap sub-system. The straps are shown in dark blue, thermal interfaces to other subsystems are shown as blue circles, and PBAF & SBAF are the photometer & spectrometer light baffles.

# Organisation

This work package is largely shared between Cardiff and MSSL, with design input, in the form of thermal and optical modeling, from RAL.

Cardiff are responsible for:-

- Thermal testing

  - Thermal conductivity of prototype materials

  - Thermal interface study – to find optimal interface configuration.

  - Thermal testing of prototype 300mK system.

- Optical testing

  - Testing the performance of prototype stray light baffles.

- System design (thermal)

MSSL are responsible for:-

- System design (mechanical)

- Mechanical testing.

- Procurement & manufacture of the 300mK system for STM/CQM, PFM & FS.

RAL are responsible for:-

- Thermal modeling.

- Stray light analysis.

- Input from RAL will be used by Cardiff and MSSL in the preliminary design phase.

# Deliverables

The current SPIRE model philosophy dictates that flight representative thermal straps are delivered for integration to the structure for STM testing. This STM structure will then become the CQM structure. It is proposed that the CQM structure is then refurbished for the flight spare, once received back from ESA. This would imply that only two 300mK strap models are necessary – one for the STM/CQM and FS, and one flight model. However, we are concerned about the thermal cycling and vibrations that the STM/CQM model will have been subjected to. High vibrational levels may cause creep of the proposed Kevlar support, as well as work-hardening of the straps. We have assumed the provision of a separate FS model, which may be integrated to the FS structure as a replacement for the STM/CQM system.

The concept of a deliverable needs clarification in this case. It is yet to be decided whether the 300mK strap system will be integrated to the structure at MSSL, prior to delivery to RAL, or whether the straps and structure will be delivered to RAL as separate entities, and integrated there (Berend/Bruce – comments please – clean room facilities etc). If the straps are integrated at MSSL, then there is no deliverable from this work package to SPIRE (apart from documentation) – it becomes an internal milestone. Rather than deliverable dates, I have quoted “available for integration” dates in table (1).

Table 1 SPIRE deliverables for each instrument model

| Deliverables to RAL* |
| --- |
| Model | Description | Required date | Available for integration | Difference from flight model | Responsible Institute |
| STM | 300mK system | 1/1/02 TBC | 16/4/02 | None | MSSL |
| CQM | 300mK system | Not required |  |  |  |
| PFM | 300mK system | 11/7/03 | 27/8/03 | None | MSSL |
| FS | 300mK system | Not required | 22/10/03 | None | MSSL |
| *Note, these may become “internal” deliverables if the straps are integrated to the structure at MSSL prior to delivery of the structure to RAL. |

Table 2 contains a list of “internal” deliverables. These are defined as deliverables between Cardiff and MSSL during the development, test and manufacture phases. These are not deliverable to SPIRE.

Table 2 Internal deliverables

| Internal Deliverables |
| --- |
| Model | Description | Required | Deliver to | Responsible |
| LBP1 | Prototype 1 light baffles (2 off) | 11/4/01 | Cardiff | MSSL |
| LBP2 | Prototype 2 light baffles (2 off) | 5/7/01 | Cardiff | MSSL |

# Constraints

## Technical constraints

The performance requirements for the 300mK straps are listed below, and are extracted from RD1.

### 300mK strap performance requirements

| Requirement ID | Description | Value |
| --- | --- | --- |
| IRD-COOL-R01 | Temperature at the detectors | The 3He cooler , in conjunction with the associated 300mK architecture, shall maintain all BDAs at less than 310mK (goal – 300mK) |
| IRD-COOL-R02 | Operating temperature control | Desirable to be able to vary the temperature of the detectors up to 320mK and below 300mK if this is permitted by the temperature drop across the thermal link. |
| IRD-COOL-R03 | Temperature drop across thermal link between detectors and evaporator cold tip | Maximum of 20mK |

## System constraints

The system requirements for the 300mK straps are listed below, and are extracted from RD1.

Additional overall system constraints are:-

- SPIRE orbital lifetime – 4.25 years

- Volume envelope/strap routing = TBD

- Mass = 900g for the photometer straps – this needs clarification – there is nothing in the mass budget for spectrometer straps – Colin has been informed

- Vibration level =

- Shock level =

- Cleanliness =

- Transit loads =

- Storage =

- Bake-out temperature on AIV integration = 80(C for 48 hours

### 300mK straps system requirements

There are no stated system requirements on the 300mK strap sub-system.

## Calendar constraints

The major SPIRE project dates are (RD2):-

| PDR | 26/27 Jun 2000 |
| --- | --- |
| DDR – Interface Review | 28/29 Nov 2000 |
| QMW Programme Review | 16 Jan 2001 |
| STM 300mK straps delivery to RAL | 17 Jan 2002 TBC |
| CDR | 3 Feb 2003 |
| SPIRE CQM delivery to ESA | Apr 2003 |
| PFM 300mK straps delivery to RAL | 17 Jun 2003 |
| SPIRE PFM delivery to ESA | 1 Jul 2004 |
| FS 300mK straps delivery to RAL | 10 Sept 2003 |
| SPIRE FS delivery to ESA | 1 Jul 2005 |
| FIRST launch | 2007 |

# Work Description

## Model philosophy

The model philosophy is compliant with the revised SPIRE project model philosophy.

The following models will be produced:-

- Light baffle prototypes. Two generations of light baffles will be produced:-

  - LBP1 - The first generation will be designed with input from RAL (stray light analysis and thermal modeling) and built under MSSL responsibility. Three identical models of LBP1 will be built – two will be sent to Cardiff for optical and thermal tests, while one will stay at MSSL for mechanical tests.

  - LBP2 – after completion of tests on the LBP1 models, a two week period of re-design follows before the manufacture of three models of LBP2 starts. The LBP2 models will also be tested in parallel, as for LBP1.

- Strap and suspension prototypes. Two strap and suspension prototypes will be built:-

  - CSTM – this is the Cold Strap Thermal Model. This will be built under Cardiff responsibility, and designed with input from RAL (thermal modeling). This model will be thermally representative of the 300mK strap system, replicating the thermal characteristics of all thermal paths in the final system. It will not be structurally representative, as it has to be tested in a cryostat with limited internal volume.

  - CSSM – this is the Cold Strap Structural Model. This will be designed and built under MSSL responsibility. CSSM will be structurally representative of the 300mK system, with, for instance, dummy masses to represent the light baffles.

- 300mK strap STM/CQM – Because of the high degree of risk associated with this development programme, in that the first overall system test will take place once the system is installed in the STM, two STM/CQM systems will be built. One will be left unassembled in component form as a back-up in the event of STM strap system failure. The STM models will be designed with information from the prototype testing, and a design review will be held on 23/1/02 (TBC). Manufacture of components will commence after this review and should be complete by 20/3/02. Manufacture and acquisition of these components is the responsibility of MSSL. Following assembly of the components, the 300mK system STM will be ready for integration to the structure by 18/4/02. The 300mK STM system will remain in the STM/CQM structure throughout the STM and CQM test campaigns.

- 300mK strap PFM – Manufacture of the PFM straps will commence after the CDR, under the responsibility of MSSL. These will be ready for integration in August 2003.

- 300mK strap FS – The present SPIRE model philosophy proposes refurbishing the CQM FPU for the FS. However, the 300mK straps in this system will have been subjected to all of the STM and CQM tests (thermal cycles, cold vibrations etc), and we are concerned that this will adversely affect the performance of the 300mK straps (work-hardening, Kevlar creep etc). Therefore, we will provide a replacement 300mK sub-system for CQM ( FS refurbishment. This will be delivered to RAL in October 2003.

## Preliminary design phase

The PDR freezes the technical specifications/requirements, while the interfaces are frozen at the interface review.

### Materials testing

A dedicated 3He cryostat has been assembled for thermal conductivity tests on candidate materials for the straps and supports. These tests will take place between January and March 2001, and include:-

- Thermal conductivity of Copper – nominally high purity (99.999%) Copper from Goodfellows – as a function of material treatment (level of annealing, Gold plating etc)

- Thermal conductivity of Kevlar, Vespel & Torlon – the materials to be tested will be from the proposed suppliers for the flight model (eg Goodfellows, DuPont). The Vespel and Torlon data will also be used for the SCAL development programme.

### Interface study

The thermal test dewar will also be used to study the thermal impedance of different interface configurations, with the goal of finding the optimal configuration for thermal conductivity across interfaces. This is necessary to meet the 20mK thermal drop requirement (IRD-COOL-R03) between the detectors and the evaporator cold tip.

### Modeling

A MathCad model has been produced for simple thermal/mechanical analysis of design concepts. The thermal analysis is compared to results from ThermXL (Alstom technology). This is used as the first step in the design process.

Detailed thermal analysis of candidate designs will then be carried out by RAL using ESATAN. Detailed mechanical FE analysis will be carried out at MSSL using the IDEAS Master Series CAD package.

### Prototyping

Prototype light baffles and strap/suspension systems will be built, as detailed in section 7.1, in order to verify the design.

### Testing

The prototype light baffles and straps will undergo the following tests (as a minimum):-

- Thermal tests (CSTM, LBP1(A&B), LBP2(A&B))

  - Thermal drop between evaporator cold tip and detector interface points (CSTM only)

  - Parasitic heat load from 2K to 300mK. The test dewar will, as a default, run with a 2K pumped Helium bath. This is because the whole 300mK system will only be suspended from 2K structure in SPIRE. This test will tell us about the efficacy of the thermal isolation of the strap supports, including the light baffles, which incorporate internal supports for the straps.

- Mechanical tests (CSSM, LBP1(C), LBP2(C))

  - Resonant frequency (warm)

  - Cold vibration (at RAL) - TBC

## Procurement of long lead-time components

Once a preliminary design has evolved, long lead-time items will be procured.

Note – need to clarify CPP procedure & items

## Detailed design phase

The detailed design of the STM/CQM straps will proceed in parallel with the prototype test campaign, with test results being used to modify the design.

The detailed design should therefore be available shortly after prototype component tests are complete.

A design review will be held in January 2002, which will freeze the STM/CQM design.

## STM/CQM manufacture & test

The detailed design is presented at the Detailed Design Review. The DDR and 300mK strap design review must have happened before STM/CQM manufacture can begin.

STM/CQM manufacture takes place between January 2002 and March 2002.

There is no way of testing the performance of the whole, assembled STM/CQM 300mK system prior to integration to the structure. The first test of the performance of the whole system will therefore coincide with the STM tests. This obviously introduces an element of risk to the program. This will be minimized by rigorous testing of the prototype components (materials, interfaces, CSTM, CSSM, LBP1, LBP2).

The design verification tests (once incorporated in the STM structure) include:-

- Verification of the basic mechanical parameters (Mass, stiffness, resonance frequencies).

- Performance verification – thermal drop, parasitic heat load.

- Warm and cold vibrations.

After the 300mK strap STM/CQM delivery, the SPIRE STM is tested at project level. The STM structure and straps will then serve as the CQM structure and straps – i.e. they will be the same components used for STM testing.

The results of the qualification tests are to be presented at the SPIRE CDR, which is the start point of the PFM and FS manufacture.

Then, the SPIRE CQM is delivered to ESA for cryogenic tests of the FIRST FPU.

## PFM & FS manufacture & test

Following the SPIRE CQM tests, some modifications may have to be implemented in the design.

The design changes are to be implemented in the flight design and be validated using the prototype components (CSSM, CSTM, LBP1, LBP2).

The 300mK strap PFM is then manufactured and undergoes acceptance tests.

The FS model is a duplicate of the PFM and is assembled after the PFM, although the components will be manufactured simultaneously. The FS model undergoes the acceptance tests after the PFM delivery.

# Work flow

A cross-functional work flow diagram is shown in figures 5, 6 & 7. Figure 5 is the top level work flow, while figures 6 and 7 show more detail with regard to the strap and baffle prototyping phases.

Figure 5 Top level workflow diagram

Figure 6 Detail of the light baffle prototyping phase

Figure 7 Detail of the strap and suspension prototyping phase

# Risk analysis

| Risk | Impact | Preventative Action | Notes |
| --- | --- | --- | --- |
| Damage during component assembly. | Development plan must be updated. Delivery dates may be delayed (margin has been built into schedule). | Clearly written & detailed integration plan. | Most likely damage would be bending (hence work-hardening) of straps, or damage to Kevlar suspension. |
| Failure during STM/CQM testing. | Major SPIRE schedule impact. Spare strap system will need to be assembled after failed system has been removed and analysed for failure mode. | Extensive testing of prototype components. Impact of failure will be minimized by the provision of spare components. | MSSL are working to make integration of the 300mK strap system as simple as possible. |
| Failure of test cryostat | TBD | Spare cryostat available at Cardiff | This cryostat is a general lab. He-3 system – it could be used for strap testing in an emergency, with little modification. |
| Unavailability of main test team member | Moderate. | Other group members at Cardiff are/will be involved in the project. | One person is identified as responsible for the test plan at Cardiff, but other group members will be involved to such a level that they can replace the missing person. |
| Qualification failure | Development plan must be updated. Delivery dates may be delayed. | None. |  |
| Limited staff resources | Development plan must be updated. Delivery dates may be delayed. | Recruitment of new staff. | Resource analysis has been completed. Two new PDRA positions have been created, of which 1.5 post-docs will be working on SPIRE. |

# Verification plan –To Be Updated

The verification plan must be compliant with the project verification plan [Refs – AD??, RD??].

300K vibrations are conducted at Cardiff - TBD

Cryovibrations are conducted at RAL under MSSL responsibility (TBC).

Vacuum cycles, soak cycles, thermal cycles are conducted at Cardiff.

Lifetime tests are conducted at Cardiff.

Performance tests are conducted at Cardiff.

In the table below,

| X = | a real test is conducted |
| --- | --- |
| A = | an analysis is conducted |
| NA = | Non applicable |

|  | DM | STM/CQM | PFM | FS |
| --- | --- | --- | --- | --- |
| Mass measurement | X | X | X | X |
| CoG measurement | X | X | X | X |
| Thermal drop measurement | X | A | A | A |
| Vibrations 300K | X | X |  |  |
| Vibrations 4K | X | X | X | X |
| Thermal/Vacuum cycle | X | X | X | X |
| Accelerated lifetime (12,000 operations) | N/A | N/A | N/A | N/A |
| Radiation tolerance** | N/A | N/A | N/A | N/A |
| Microphonics | N/A | N/A | N/A | N/A |
| EMI / EMC | N/A | N/A | N/A | N/A |

# Development calendar & schedule

The major project milestones pertinent to the 300mK straps sub-system are:-

STM/CQM straps to RAL	01/01/02

PFM straps to RAL		11/07/03

FS straps to RAL		not defined

Internal milestones and delivery dates are:-

| ID | Milestone | Date | Status | Comment |
| --- | --- | --- | --- | --- |
| 306 | GRTs from Lakeshore | 25/1/01 | Complete |  |
| 304 | He-3 fridge shield ready | 12/02/01 | On schedule |  |
| 313 | Test dewar ready | 27/2/01 | On schedule |  |
| 326 | Design Review – LBDR1 | 28/2/02 | On schedule | Light baffle DR1 |
| 328 | LBP1 to Cardiff | 12/4/01 | On schedule | Light baffle prototype 1 (2 off) |
| 322 | Interface study complete | 9/5/01 | On schedule |  |
| 334 | Design Review – LBDR2 | 29/5/01 | On schedule |  |
| 336 | LBP2 to Cardiff | 11/7/01 | On schedule |  |
| 340 | Design report | 2/8/01 | On schedule | Light baffle design report |
| 342 | Light baffle design complete | 23/8/01 | On schedule |  |
| 347 | Design review – CSDR1 | 24/8/01 | On schedule | Cold strap design review 1 |
| 353 | Cold strap prototypes – test report | 10/12/01 | On schedule | Report on CSSM and CSTM tests |
| 357 | STM design review – CSDR2 | 28/1/02 | On schedule |  |
| 362 | STM/CQM straps ready for integration | 23/4/02 | On schedule |  |
| 370 | PFM straps ready for integration | 3/9/03 | On schedule |  |
| 374 | FS straps ready for integration | 03/09/03 | On schedule |  |

Figure 8 300mK strap sub-system milestones.

# 300mK straps sub-system schedule

Figure 9 300mK strap schedule.

# Text boxes

Draft

For approval