## Introduction
SPIRE alignment sequence
LAM.PJT.SPI.???.200100x Ind. 01/SPIRE-LAM-PRJ-000637 Date: 11 April 2001
SCOPE The document gives a detailed, step by step description of the sequence for verification of the SPIRE optical alignment. This document is accompanied by the alignment plan description document [RD1] and an alignment tools specification document [RD2].
Reference documents RD1 SPIRE optical alignment verification plan K. Dohlen, A. Origné 11/04/2001 LAM. PJT. SPI. ….. RD2 SPIRE alignment tools specification K. Dohlen, A. Origné 26/10/2000 LAM. PJT. SPI. …..

## History
Issue | Filename | Date | Comments
1 | Alignment Sequence01 | 110401 | Creation of document

## Sequence
Procedure |  |  | Task | Comments
Photometer 2K box alignment mode integration | 1 | 1 | Mount 2K box in TBD alignment jig.
| 1 | 2 | 3D metrology | Voir 3.3; Reference TBD
| 1 | 3 | Mount PCS-tool at the 2K box entrance hole
| 1 | 4 | Adjust MAT for autocollimation on reflective part of tool and move to central hole of tool | Defines gut ray perpendicular to CS
| 1 | 5 | Mount Apex tool in PM9 position, verify gut ray centering | Verifies position of PM9
| 1 | 6 | Move Apex tool to PM11 position, mount PM9, verify gut ray centering
| 1 | 7 | Mount PM11 and PD-tool in PLW position, verify position of central source on the tool.
SOR alignment | 2 | 1 | Assemble the instrument box | Apart from mirror stands, the box contains the spectrometer cold stop (SCS). The SOR is fixed to an externally accessible part of the SOB and remains in place when panels are removed.
| 2 | 2 | Mount box on FOB simulator | FOB simulator consists of interface holes for mounting of the SPIRE box and a reference cube (FOR) materializing the telescope optical axis.
| 2 | 3 | Adjust/calibrate SOR wrt FOR | The Micro alignment telescope (MAT) mounted on a precise translation/rotation stage compares position and orientation of the references.
Pre-integration verification | 3 | 1 | Move box to integration jig | I suppose the integration jig has appropriate interface with the SOB allowing removal of some (or indeed all but this leaves the SOB floppy) panels. It should also allow either side of the instrument.
| 3 | 2 | Remove Photometer panels
| 3 | 3 | Visual inspection of interfaces | Detect particles or surface defects
| 3 | 4 | 3D metrology | Verification of the coordinates and the orientation of the interface planes with respect to the optical design. Any error detected will be analyze to find its cause and corrected if necessary. A specific, "3 D tool" will be used in place of the mirrors in order to ease the 3-D measurement and to avoid damage of the mirror surface.
| 3 | 5 | Replace photometer panels
| 3 | 6 | Remove Spectrometer panels
| 3 | 7 | Visual inspection of interfaces | Detect particles or surface defects
| 3 | 8 | 3D metrology | Verification of the coordinates and the orientation of the interface planes with respect to the optical design. Any error detected will be analyze to find its cause and corrected if necessary. A specific, "3 D tool" will be used in place of the mirrors in order to ease the 3-D measurement and to avoid damage of the mirror surface.
| 3 | 9 | Replace spectrometer panels
Integration of common and photometer optics | 4 | 1 | Align MAT with SOR
| 4 | 2 | Remove photometer panels
| 4 | 3 | Verify MAT and SOR alignment
| 4 | 4 | Move MAT to materialize the photometer gut ray
| 4 | 5 | Place Apex tool in CM3 position and verify centred on gut ray
| 4 | 6 | Move Apex tool to CM5 position, mount CM3 and BSM replacement tool, verify gut ray centering.
| 4 | 7 | Move Apex tool to PM6 position, mount CM5, verify gut ray centering. | If SM6 has separate stands then its alignment verif can be done separately. This is assumed. If not then alignment of SCS must be performed here by loving the MAT to the spectrometer gut ray direction.
| 4 | 8 | Move Apex tool to PM7 position, mount PM6, verify gut ray centering.
| 4 | 9 | Move Apex tool to PM8 position, mount PM7, verify gut ray centering.
| 4 | 10 | Remove Apex tool, mount PM8 and pre-assembled 2K box. | See Procedure 1
| 4 | 11 | Verify centering of CS tool and D-tool on gut ray.
| 4 | 12 | Replace photometer panels
| 4 | 13 | Verify MAT and SOR alignment
Integration of spectrometer optics | 5 | 1 | Turn box around
| 5 | 2 | Align MAT with SOR
| 5 | 3 | Remove spectrometer panels
| 5 | 4 | Verify MAT and SOR alignment
| 5 | 5 | Move MAT to materialize the spectrometer gut ray
| 5 | 6 | Place Apex tool in SM6 position and verify centred on gut ray
| 5 | 7 | Move Apex tool to SM7 position, mount SM6, verify gut ray centering in SCS and on Apex tool.
| 5 | 8 | Move Apex tool to SM8 position, mount SM7, verify gut ray centering.
| 5 | 9 | Move Apex tool to SM9B position, mount SM8 and SBS1 pellicle replacement, verify gut ray centering (transmission through SBS1).
| 5 | 10 | Move Apex tool to SM9A position, verify gut ray centering (reflection at SBS1).
| 5 | 11 | Mount SM9 A and B, verify autocollimation | Focalise MAT on central reticule of tool in SPIRE object plane (SO-tool). Twin images returned by autocollimation should coincide with reticule.
| 5 | 12 | Place Apex tool in SM10A position, mount corner cube assembly (CCA) replacing FTS mechanism, verify gut ray centering. | Deviation indicates lateral displacement of CC apex
| 5 | 13 | Move Apex tool to SM11A, mount SM10A, SM10B and SBS2 pellicle replacement, verify gut ray centering | Identify image transmitted through SBS2 to verify alignment of SM10B
| 5 | 14 | Move Apex tool to SM11B, verify gut ray centering | Identify image transmitted through SBS2 to verify alignment of SM10A. Identify image reflected at SBS2 to verify alignment of SBS2.
| 5 | 15 | Move Apex tool to SM12A, mount SM11A, verify gut ray centering
| 5 | 16 | Move Apex tool to SM12B, mount SM11B, verify gut ray centering
| 5 | 17 | Mount SM12A and SM12B, verify gut ray centering on detector tools (SD tools).
Pupil quality verification | 6 | 1 | Locate M2-tool with respect to the SPIRE box | Light up central source in D-tool, observe the image of the central hole of the CS-tool projected onto the central reticule of the M2-tool. Adjust the position of the M2-tool to make these coincide.
| 6 | 2 | Verify cold stop position for different field points | Observe the projected edge of the CS-tool through one of the edge reticules in the M2-tool. Light up sequentially each of the sources in the D-tool, measure position of the edge for each field point. Repeat for each of the edge reticules in the M2-tool.
Image quality verification | 7 | 1 | Observe image of D-tool sources in SPIRE object plane. | Simple star test sufficient to verify image quality. Hartmann test can be implemented if star test introduces an uncertainty. This requires replacement of CS-tool with Hartmann tool (screen with regularly spaced holes). This test will determine shape of wavefront and allow analysis of error source.
Image position stability test | 8 | 1 | Mount PSD tool in the SPIRE object plane (entrance of the box) | Stand-alone test of internal alignment required for verification of internal alignment during environmental testing. Detects relative movements between SPIRE object and image planes.
| 8 | 2 | Light central source of D-tool
| 8 | 3 | Register position of the projected image on the PSD tool
Photometer 2K box detector integration | 9 | 1 | Remove Phot-side covers, remove 2K box (alignment mode) from SOB
| 9 | 2 | Adjust MAT in direction of the 2K box gut ray using CS tool and D-tool
| 9 | 3 | Mount pellicle replacing PDIC1, Apex tool in PM10 position, verify gut ray alignment
| 9 | 4 | Mount PM10 and move PD-tool to PSW position, verify position of central source on the tool.
| 9 | 5 | Mount pellicle replacing PDIC2, and move PD-tool to PMW position, verify position of central source on the tool.
| 9 | 6 | Remove PD-tool and integrate detectors. Verify absolute and relative positions of TBD fiducial marks wrt gut ray.
| 9 | 7 | Close the box and reverify fiducial mark positions
| 9 | 8 | Remove pellicles and mount dichroics
| 9 | 9 | Remove PCS tool, mount PCS and filter, PCS visible from outside | Phot detectors are now invisible
| 9 | 10 | Integrate 2K box into instrument,
| 9 | 11 | Adjust MAT wrt SOR, verify position of CS edges wrt gut ray.
| 9 | 12 | Replace phot-side covers, reverify CS edges
Spectrometer detector integration | 10 | 1 | Remove spec side covers, adjust MAT along spec gut ray using SOR, verify alignment wrt SCS tool and SD tools.
| 10 | 2 | Remove SD tools, mount detectors, verify position of TBD fiducial marks
| 10 | 3 | Remove pellicles, mount BS and filters | Spec detectors are now invisible
| 10 | 4 | Remove SCS tool, mount SCS, verify position of edges wrt gut ray
| 10 | 5 | Replace spec-side covers, reverify SCS edges
Final integration | 11 | 1 | Remove phot-side covers
| 11 | 2 | Remove remaining tools
| 11 | 3 | Mount FIR equipment | SPIRE is now closed for visible radiation
| 11 | 4 | Replace phot-side covers