Work Package:	BSM                                                                     SPIRE-ATC-REP-000721

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. Progress to DDR and IBDR underway. |
| 2. Subsystem Progress This Month |
| Manufacture of test dewar parts has started. The specification for a 20K closed cycle test dewar has concluded and RFQ's will be issued. The jiggle frame manufacture for the 2 axis prototype is complete and all other components are into the workshop. Work on drift in the CDL laser measurement device has been performed. The drift remains just outside the BSM specification - though indications are that the BSM sensor stability is adequate it cannot be proved conclusively at this stage. Options are being considered. A quotation on flex pivots has been received, and has proved significantly outside budget. MPIA/Zeiss have confirmed availability of space qualified cryo-motors, albeit at a high price. Cross-talk tests indicate no influence of stray motor fields on sensor readings. Collaboration meetings with LAM have been set up for mid-June. |
| 3. Problem Areas | Remedial Action |
| Flex pivot prices over budget | Alternatives manufacturing strategies and suppliers being sought |
| 4. Engineering Activities |
| FEA analysis of the structure for stress/deflection and resonant modes has completed though software problems have prevented extension of this analysis to give a PSD. Detailing of all items is now largely complete, bar a few tweaks. However this has delayed the ICD drawings first issue. |
| 5. Design Changes |
| Details of LAM's candidate launch latch have been obtained and a proposed change to the PCAL interface circulated. |
| 6. PA/QA Activities |
| A product assurance plan for the BSM has been released at ATC for comment. Feedback is now due, and the PA plan will then be released externally. A programme risk assessment for the BSM project is underway, with useful strategies already emerging. |
| 7. Subsystem Management Issues |
| Flex pivot cost over-run (94k compared to 13k allocated) is a potential show-stopper and options are being explored urgently. A slip to the DDR date to 24-31 July has been achieved. An internal-to-ATC DDR is scheduled for 3rd July. Solid progress is being made to DDR, but pressure must be kept on, especially for key resources. |
| 8. Actions Requiring Immediate Attention |
| ATC-83 Provide Tony Richards with BSMs/BSMm geometry (IGES file) ATC-various (10,11,14,15,17,25,29,144 ) close up various issues with LAM on BSMe ATC-159 Issue PCAL ICD input to P.Hargraves. ATC-160 Issue structure ICD to MMSL. |
| 9. Status of Previous Actions |
| RAL-010509-05 IP to confirm the date of the BSM DDR. Complete pending consortium choice (24-31 July). RAL-010514-01 Ian/Dominique to set up a SMEC/BSM electrical interface meeting - complete (scheduled 21 June) RAL-010509-17 (ATC-60) Ian to confirm the use by ATC of the RAL cold vibration facility - open |
| 10. Activities Yet to be Achieved |
| ICD release. PA plan release. Conclusive long term sensor stability demonstration |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| Report on sensor stability to LAM | 07 Jul 00 | 21 Jun 01 |  | +1 month |
| Prototype Detail design release | 24 Jan 01 | 30 May 01 | 30May01 |  |
| Update ICD structure | 24 Oct 00 | 13 Jun 01 |  | +1 month |
| 20K test dewar available | N/A | 27 Aug 01 |  |  |
| Deliver draft Analog Brd Design Doc to LAM | 14 Aug 00 | 25 Dec 00 | Jan.01 |  |
| Select motors | 30 Jan 01 | 22 Feb 01 | 22 Feb 01 |  |
| Deliver ICD WE to LAM | 11 Aug 00 | 12 May 01 |  | superceded |
| Receive ICD info for WE from LAM | N/A | 21 Jun 01 |  |  |
| Analog Brd Detailed design to LAM | 26 Sep 00 | 23 Mar 01 | 23.Mar.01 |  |
| Deliver refined Simulink Model to LAM | 14 Aug 00 | May 01 |  | +1 month |
| Deliver d-space controller to LAM | 31 Jan 01 | May 01 |  | +1 month |
| SMEC/BSM programme review. | 31 Jan 01 | 31 Jan 01 | 27 Jan 01 |  |
| SPIRE Intermediate Instrument Design Review (IIDR) | TBD | 23-24Apr.01 | 23-24Apr.01 |  |
| Deliver Prototype (in place of DM 2) to LAM | 30 Mar 01 | Tbd |  | Pending |
| Internal ATC review | new | 3 Jul 01 |  | new |
| Detailed Design Review | 30 Jan 01 | 24 Jul 01 |  | + 3 weeks |
| DM tests complete | N/A | 22 Mar 02 |  |  |
| BSM STM del'y to RAL | 01 Feb 00 | 01 Jul 02 |  |  |
| BSM CQM del'y to RAL | 13 Mar 02 | Under review |  |  |