Notes on project managers teleconference                       SPIRE-RAL-MOM-000758          18th July 2001

Chair:		Eric Sawyer

Present:

| Name | Yes | No |
| --- | --- | --- |
| Joe Taylor |  |  |
| Ian Pain |  |  |
| Don Peterson | X |  |
| Jerry Lilienthal | X |  |
| Berend Winter |  |  |
| Dominique Pouliquen |  |  |
| Gary Parks |  |  |
| Jean-Louis Auguerres |  |  |
| Matt Griffin | X |  |
| Doug Griffin |  |  |
| Dave Smith |  |  |
| Eric Clark | X |  |
| Ken King |  |  |
| Bruce Swinyard | X |  |
| John Delderfield |  |  |
| Peter Hargrave | X |  |
| Didier Ferrrand | X |  |

It was agreed by all present that we should return to Mondays for these meetings, starting on 30/8/01.  Judy will send out a reminder before each meeting.

Subsystem reports

RAL

Mass budget, this is getting urgent, can subsystem groups please send in updates as a matter of urgency.

DDRs,  a system to track RIDs is being set up at RAL.

USK

DDR complete yesterday, no technical show stoppers, action on Doug to review impact of cryostat thermal design.

Power consumption to be refined.

Latch status monitoring raised.

Black coating discussed, Cardiff black to be investigated.

ATC

Documents being prepared for DDR, date confirmed as 30/7/01.

Financial issues associated with the flex pivots to be discussed.

JPL

DDR is being prepared.

Technote is being prepared on vibration testing.

Business agreement, comments sent from Matt, it is now being signed off at JPL, and will be signed off ASAP in the UK.

Cryo harness spec is being worked on.

Tech note on vibration levels received from MSSL.

MSSL

No report

LAM

Vibration levels, a compromise on pivot size has been established, but as a safety measure provision for a second latch has been requested.

Change requests received for, second latch and mode of latch operation.

Micro vibration, SMEC mechanism has a control loop, but this does not filter micro vibrations.

Patrick will attend BSM DDR.

Didier would like to attend the software DDR, 31/7/01 to 1/8/01.

Proposal for interface control is:

Internal interfaces controlled by LAM.

RAL are responsible for MCU to FPU harness.

ATC are responsible for defining the FPU interface.

Sap

No Report

Cardiff

More engineering effort available from 1 August.

Testing continuing.

PCAL procurement agreed.

DDR dates, 21 August proposed,  may be delayed a short time.

FMECA started, plus PA database.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010402-05 | Provide information on the parts approval and quality status for the Canadian components. | Don | 31/7/01 | USK plan to use NASA approved parts wherever possible. A preliminary parts list will be available at the DDR. | Open |
| 010509-10 | Specify date of the FTS DDR | Dominique |  | Likely end Sept TBC | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010509-16 | Confirm the use by Cardiff of the RAL cold vibration facility | Peter | 25/6/01 | One test April/May 2002 | Closed |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| 010611- 02 | Send e-mail with info on the number of cold vibration campaigns foreseen and approximate dates | Ian | 29/6/01 | No funds available with current costing, RAL and ATC to discuss offline | Closed |
| 010611-03 | Devise and implement a Livelink report to display document information for a given folder | Ken | 29/6/01 |  | Open |
| 010611-05 | Notify SAP of the grounding scheme to be used for the DRCU | John | ASAP | Status not known | Open |
| AI-MAN-0753-01 | Specify DDR date | Ian | 20/7/01 | 30 July | Closed |
| AI-MAN-0753-02 | Optimise DDR dates to minimise clashes | Eric S | 20/7/01 |  | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 |  | Open |
| AI-MAN-0753-04 | Check shutter indictor requirements with Alcatel | Doug | 15/7/01 |  | Closed |
| AI-MAN-0753-05 | Confirm mass figures | Dominique | 20/7/01 |  | Closed |
| AI-MAN-0753-06 | Provide more detailed mass breakdown | JPL | 20/7/01 |  | Open |