Notes on project managers teleconference                       SPIRE-RAL-MOM-000820        13/8/2001

Chair:		Eric Sawyer

Present:

| Name | Yes |
| --- | --- |
| Lionel Duband |  |
| Ben Parvin |  |
| Berend Winter |  |
| Matt Griffin |  |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor |  |
| Ian Pain |  |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King | X |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark | X |
| John Delderfield |  |
| Didier Ferrrand |  |

Subsystem reports

USK.

Interface drawing sent to MSSL.

Design is  for stepper not a motor to work against a spring force, some more design work required.

Position indicator, no further progress.

Power consumption is an issue.

Cardiff.

Preparations for DDR continuing, proposed date 18 September.

Tests on SCAL continuing following design changes.

Two extra thermometry channels required.

No changes to harness.

300mK strap test item is also under test.

JPL.

Documentation is being completed prior to the CDR.

Drawings being readied for manufacture.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010402-05 | Provide information on the parts approval and quality status for the Canadian components. | Don | 31/7/01 | USK plan to use NASA approved parts wherever possible. A preliminary parts list will be available at the DDR. | Open |
| 010509-10 | Specify date of the FTS DDR | Dominique |  | Likely end Sept TBC | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| 010611-03 | Devise and implement a Livelink report to display document information for a given folder | Ken | 29/6/01 |  | Open |
| 010611-05 | Notify SAP of the grounding scheme to be used for the DRCU | John | ASAP | Status not known | Open |
| AI-MAN-0753-01 | Specify DDR date | Ian | 20/7/01 | 30 July | Closed |
| AI-MAN-0753-02 | Optimise DDR dates to minimise clashes | Eric S | 20/7/01 |  | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 |  | Open |
| AI-MAN-0753-06 | Provide more detailed mass breakdown | JPL | 20/7/01 |  | Closed |
| AI-MAN-0796-01 | Respond cleanliness questions,. | RAL | 17/8/01 |  | open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |