Notes on project managers teleconference                       SPIRE-RAL-MOM-000823    20/8/2001

Chair:		Eric Sawyer

Present:

| Name | Yes |
| --- | --- |
| Lionel Duband | x |
| Ben Parvin |  |
| Berend Winter |  |
| Matt Griffin |  |
| Peter Hargrave |  |
| Jerry Lilienthal |  |
| Joe Taylor | x |
| Ian Pain | x |
| Don Peterson | x |
| Bruce Swinyard |  |
| Ken King |  |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark | x |
| John Delderfield |  |
| Didier Ferrrand |  |

Subsystem reports

Grenoble

Parts in manufacture, Testing on thermal straps ongoing. Temp stability tests ongoing.

Still awaiting input on cleanliness.

USK.

Outstanding actions to be cleared next week.

PDR issues are being addressed.

Harness doc still has info that pre dates PDR, comments will be passed to John.

IID-B changes are being addressed.

Instrument spec changes are being addressed.

Cardiff.

Not present, but sent a report

DDR date now fixed for 18th September. Invites & agenda to go out by

tomorrow.

Thermal tests on SCAL prototype (new design) have validated the thermal

model & exceed instrument requirements (goals achieved - spectrum matched to

within 5% from 200-400um). The spectrum matching estimate comes from another

(radiative) model which estimates the emitter temperatures required, and

these temperatures have been exceeded within the power budget.

New PCAL source in lab (HB6) - Install in dewar this week.

300mK strap tests will proceed this week - these are conducted in the same

dewar as the SCAL tests, and will run in parallel with further SCAL tests.

JPL optics are ready for shipping - need to talk to Hien/Jamie to talk over

a few details - filters are in manufacture.

ATC

Wrap up session 23/8/01.

Prototype is assembled and cool down test completed.

JPL

No specific report.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010402-05 | Provide information on the parts approval and quality status for the Canadian components. | Don | 31/7/01 | USK plan to use NASA approved parts wherever possible. A preliminary parts list will be available at the DDR. | Open |
| 010509-10 | Specify date of the FTS DDR | Dominique |  | Likely end Sept TBC | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| 010611-03 | Devise and implement a Livelink report to display document information for a given folder | Ken | 29/6/01 |  | Open |
| 010611-05 | Notify SAP of the grounding scheme to be used for the DRCU | John | ASAP | Status not known | Open |
| AI-MAN-0753-01 | Specify DDR date | Ian | 20/7/01 | 30 July | Closed |
| AI-MAN-0753-02 | Optimise DDR dates to minimise clashes | Eric S | 20/7/01 |  | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 |  | Open |
| AI-MAN-0753-06 | Provide more detailed mass breakdown | JPL | 20/7/01 |  | Closed |
| AI-MAN-0796-01 | Respond cleanliness questions,. | RAL | 17/8/01 |  | open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0823-01 | JD to inform USK of cryo harness to the shutter details. | John Delderfield |  | JD to contact Don | open |