# Minutes of SPIRE Project Team Meeting 15

# SPIRE-RAL-MOM-000824

# RAL 20 August 2001

# Present:     Matt Griffin,  Eric Sawyer, Bruce Swinyard, John Delderfield,  Eric Clarke.

New IID-B and IID-A received from ESTEC on CDROM.  Will be put on live link.

Topics.

Contact with Saclay (Christophe) has not been possible for the last two weeks, no visit has been arranged.

JPL review situation.

DDR dates.

Cold vibration testing, at SS level.

CDR at ATC.

System level AIT.

Schedule questions from ESA

Warm electronics status

Harness construction

# Review of outstanding actions from previous meetings

| No. PT-04-0570 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| AI-MAN-0570-01 | KJK | Write WE integration and test plan | High | Oct. 2001 | Still Open. Needed for IBDR. |

| No. PT-10-0682 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| AI-MAN-0682-04 | MJG | Arrange for QMW to evaluate filter suppression. | Medium | May 31 | Open, not yet documented in the SSRD |

| No. PT-12-0726 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| AI-MAN-0726-02 | EC KJK | Update the document management plan to reflect the new scheme for interaction of institute PMs with the documentation configuration control system. |  | June 29 | Still open, action being taken This is an action on Ken |
| AI-MAN-0726-03 | EC | Write a document describing the configuration control system for internal RAL use. |  | June 29 | Closed |

| No. PT-13-0772 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| AI-MAN-0772-03 | KJK | Send ESA a progress report for JUNE |  | 27/7/01 | ECS to do one this week for July |
| AI-MAN-0772-04 | BMS DKG | Bruce and Doug to talk to John and distribute a draft list of documents showing approval status. |  | 3/8/01 | In progress |
| AI-MAN-0772-05 | BMS | Bruce to propose a logical scheme for the documents on live link. |  | 3/8/01 | Closed |
| AI-MAN-0772-06 | MJG | Matt to meet with Ken to discuss the outstanding MOUs |  | 3/8/01 | Open, Matt to have at least a contents list ready for Ken’s return. |
| AI-MAN-0772-07 | DKG JD | Check scope for increasing the thermal load on the detector box JD to look at the fraction of the 2-K load that is due to the 2-K box |  | 27/7/01 | Open, there appears to be little scope to increase thermal load. But MSSL are planning to optimise the dynamic performance without the thermal performance suffering. The load on the 2K strap is not cast in concrete |
| AI-MAN-0772-08 | BMS | Check orientation of the BDA for the spectrometer |  | 27/7/01 | Closed, note written and circulated. Will be incorporated into the BDA interface doc and SSRD. |
| AI-MAN-0772-10 | System team | develop a strategy for dealing with power increase. |  | 31/7/01(progress meeting with Gavazzi) | This is a project level problem, Ken to discuss with the other instruments. |
| AI-MAN-0772-11 | ECS | Outline new document scheme to the consortium |  |  | Open, check new proposals, and circulate note. |
| AI-MAN-0772-12 | KJK | Ask for copy of PACS MOU |  | 31/7/01 | Yes but not yet received |
| AI-MAN-0772-13 | ECS | Seek confirmation of DDR dates |  | 27/7/01 | open |

| No. PT-14-0797 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| AI-MAN-0797-01 | KJK | Ken to draft a memo to ESA identifying concerns about the responsibilities of the various parties. |  | (by the end of this week) | Closed, communicate with Bruston and Lund in parallel. |
| AI-MAN-0797-02 | ECS | consider instigating an investigation into alternative design solutions to the cold bus bar. |  |  | Closed |
| AI-MAN-0797-03 | Peter Hargrave | define detector filter and incorporate into the filter ICD. |  | This to be defined before the BDA review. | Open |
| AI-MAN-0797-04 | ECS | Compile contents list for JPL ICD |  | 10/8/01 | Closed, some proformas required by JPL, |
| AI-MAN-0797-05 | KJK | confer with other PMs to decide what to do - maybe require IFSI to do the appropriate analysis. |  | 17/8/01 | Open, |

Actions raised during this meeting

| No. PT-15-0824 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| AI-MAN-0824-01 | MJG | Combine Matt and Kens comments on partnership agreement and send to Alcatel |  | 12/9/01 | open |
| AI-MAN-0824- | ECS | Review product tree |  | 12/9/01 | Open |
| AI-MAN-0824-03 | JD | Organise review of IID-A and B |  | 27/8/01 | Open |
| AI-MAN-0824-04 | ECS | Clarify date of technical meeting with ESTEC |  | ASAP | Open |
| AI-MAN-0824-05 | ECS | ES to let JB know that current version of the DDD is not to be updated until the IBDR. |  | 30/8/01 | Open |
| AI-MAN-0824-06 | ECS | Set up structure review meeting |  | Proposed date 29/8/01 | Open |
| AI-MAN-0824-07 | BMS | Circulate first DDR draft report and amend as a result of the wrap up review. |  | 21/8/01, stage 1 30/8/01, stage 2 | Open |
| AI-MAN-0824-08 | MJG | Circulate agenda for the BMS delta review |  | 21/8/01 | Open |
| AI-MAN-0824-09 | ECS | Remind hardware managers to provide their reports every month without fail. |  | 30/8/01 | Open |
| AI-MAN-0824-10 | MJG | Matt to contact CEA regarding lack of contact recently. |  | 30/8/01 | Open |
| AI-MAN-0824-11 | JD | John to chase electronics suppliers for documents and dates for DDR |  | 29/8/01 | Open |
| AI-MAN-0824-12 | BMS JD | Produce a list of critical information that’s ill-defined or incomplete in the IID-A and IID-B that we need to know about before holding the IBDR. |  | 30/8/01 | Open |

General comment :  We need to keep an open items list, not just a list of actions - agenda will be changed to incorporate this.

# Project Management Issues

Alcatel

Lack of information on how Alcatel and ESA work together.  Requests for information come from both parties.

No action to be taken in the short term.

Partnership agreement, dates are still in the document and not agreed by SPIRE.

Matt to combine Ken’s and his own comments and send to Alcatel

Product tree needs revising, e.g. harness. ECS to review.

IIDB.

New versions of A and B received, JD to organise review of these docs by 27/8/01.

Design description document needs updating, but low priority until after the DDRs.

ES to let JB know that current version is not to be updated until the IBDR.

Spacecraft level testing EQM

Response received by T PassVogel, disappointed by the SPIRE response, they consider the EQM tests to be more important than instrument level tests.

Technical/progress meeting planned for 10/9/01 or 25/9/01,  ECS to clarify date of meeting and to ensure that the EQM test programme is a major agenda item.

Agenda item to be list of missing/poorly defined critical interface issues.

Structure and thermal strap programme

Set up meeting to review structure at MSSL 29/8/01 confirm with Berend. Invite Ray Carvell. ACTION ECS:

Topics to discuss

JPL interfaces, for detector review, plus mirrors

Overall schedule.

Status and plans for thermal strap.

BSM flex pivots

Wrap up review on 23/8/01.  Matt and Bruce to attend

Technical review.

Funding.

Circulate first DDR draft report and amend as a result of the wrap up review. ACTION BMS

Circulate agenda  ACTION Matt

Electronics issues

John to visit CEA next week, probably.

Matt to contact CEA regarding lack of contact recently.

## Management Reporting and Control

Many subsystems still not sending in monthly reports.
Subsystem and SPIRE monthly reports are essential.

Action:  ES to remind hardware managers to provide their reports every month without fail.

## Document change and configuration control

## PA

Cleanliness plan almost complete.

Maintaining outside cleanliness will be difficult to achieve and quantify.

Develop a procedure for cleaning.

Insist on clean subsystems.

## Business Agreements

JPL in progress

CEA awaiting response

Others TBD

## Schedule:

ESA have requested visibility of next DDRs and proposed IBDR

# Instrument Issues

Mirrors

Still some inconsistency between optical prescription and MSSL model, probably in transfer of models.

Tony Richards has analysed the system and has found no errors in the LAM model.

Detectors

## OBS and Instrument Control

## DPU

# ICC Issues

Not Discussed

# Meetings:

## Detailed design Reviews

### Planned Dates for other DDRs

Latest summary:

- Mirrors:						Complete

- FTS:								Some time in September.  MCU and SMEC should be	reviewed together.

- DRCU/WIH 				TBD.

- Structure/thermal straps 			End September TBD

- DPU:  						Not decided yet

- AIV							6/9/01

- EGSE:				 		TBD

- BDAs:/JFETs				30/7/01, NASA review, formal DDR done by a document review  and meeting in September.

- Filters/calibs:				18/9/01

- BSM: 						30/7/01 not all issues closed out, delta review on 23/8/01

- OBS							Requirements review 30/7/01

- Shutter PDR: 				July 17,  Almost a DDR, some aspects still open.

- Cooler						Complete, some RIDs to be signed off.

- DRCU simulator			TBD

John to chase electronics for documents and dates for DDR

IBDR

Action:  BMS/JD to produce a list of critical information that’s ill-defined or incomplete in the IID-A and IID-B that we need to know about before holding the IBDR.

This to be raised as key issue at the technical meeting on (September 25 TBC).

# Progress on Open Issues

None discussed

# AOB

Nothing raised

Next meeting

12/9/01,  Start 12:00,  RAL