Work Package:	BSM                                                                     SPIRE-ATC-REP-000855

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype assembled. Prep for IBDR underway. |
| 2. Subsystem Progress This Month |
| DDR closeout held on 23.Aug. Opted to attempt up-screening of 429 stainless flex pivots and Smiths Industries picots. By opting not to fit inconel pivots to STM a six month breathing space before QM model purchase exists. 2 axis prototype assembled. Magnetic field tests scheduled for next week. and DM design changes in hand. |
| 3. Problem Areas | Remedial Action |
| Flex pivot prices over budget. | Up-screening of commercial pivots will be attempted. Inconel a fallback. |
| 4. Engineering Activities |
| Drawing pack undergoing configuration control release and design iteration towards DM manufacture. BSM Test Plan meeting held and test plan being written. Control systems checks of BSM motor damping performed |
| 5. Design Changes |
| Design for manufacture review held and small changes in hand. Prototype assembly being studied for design tweaks - chop axis throw currently undersize by 40%. |
| 6. PA/QA Activities |
| NCR system being trialled. Flex pivot up-screening test rig concept design in hand. |
| 7. Subsystem Management Issues |
| Flex pivot - Collaboration with HIFI on flex pivots yet to be closed out. Some effort constraints delaying release of DM drawings and FEA of assembly vibration response. Quotes for off the shelf Infineon position sensors for DM have a high MoQ. Given the required outlay Delaying purchase while we work out if we can get some which are closer to flight status. RFQ for 20K dewar issued |
| 8. Actions Requiring Immediate Attention |
| ATC-116 - M.Griffin/R.Carvell - Talk to Mike Sandford about costs of use of RAL cold vibration facility ATC -187 - BG to order additional position sensors D.Griffin - release of final BSM DDR report |
| 9. Status of Previous Actions |
| ATC-159 - B.Graham characterise the flux of the BSM magnets/motors. - scheduled ATC-183 - B.Stobie to check effects of harness length on motor damping - complete, ATC tech note issued |
| 10. Activities Yet to be Achieved |
| Configuration control release of drawing pack presented at DDR. PA plan up-issue delayed by effort shortfall. |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| Report on sensor stability to LAM | 07 Jul 00 | 21 Jun 01 | 30.Jul.01 | +1 month |
| Prototype Detail design release | 24 Jan 01 | 30 May 01 | 30May01 |  |
| Update ICD structure | 24 Oct 00 | 13 Jun 01 | 13 Jun 01 |  |
| 20K test dewar available | N/A | Oct 01 |  |  |
| SPIRE Intermediate Instrument Design Review (IIDR) | TBD | 23-24Apr.01 | 23-24Apr.01 |  |
| Integrate Prototype (in place of DM 2) to LAM | 30 Mar 01 | Dec.01 |  | revised |
| Internal ATC review | new | 3 Jul 01 | 2.Jul.01 |  |
| Detailed Design Review | 30 Jan 01 | 31 Jul 01 | 30.Jul.01 | -1 day |
| DM release for manufacture | Oct.01 | Oct.01 |  | New |
| 2 axis prototyping at ATC complete | N/A | Dec.01 |  | New |
| SPIRE IBDR | N/A | Nov.01 (TBC) |  | New |
| DM tests complete | N/A | 22 Mar 02 |  |  |
| BSM STM del'y to RAL | 01 Feb 00 | 01 Jul 02 |  |  |
| BSM CQM delivery to LAM | N/A | Jul.02 |  |  |
| BSM CQM del'y to RAL | 13 Mar 02 | Under review |  |  |