Work Package	PCAL                                                                    SPIRE-UCF-REP-000858

| 1. Subsystem Progress Since Project Inception |
| --- |
| Haller-Beeman thermal source evaluated - meets SPIRE requirements for power dissipation vs photometric power. Design needs modification to meet speed requirement. Detailed design of housing in progress. Prototype housing complete to enable tests of light pipe coupling to proceed. Tests show there is no significant reduction in light output when using the prototype light pipe coupled to the illuminator. |
| 2. Subsystem Progress This Month |
| Design almost complete in run-up to DDR New device, HB6, received |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| Two new design engineers appointed for SPIRE/HFI – Brian Kiernan started work 6/8/01 DDR date fixed for 18/9/01 Jeff Beeman & Ernst Kreysa confirmed attendance as external reviewers at DDR |
| 5. Engineering Activities |
| 6. Design Changes |
| New thermal sources are being modelled at Cardiff. Iteration on source design with Jeff Beeman. New device (in manufacture) will trade-off speed and power dissipation, following the design of HB5, with small modifications to the heat capacity & thermal conductivity of the legs. |
| 7. PA/QA Activities |
| Cardiff PA plan completed. FMECA complete. |
| 8. Actions Requiring Immediate Attention |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones – NB. These are common with SCAL | Status |
| Tue 05/12/00 Tue 03/04/01 Fri 30/03/01 Tue 22/05/01 Wed 17/10/01 Wed 27/03/02 Thu 20/06/02 Thu 13/12/01 Fri 22/03/02 Fri 18/10/02 Tue 04/02/03 Wed 14/05/03 Wed 01/10/03 Wed 03/09/03 Tue 09/12/03 | QMW Source Design review Prototype source testing complete Final Interface definition from ATC Calibrators design review (Internal) DM PCAL Delivery to ATC SCAL STM delivery to RAL CQM SCAL design review CQM PCAL design review CQM PCAL to ATC CQM SCAL to RAL PFM calibrators design review PFM PCAL to ATC PFM SCAL to RAL FS PCAL to ATC FS SCAL to RAL | Complete Tests continuing – not driving schedule Complete Complete On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |

Work Package	SCAL

| 1. Subsystem Progress Since Project Inception |
| --- |
| SCAL completely redesigned – photometric modelling showed inability to match telescope spectrum with previous design. New design almost complete. Thermal model validated design. |
| 2. Subsystem Progress This Month |
| New design nearing completion. Thermal prototypes built & tested – validated design. Basic mechanical tests passed – will perform warm vibration at MSSL in early September. |
| 3. Problem Areas | Remedial Action |
| None |  |
| 4. Subsystem Management Issues |
| Two new design engineers appointed for SPIRE/HFI – Brian Kiernan started work 6/8/01 DDR date fixed for 18/9/01 Jeff Beeman & Ernst Kreysa confirmed attendance as external reviewers at DDR |
| 5. Engineering Activities |
| New thermal/mechanical prototypes in manufacture |
| 6. Design Changes |
| New design of complete SCAL system (including structure) almost complete – interface drawings in production. |
| 7. PA/QA Activities |
| PA plan complete. Compiling DML and DPL. FMECA complete. |
| 8. Actions Requiring Immediate Attention |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones – NB. These are common with PCAL | Status |
| Tue 05/12/00 Tue 03/04/01 Tue 22/05/01 Wed 27/03/02 Thu 20/06/02 Thu 13/12/01 Fri 22/03/02 Fri 18/10/02 Tue 04/02/03 Wed 14/05/03 Wed 01/10/03 Wed 03/09/03 Tue 09/12/03 | QMW Source Design review Prototype source testing complete Calibrators design review (Internal) SCAL STM delivery to RAL CQM SCAL design review CQM PCAL design review CQM PCAL to ATC CQM SCAL to RAL PFM calibrators design review PFM PCAL to ATC PFM SCAL to RAL FS PCAL to ATC FS SCAL to RAL | Complete Tests continuing – not driving schedule Complete On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |

Work Package	Filters

| 1. Subsystem Progress Since Project Inception |
| --- |
| SPIRE filtering scheme finalised. Prototyping in progress. Filter SSSD updated for DDR. Slight change of MW band for commonality with HFI band. |
| 2. Subsystem Progress This Month |
| Filter SSSD updated for DDR. Slight change of MW band for commonality with HFI band. |
| 3. Problem Areas | Remedial Action |
| Space limitations from structure mean Cardiff have to investigate the use of dichroic rings which are thinner than desired in order to avoid warpage | Prototype rings are being designed, and will be tested for flatness at 77K, using a mylar film as the suspended medium. |
| 4. Subsystem Management Issues |
| New filter technician started 1/8/01 300mK interface with JPL BDAs needs immediate resolution – no information from JPL. Also need delivery dates for each model for the 300mK filters. Resolution in progress – MJG to push for resolution at Caltech meeting – 5/9/01. |
| 5. Engineering Activities |
| Prototyping |
| 6. Design Changes |
| none |
| 7. PA/QA Activities |
| PA plan and DPL/DML complete. FMECA performed on all filter components. |
| 8. Actions Requiring Immediate Attention |
| Resolution of 300mK filter interfaces with JPL. Delivery dates of 300mK filters to JPL for each model. |
| 9. Status of Previous Actions |
| None |
| 10. Activities Yet to be Achieved |
| Demonstration of working prototype dichroics & beam splitters (hot pressed, rather than vacuum gap). |
| 11. Budgets |
| 12. Milestones | Status |
| Wed 21/11/01 Wed 19/06/02 Tue 14/10/03 Wed 15/09/04 TBD TBD TBD | STM filters to RAL CQM Delivery to RAL PFM delivery to RAL FS delivery to RAL 300mK CQM filters to JPL 300mK PFM filters to JPL 300mK FS filters to JPL | On schedule On schedule On schedule On schedule Need info. From JPL Need info. From JPL Need info. From JPL |
| 13. Schedule Changes |
| None |

Work Package	300mK straps

| 1. Subsystem Progress Since Project Inception |
| --- |
| Thermal test dewar ready Thermal interface tests in progress |
| 2. Subsystem Progress This Month |
| None |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| No progress on this subsystem this month – this will receive full attention from Cardiff after filter & calibrators DDR. |
| 5. Engineering Activities |
| Cryostat modification to enable bus-bar tests to proceed – new thermal link from He3 head to bus bar in manufacture |
| 6. Design Changes |
| 7. PA/QA Activities |
| None |
| 8. Outside Agency Interfaces |
| MSSL for drawings and hardware |
| 9. Actions Requiring Immediate Attention |
| Routing of 300mK bus bars in photometer & spectrometer 2K boxes. Specification document Re-definition of development plan. |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| 12. Budgets |
| 13. Milestones | Status |
| Mon 12/02/01 Thu 25/01/01 Tue 27/02/01 Wed 09/05/01 Wed 28/02/01 Thu 12/04/01 Tue 29/05/01 Wed 11/07/01 Thu 02/08/01 Thu 23/08/01 Thu 23/08/01 Fri 24/08/01 Mon 10/12/01 Mon 28/01/02 Tue 23/04/02 Wed 03/09/03 Wed 29/10/03 | He-7 fridge shield ready GRTs from Lakeshore Test dewar ready Interface study complete Design Review - LBDR1 LBP1 to QMW (2 off) Design Review - LBDR2 LBP2 to Cardiff (2 off) Design report Light baffle design complete Prototype light baffle design Design Review - CSDR1 Cold strap prototypes - Test Report STM design review - CSDR2 STM/CQM straps ready for integration PFM straps ready for integration FS straps ready for integration | Complete Complete Complete Late Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) On schedule On schedule On schedule On schedule On schedule |
| 14. Schedule Changes |
| Development plan to be re-defined |

Work Package	AIV participation

| 1. Subsystem Progress Since Project Inception |
| --- |
| Cryogenic black body & flip mirror/shutter concept produced – approved at AIV review |
| 2. Subsystem Progress This Month |
| None |
| 3. Problem Areas | Remedial Action |
|  | . |
| 4. Subsystem Management Issues |
| Development plan and specification/design documents needed. This will receive attention from Cardiff after filters & calibrators DDR |
| 5. Engineering Activities |
| none |
| 6. Design Changes |
| Constant! |
| 7. PA/QA Activities |
| None |
| 8. Outside Agency Interfaces |
| RAL for design changes & interface definition. |
| 9. Actions Requiring Immediate Attention |
| Resolution of shutter/CBB interface |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| Production of CBB & flip mirror module. Provision of reference detector Provision of FTS |
| 12. Budgets |
| 13. Milestones | Status |
| 14. Schedule Changes |
| None |

Work Package	JPL BDA test support

| 1. Subsystem Performance Progress Since Project Inception |
| --- |
| Optics modules designed manufactured Test cryostats at JPL Fridge #1 at JPL |
| 2. Subsystem Progress This Month |
| Second fridge completed by Simon Chase & sent to JPL. Optics modules ready for shipping. Filters in manufacture. |
| 3. Problem Areas | Remedial Action |
| According to JPL, problems with first fridge - poor hold time – out of spec. – elevated temperature of evaporator head during He3 condensation – seems to be caused by poor cooling power of He4 pump – leak?? | PCH consulting with Simon Chase |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| Filters in production. |
| 6. Design Changes |
| 7. PA/QA Activities |
| None |
| 8. Outside Agency Interfaces |
| Janis Cryogenics for test dewars. Chase research for fridges. Tekdata for wiring harnesses. Symons mirror technology for mirrors. Deteronics (TBC) for connectors (hermetic). TMC for machining work (optics module) |
| 9. Actions Requiring Immediate Attention |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| To be defined |
| 12. Budgets |
| 13. Milestones | Status |
| 14. Schedule Changes |
| None |