Notes on project managers teleconference                       SPIRE-RAL-MOM-000865

17/9/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin | X |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin |  |
| Peter Hargrave |  |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain |  |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King |  |
| Dominique Pouliquen |  |
| Gary Parks | X |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith | X |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand | X |
| Riccardo Cerulli-Irelli |  |

Subsystem reports

IFSI  (Riccardo) - DPU

Not present

Grenoble  (Lionel) – Cooler

Procedures being written.

No problems identified.

AIV plan issued, comments from RAL invited.

USK. (Don)  - Shutter

Design description document  in preparation

ECR being readied for a change from spring to a stepper.

Subsystem spec doc (IRD) being updated.

Parts – proposed plan using NASA approved parts is ok, system team will review parts list when available.

Tests being carried out on flex cable at 12K, extra tests from last week have been carried out, still ok.

Telecon with Com Dev held.

Shutter is not designed to be a contamination barrier; Plastic cover will be supplied as a separate part.

Cardiff. (Peter)  Filters, calibrators

Not present

ATC  (Ian)  -  BSM

Not present (public holiday in Scotland)

JPL  (Jerry)  - Detectors

Second part of review process complete.

Preparing for document review (DDR), planned for end September.

Procurement started.

No Major issues from JPL side.

CQM BDA release back to JPL date, ECS to specify date.

MSSL (Berend) – Structure

Project meetings now held on Monday mornings.

Mirror issues are being addressed.

DDR still planned mid November.

Shutter model to be sent to RAL  (Tony Richards)

Documentation for DDR being completed.

LAM.  (Didier)  - Mirrors, SMEC

Documentation for SMEC DDR being prepared.

26th and 27th, Bruce and John D to attend.

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

DDR last week, some schedule issues.

STM, BSM will be used for test, what surface finish is required, RAL to specify.

HOB simulator discussion required, Dave to schedule.

Test plans for functional and acceptance tests required, including subsystem EGSE requirements. Required by start October.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010402-05 | Provide information on the parts approval and quality status for the Canadian components. | Don | 31/7/01 | USK plan to use NASA approved parts wherever possible. A preliminary parts list will be available at the DDR. | Closed |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| 010611-05 | Notify SAP of the grounding scheme to be used for the DRCU | John | ASAP | Covered by harness doc | closed |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN-0796-01 | Respond cleanliness questions,. | RAL | 17/8/01 | Cleanliness plan (draft) issued | closed |
| AI-MAN- | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| A!-MAN- | Check status of the FTS for the AIT facility | Don | 17/9/01 | Cardiff to supply | Close |
| AI-MAN-0851-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 |  | open |
| AI-MAN-0865-01 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |