Notes on project managers teleconference                       SPIRE-RAL-MOM-000873

24/9/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter | X |
| Chris Brockley-Blatt | X |
| Matt Griffin |  |
| Peter Hargrave |  |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain | X |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King | X |
| Dominique Pouliquen |  |
| Gary Parks | X |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark | X |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato | X |

Subsystem reports

IFSI  (Riccardo) – DPU

Progress meeting at CG next week,

HIFI simulator delivered 7/9/01.

CPU board on schedule.

IF board late.

SPIRE simulator to be delivered next week.

Grenoble  (Lionel) – Cooler

New test cryostat is planned.

Cooler parts manufacture on schedule.

USK. (Don)  - Shutter

Shutter solid model is consistent.

Harness definition doc being reviewed.

Latch telemetry issue to be discussed at meeting with ESA/Alcatel this week.

DDR report to be in final draft this week

Shutter heater will be off during cooler regeneration.

Cardiff. (Peter)  Filters, calibrators

Not present

ATC  (Ian)  -  BSM

2 week delay in STM programme.

Prototype working in chop and jiggle.

Magnetic modelling request to MPAe.

Clean room tests being carried out.

JPL  (Jerry)  - Detectors

Release of drawings for fab 25/9/01.

Some minor interface issues still open

JFET membrane test scheduled for this week.

All documents planned for sign off at next meeting.

Thermal strap interface is still open, in detail e.g. torque of fasteners.

MSSL (Berend) – Structure

DDR date likely mid December.

Some Interfaces not closed, especially SMEC, JFET and  baffles.

Mirrors, 2K box supports, DBAs being progressed.

MGSE/AIT facility meeting held.

LAM.  (Didier)  - Mirrors, SMEC

Not present

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Not present

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0851-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 |  | open |
| AI-MAN-0865-01 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |