# SPIRE Project

## General

- This report covers July and August 2001.  Individual monthly reports shall be produced in the future.

- Project team has focussed on
-	Support and assistance of subsystem DDRs
-	Cryo-harness definition
-	IID-B update for SRR
-	Thermal modelling and analysis
- 	Follow-up of high priority items identified at IIDR

## Instrument performance

- Optimisation of the photometer and FTS bands was discussed  at the July 4-6 Consortium meeting.

- Photometer bands have been modified very slightly to provide complementarity with Planck HFI.

- FTS bands being studied and will be frozen for NASA CDR in September

- Instrument sensitivity models updated (minor changes)

## Problem Areas

- Vibration levels at detector level. Following extensive analysis and discussions with ESTEC and JPL, a solution is almost agreed.

- Late definition of cryo harness connectors.

- We need to procure our cold test harness now to keep to CQM schedule.

- Requested CQM delivery date is not compatible with the SPIRE schedule.  The payload-level EQM test programme  must be discussed with ESA and Alcatel

## Meetings

- Consortium meeting Cardiff 4 and 5 July.

- Optics DDR, LAM, 10 July.

- OBS meeting, IFSI, 10 and 11 July

- Meeting with ESTEC PA, RAL, 12 July.

- Shutter  PDR; ComDev, 17 July

- Project team meeting, RAL, 20 July.

- BSM DDR, ATC, 30 July

- Detector Peer Review, JPL, 30 and 31 July.

- Project team, RAL, 7 August.

- Vibration testing, ESTEC, 17 August.

- Project team, RAL, 20 August.

- BSM delta review, ATC, 23 August.

- Structure mini review, MSSL, 29 August

- EMC Working Group meeting, Cannes, 29 August

## Documents Issued

- Documentation set for Optics Detailed Design Review

- Documentation set for BSM Detailed Design Review

- Documentation set for Shutter Preliminary Design Review

- Documentation set for AIV Facility Detailed Design Review

- Viewgraph pack from detector Peer Review

- Cooler DDR report and RIDs

- Optics DDR report and RIDS

- Inputs to IID-B

- Wiring harness Definition Document

# Instrument Management

## Personnel

- Eric Sawyer joined the Project at the start of July as Instrument Development Manager (in charge of hardware programme).

- Trevor Dimbylow stood down as ICC Development Manager due to pressure of other projects.

- Ken King remains as overall Project Manager and has taken over as ICC Development Manager.

- Maintenance of instrument budgets has transferred from ATC (Colin Cunningham) to RAL ( Doug Griffin).

## Workpackages

The agreement with NASA over the deliveries and workpackages for the JPL  group has been updated and revised and will be formally signed in early September, prior to the NASA CDR.

## Schedule

No changes to major milestone list since April 2001

## Funding

The UK funding envelope is still inadequate fore the hardware plus ICC development programme.  Pressure still exists to descope hardware (BSM or Flight Spare).

# Instrument engineering

## Instrument Design Changes

- Minor changes to wavelength bands as noted above.

- Spectrometer calibrator design has been improved for better spectral nulling and redundancy.

## PA/QA

- Documentation control system has been implemented.

- Cleanliness

## Budgets

- Nothing to report

# Instrument Subsystems

| Subsystem | Responsible | Status | Schedule status |
| --- | --- | --- | --- |
| BSM | ATC | DDR held on 30/7/01. Some outstanding issues, especially selection/cost of flex pivots. Procurement plan has been formulated with two main options. | OK |
| Calibrators | Cardiff | Design and prototype testing continuing. DDR will be on Sept. 18 | OK |
| Cooler | SBT | DDR completed – RIDS not yet closed | OK |
| Detectors, JFETS and RF Filters | JPL | JPL peer review held on 30/7/01 NASA CDR scheduled for 11-12/9/01. Vibration levels problem near solution DDR close out will follow within ~ 3 weeks. | OK |
| DPU and OBS | IFSI | OBS meeting held | OK |
| DRCU and WIH | SAp | DRCU specification v8 issued FMECA carried out on DRCU – no major problems. | OK |
| DRCU simulator Inst simulator | Stockholm | OBS meeting supported | OK |
| Filters, Dichroics | Cardiff | Filtering scheme being finalised following small modifications to bands; prototyping in progress DDR will be on Sept. 18 | OK |
| Mirrors | LAM | DDR complete RIDS not yet closed Some final iterations before manufacture | OK |
| Shutter | USK | PDR complete SPIRE has proposed possibility of common shutter for all instruments. Early decision needed on this. | OK |
| Spectrometer Mechanism | LAM | Study done by BE systems on selection of flex pivots. Pivot type selected. Request for increased maximum thermal dissipation studied and report issued (SPIRE-RAL-NOT-000771) | OK |
| Structure | MSSL | FPU mechanical model enhanced to allow more accurate analysis/prediction of subsystem vibration levels. 2-K photometer box will need to be redesigned to minimise vibration levels at detectors. 300mK strap design has been delayed due to this activity. Structure DDR delayed (now expected November 2001) | To be reviewed |
| Thermal straps | Cardiff | Testing of prototype straps about to start | OK |
| AIV/Calibration facility | RAL | DDR planned for 6/9/01, this will release the cryostat for manufacture | OK |

# Instrument AIV

A review of the AIV and calibration facility is scheduled for 6/9/01

# Action Item List

Note, These actions mostly appear to be old and are probably obsolete and able to be closed.  We can discuss them at the next ESA/SPIRE meeting.

| Action Number | Description | Due Date | Responsible | Status | Disposition | Reference |
| --- | --- | --- | --- | --- | --- | --- |
| AI-ESA-0354-01 | Modes of observations: instrument teams to provide typical observation profiles for the different observation modes | 15/09/00 | MJG | Open |  |  |
| AI-ESA-0394-03 | ESA to provide thermal model of cryostat OB | 10/05/00 | ESA | Open |  |  |
| AI-ESA-0394-06 | SPIRE to re-send comments on FIRST Alignment Plan | 19/04/00 | MJG, KJK, BMS, Winter | Open |  |  |
| AI-ESA-0366-01 | Instrument teams to complete questionare and return to Bernard Jackson and Antonio Ciccolella | 14/04/00 | All, CRC | Closed |  | SPIRE-ATNOT-000482 |
| AI-ESA-0428-03 | To request mass, thermal and power dissipation to be put in the Subsystem Specification Documents |  | KJK | Open |  |  |
| AI-ESA-0428-04 | To clarify information in the Cryoharness Tables |  | CRC | Closed |  |  |
| AI-ESA-0428-05 | To confirm pointing requirement in section 5.12..2 |  | MJG | Open |  |  |
| AI-ESA-0428-06 | To provide the maximum shock level (plus time duration) allowed on the instrument during transport. |  | Winter | Open |  |  |
| AI-ESA-0428-07 | To confirm maximum level of microvibrations that we can accept at the optical bench interface |  | CRC | Open |  |  |
| AI-ESA-0428-08 | To send Delta PDR agenda to ESA |  | KJK | Open |  |  |
| AI-ESA-0428-09 | To send Word macro to CRC |  | KJK | Open |  |  |
| AI-ESA-0483-01 | Instrument groups to comment/approve 5.11.1 of IID-A "Instruments, which are not the prime instrument for a certain observation, shall not exceed a TM rate of 2 kbps each" |  | MJG, KJK | Open |  |  |