Notes on project managers teleconference                       SPIRE-RAL-MOM-000898

01/10/2001

Chair:		Ken King

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin |  |
| Peter Hargrave |  |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain | X |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King | X |
| Dominique Pouliquen | X |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand | X |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |

Subsystem reports

JPL (Jerry)

Purchase orders issued for BDA, except for critical items (waiting for mechanical ICD sign-off at end of week). Strain relief is the only open item.

Monthly report to be issued today.

Delivery of CQM BDAs is likely to be 3 months late - still to be checked and confirmation of date given by Thursday

ATC  (Ian)  - BSM

Has Brian requested connectors for common procurement? Ian will contact John about this.

2 week delay in DM programme - people are now back at ATC and the delay will be fmonitored over the next week or so.

Talking with RAL about doing some FEA work but RAL may be overbooked?

MSSL (Berend) – Structure

2k Box work is progressing

Reviewing Schedule - should be done this week - trying to bring DDR to mid-November

BDA, BSM ,SCAL, thermal straps interfaces should be closed this week

Beam footprint analysis continued to non-optical components (stops/dichroics)

USK. (Don)  - Shutter

Worry about meeting the lower blade temperature requirement if the cryostat lid is at 300k. Need emissivity of ~3% to allow this. Joe will contact Bruce about the need for the lower temperature (i.e. for which tests is it requiored?)

Test Procedures are available - will be distributed to Dave on Friday.

LAM.  (Dominique)  - Mirrors, SMEC

Preparing for DDR (22-23 Oct) - documents needed by end of next week.

SMEC actuator - is it necessary to provide full performance at room temperature?

- if not then could alter pivot stiffness and reduce current required at low temps.

Consequence would be that it would only be possible to move the FTS by ~10% of the full travel at room temperature using the MCU.

Test of mirror manufacture procedure next week at manufacturer's workshop.

List of commands should be available by end of next week

SBT (lionel)

Coolers are being manufactured.

Test procedures being written

Drawings for new test cryostat (able to test 48 hrs hold time) ready for issue of ITT

IFSI  (Riccardo) – DPU

Not present

Cardiff. (Peter)  Filters, calibrators

Not present

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Not present

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820.01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820.02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |