| CARLO GAVAZZI SPACE SpA | RELAZIONE DI RIUNIONE/VISITA NOTES OF MEETING/VISIT | N° DPU-MI-CGS-010 |
| --- | --- | --- |
|  |  | FOGLIO DI SHEET 1 OF 4 |
| DATA – DATE 04/09/2001 | LOCALITA’ – LOCATION MILANO | COMMESSA – JOB HSO/FIRST - DPU | RIF. - REF. 1916 |
| IMPIANTO PROJECT | DESCRIZIONE DESCRIPTION | CLIENTE CUSTOMER |
|  | LOCALITA’ LOCATION | ORDINE CONTRACT |
| SCOPO RIUNIONE PURPOSE OF MEETING | HSO/FIRST – DPU Progress Meeting 3 | REDATTO – WRITTEN BY A. LONGONI DISTRIBUZIONE DISTRIBUTION |
| PRESENTI ATTENDED BY | NOMI - NAMES | POSIZIONE - POSITION |  |
| PUNTI ITEMS | ARGOMENTI DISCUSSI – DESCRIPTION OF DISCUSSION | AZIONE A CURA (1) ACTION BY (1) |
|  | PARTICIPANTS O. BAUER MPE Garching (PACS) R. ORFEI CNR IFSI R. CERULLI CNR IFSI A. LONGONI CGS G. SANTORUVO CGS A. SCIORTINO CGS (Part Time) A. BERTOLI CGS (Part Time) |  |
| CARLO GAVAZZI SPACE SpA | RELAZIONE DI RIUNIONE/VISITA NOTES OF MEETING/VISIT | N° DPU-MI-CGS-010 |
|  |  | FOGLIO DI SHEET 2 OF 4 |
| DATA – DATE 04/09/2001 | LOCALITA’ – LOCATION MILANO | COMMESSA – JOB HSO/FIRST - DPU | RIF. - REF. 1916 |
| PUNTI ITEMS | ARGOMENTI DISCUSSI – DESCRIPTION OF DISCUSSION | AZIONE A CURA (1) ACTION BY (1) |
| 1 2 | The Meeting Agenda is the following: Presentation of Activities Status Open Points Any Other Business Activities Status CGS presents the Progress Meeting 3 Hand Out (attached as Annex 1). A short summary on the activities status, extracted from the Hand Out, is reported hereafter: CPU Board: Activities in line with the schedule PL I/F Board: A delay due to the unavailability of IFSI FSDL and LSL simulators is reported DC/DC Board: A delay of two weeks is reported due to delays in the Artwork Design Motherboard: A delay of one week is reported due to delays in the Artwork Design SW: A delay between one and two weeks is reported. This delay could be recovered by CGS. Open Points Availability of IFSI FSDL and LSL simulators: IFSI reports that the simulators will be delivered within week 37. Any Other Business Power Consumption: SPIRE and PACS will not accept 26W for DPU power consumption. CGS to revise the DPU power budget (considering also the power consumption measured on the boards instead of the estimated). PACS will investigate with ESA about the possibility to increase the DC/DC converters frequency to try to improve the efficiency. | AI #1 CGS 28/09/2001 AI #2 PACS 14/09/2001 |

| CARLO GAVAZZI SPACE SpA | RELAZIONE DI RIUNIONE/VISITA NOTES OF MEETING/VISIT | N° DPU-MI-CGS-010 |
| --- | --- | --- |
|  |  | FOGLIO DI SHEET 3 OF 4 |
| DATA – DATE 04/09/2001 | LOCALITA’ – LOCATION MILANO | COMMESSA – JOB HSO/FIRST - DPU | RIF. - REF. 1916 |
| PUNTI ITEMS | ARGOMENTI DISCUSSI – DESCRIPTION OF DISCUSSION | AZIONE A CURA (1) ACTION BY (1) |
|  | IFSI to provide CGS with the files of the latest versions of IIDs. PACS and IFSI strongly suggest to run acceptance tests at integrated level. CGS to verify if the shape of OP400 already ordered by Tecnologica (LCC leadless chip carrier) fits with CGS need or if it will be necessary to order a different shape (DIL dual in line or other). CGS to issue an ATP for FM remaining active parts (transistors and diodes). IFSI requests to CGS to provide a detailed schedule (same level of actual EM detailed schedule) also for QM and FM/FS, assuming relevant ATPs as by the contract: QM ATP: 15/11/2001 FM ATP: 15/12/2002 It is understood that these schedules will not take into account any major modification to the actual design. PACS recommends a close collaboration between IFSI and CGS to optimise activities, efficiency and overall schedule. IFSI and CGS confirm that different actions have been taken to set up a closer collaboration between IFSI and CGS, going through the IFSI participation on the integration phase and CGS assistance at SW integration at IFSI premises, if needed. During the visit in CGS laboratories, CGS shows the CPU board under testing trough emulator connected to DSP and the PL I/F board (under repairing for a chip replacement) | AI #3 IFSI 14/09/2001 AI #4 CGS 07/09/2001 AI #5 CGS 14/09/2001 AI #6 CGS 07/09/2001 |

| CARLO GAVAZZI SPACE SpA | RELAZIONE DI RIUNIONE/VISITA NOTES OF MEETING/VISIT | N° DPU-MI-CGS-010 |
| --- | --- | --- |
|  |  | FOGLIO DI SHEET 4 OF 4 |
| DATA – DATE 04/09/2001 | LOCALITA’ – LOCATION MILANO | COMMESSA – JOB HSO/FIRST - DPU | RIF. - REF. 1916 |
| PUNTI ITEMS | ARGOMENTI DISCUSSI – DESCRIPTION OF DISCUSSION | AZIONE A CURA (1) ACTION BY (1) |
|  | Review of Actions from Progress Meeting 2 (Ref. DPU-MI-CGS-015 dated 31/07/2001) Item 6: Documentation Delivery IFSI to circulate CDR1 and CDR2 MOM: Closed CGS to provide the CDR presentation file: Closed CGS to provide IFSI the PM2 presentation: Closed Item 7: IFSI to update Test Plan: Open Item 8: HIFI, SPIRE and PACS PA managers to comment CGS PA Plan: Open NEW ACTION: IFSI to circulate the CGS DPU Product Assurance Plan. Item 9: Planning Review Line 3: SW CCSDS Delivery: CGS to replace word CCSDS with PKT TM/TC: Open CGS to update the planning and to provide the file to IFSI: Closed To add a Progress Meeting on 07/11/2001 Closed To add a Progress Meeting on 03/12/2001 Closed To provide a better visibility on SW: Closed Schedule optimisation: Closed Item 10: HIFI to provide to IFSI EIDP Definition: Closed NEW ACTION: IFSI to circulate the EIDP Definition received from HIFI Item 11:HIFI to review CGS EIDP contents: Open | AI #7 IFSI 10/09/2001 AI #8 IFSI 10/09/2001 |

# Text boxes

CARLO GAVAZZI

CARLO GAVAZZI

CARLO GAVAZZI

CARLO GAVAZZI