Notes on project managers teleconference                       SPIRE-RAL-MOM-000976

22/10/2001

Chair:		Ken King

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin | X |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor |  |
| Ian Pain | X |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King | X |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith | X |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |

General

The IBDR has been confirmed for March 5/6 2002. Probably at RAL

There is a need to document the STM units to be delivered next year. Sam is putting together a Thermal Test Plan, which will specify the number and location of temperature sensors. We need ICDs for the STM subsystems that define how these sensors can be connected to the EGSE.

Action on subsystem groups

Subsystem reports

IFSI  (Riccardo) – DPU

Not Present

CEA Grenoble  (Lionel) – Cooler

Leak on test cryostat has been fixed

Parts for STM/CQM coolers have arrived assembly has started.

Comments are required on the Cooler AIV Plan (a new version will be distributed by Lionel)

USK. (Don)  - Shutter

Updated reduced thermal model of the shutter has been sent to RAL - waiting for SAM's reply as it needs to be iterated upon.

Test procedures for the CQM/STM have been submitted, but no comments received yet.

ECR submitted for update to URD.

ECR to be submitted for the harness definition

Document updating in progress: Design Description - to be available end Nov, Work Plan shows delivery on time.

Cardiff. (Peter)  Filters, calibrators

Progress on DDRs: ICDs should be closed over next two weeks.

Filters: JPL Test Facility filters are manufactured, need testing. I/F drawing needs to be clarifiedin order to make the mounts.

SCAL: Drawings for SCAL have been submitted but the workshop has not been available.

300mK: Interface testing  starts tomorrow.

ATC  (Ian)  -  BSM

Two axis prototype: Calibration of spring stiffness underway.

RAL cannot take on the FEA work so an ITT will be issued soon.

JPL  (Jerry)  - Detectors

There are still some drawings to be released but still on track to get hardware in December and start assembly.

Friction testing of Kevlar bands carried out: coefficient is greater than required minimum, low temperature tests to be completed, strength tests to be completed in next two weeks.

Detailed planning and costing will be finished in 1 week.

MSSL (Chris) – Structure

Testing of thermal bus bar has started.

Design of baffles almost complete, the harness layout will be next.

DDR will be 28-29 November.

LAM.  (Didier)  - Mirrors, SMEC

Not present

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Drawings for outer vacuum vessel are being reviewed before the end of the month.

Milestones for delivery of facility bits are still to be agreed by Cardiff

Comments on the job specification are required.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0851-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 | Closed at Telecon | closed |
| AI-MAN-0865-01 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |
| AI-MAN-0976-01 | To provide ICDs for STM subsystems | ALL | TBD |  |  |