Notes on project managers teleconference                       SPIRE-RAL-MOM-000984

15/10/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter | X |
| Chris Brockley-Blatt |  |
| Matt Griffin | X |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor |  |
| Ian Pain |  |
| Don Peterson |  |
| Bruce Swinyard | X |
| Ken King | X |
| Dominique Pouliquen | X |
| Gary Parks | X |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli | X |
| Renato Orfei |  |
| Brian Stobie | X |

General

Proposed date for IBDR March 5/6 2002 at RAL, TBC

Comments on JPL proposal for 300mK thermal control sent last week, a response will be sent by JPL this week.

Subsystem reports

IFSI  (Riccardo) – DPU

Meeting with CG earlier this month, some delay identified, due to 1553 interface problems, the   problems now solved.

Delivery likely 5 Nov.

Simulator problems are resolved and should meet the above date.

CEA Grenoble  (Lionel) – Cooler

Leak on test cryostat has caused small delays.

Parts should be received and assembly start soon.

USK. (Don)  - Shutter

Not present, but phoned later.

Emissivity of cover required from Sam’s model.

Cardiff. (Peter)  Filters, calibrators

300mK strap development continues.

Cold testing delayed by technical problems in the cryostat.

SCAL and PCAL interfaces being closed.

ATC  (Ian)  -  BSM  (Brian Stobie)

Two axis prototype being tested, some problems with sensor.

Supplier for small flex PCB being sought.

JPL  (Jerry)  - Detectors

Friction coefficient measurements on Kevlar being carried out, this may be made available to the consortium if ITAR allows, Jerry to check.

ICD (drawings), progress being made, a response from the system team should be available soon, including filter i/f.  Comments from RAL to JPL in the next few days.

Dustin to confirm to Cardiff that interface is finalised.

Detector summit, Jamie and Victor to attend.

MSSL (Berend and Chris) – Structure

FMECA complete in draft form.

2K box design progressing.

LAM.  (Didier)  - Mirrors, SMEC

Documentation being produced for DDR.

Mass budget not sufficient, 1.65Kg compared with 1.3Kg both excluding harness, to be discussed at DDR.

An upper stage launch lock is not planned.

Harness length required from MSSL, should be sent this week.

Micro vibration note is not understood well by the system team, LAM are asked to clarify some issues.

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Not present

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |