Notes on project managers teleconference                       SPIRE-RAL-MOM-001014

19/11/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin | X |
| Peter Hargrave |  |
| Jerry Lilienthal | X |
| Joe Taylor |  |
| Ian Pain |  |
| Don Peterson |  |
| Bruce Swinyard | X |
| Ken King |  |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith | X |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli | X |
| Renato Orfei |  |
| Brian Stobie |  |

General

HST meeting,  Funding problem in US, could impact Plank and SPIRE.

To be compatible with the system level CQM requirements we need to build the CQM to the standard proposed by the SPIRE consortium.

DDR preparations are ongoing. A note will be issued specifying Subsystem inputs.

Subsystem reports

IFSI  (Riccardo) – DPU

Interface boards delivered form CG and under test.

CEA Grenoble  (Lionel) – Cooler

Note on Kevlar to be issued tomorrow.

All parts in and verified.

EB welding next week.

Further tests on fatigue life of Kevlar,  100,000 cycles complete.

Analysis has shown that Silicon is present on the surface of the  Kevlar.

CQM will not be built to the same clean standards as the FM.

RAL to specify witness mirror.

USK. (Joe)  - Shutter

Not present

Cardiff. (Peter)  Filters, calibrators

Not present, sent this report

Got the re-furbished 300mK strap test dewar (ex. BACUS) to 4K last Sunday,

only to find a Helium leak - all Helium boiled off within 2 Hrs!

Found leak was at the interface between the stainless steel LHe fill pipes

and the top of the Al Helium tank. Spent all this week dismantling dewar,

repairing (hopefully) the leak, & re-building. We are closing up the dewar

this afternoon, with the experiment in place, and will leak check it

tonight. If all's well, I'll leave it on the pump over the weekend, and Iris

will pre-cool and further leak check on Monday.

I've also put a heater and thermometer on the heat exchanger of the first

fridge, & intend to troubleshoot the fridge in parallel next week.

I have some components now which will be used to simulate the cooler and BDA

strap interfaces. These will go into the dewar mid next week if all goes

well.

The Cardiff loo-rolls are in manufacture, as are the 300mK filter clamps.

All DDR documents have been checked, and errors corrected, ready to be sent

to Judy for livelinking. ICDs will follow ASAP.

ATC  (Ian)  -  BSM

Not present

JPL  (Jerry)  - Detectors

Report on Kevlar available and will be sent to RAL.

Component level qual testing added to development plan.

On schedule for manufacture, first components due in one week

Bolometer manufacture started, pin holes in Si nitride layer, had to be stripped and re coated.

Budget problems are being assessed, some reduction achieved. Some optical testing reduced, reduced spares etc.  No effect on deliverables.

No agreement on extra boards to be delivered to CEA.

Note on JFET interface to be issued by RAL.

MSSL ( Chris) – Structure

RF filter interface completed.

Filter mounts complete.

Dichroic mounts released for manufacture.

Agenda for DDR issued.

Docs to be released by Thursday.

LAM.  (Didier)  - Mirrors, SMEC

Not present

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Test plans outstanding from most subsystems. Integration procedures required from subsystems.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |