Notes on project managers teleconference                       SPIRE-RAL-MOM-001039

26/11/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband |  |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin | X |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain | X |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King |  |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres | X |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |

General

Subsystem reports

IFSI  (Riccardo) – DPU

Not present

CEA Grenoble  (Lionel) – Cooler

Not present.

RAL to specify witness mirror.

USK. (Joe)  - Shutter

First contract with COMDEV completed.

Second contract in preparation.

ECR in preparation  for no latch indicator, and harness update.

Canadian funding now secure, delays due to funding issues should be avoided if possible, USK still has contract open.

Thermal control is still an issue and depends upon cryostat lid performance, more thermal analysis required.

Cardiff. (Peter)  Filters, calibrators

Problems with cryostat solved.

Tests with gold plated joints complete, results confirm theoretical predictions.

More tests planned.

300mK strap components almost complete.

BDA  filter clamp in manufacture.

PCAL , HV6 source tested and meets requirements.

ICDs in progress.

Filter prototype work continuing.

ATC  (Ian)  -  BSM

Motor and spring torque retested

Ribbon harness being investigated.

Manufacture drgs to be released this week.

Meeting on flex pivots scheduled for next week.

Stability assessment started.

Lab move will cause a short delay.

Live Link sending two messages.

JPL  (Jerry)  - Detectors

Holiday week in US, little progress.

RF filter interface nearly agreed.

MSSL ( Chris) – Structure

Issue 13 of interface drg released.

DDR docs on the internet site.

Photometer detector box progressing.

Internal harness details need finalising, ACTION on RAL.

Filter interface needs finalising.

Areas to be coated with black need defining so qualification can be started. ACTION SYSTEM TEAM. (Matt and Bruce).

LAM.  (Didier)  - Mirrors, SMEC

Not present

SAp (Jean-Louis)   -  DRCU

Meeting requested with Astrium for interface discussion. ECS to chase.

System issues to be sorted before design can be frozen. ECS to chase.

New issue of DRU spec and ICD to be issued soon.

Meeting with LAM next week to finalise interfaces.

RAL,  (Dave) -  AIT

Not present.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-01 | RAL to specify., what surface finish is required, for the STM, BSM . | Dave Smith | 30/9/01 |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |