Work Package:	MCU electronics                                                 SPIRE-LAM-REP-001043

| 1. Subsystem Progress Since Project Inception |
| --- |
| Prototyping: DSP 21020 Evaluation board purchased Preliminary software for SMEC and BSM control (3 PIDs) done Performances between dSpace and evaluation board control software done Control loop performances using GSFC prototypes and dSpace done SMEC prototype board done MCU QM1 MAC QM1 electronics layout finished MAC QM1 routing finished MAC QM1 Board received MAC QM1 Board Control Bus FPGA tests: electrical tests OK, DAC control MAC QM1 Board ADC validated Qualification and Flight Model First list of critical components done/Participation of final list with Tecnologica |
| 2. Subsystem Progress This Month |
| DDR passed in October Size of electronics board received from CEA Boards mechanical interfaces received from CEA Tests on MAC Board MAC QM1 Reading/Writing DSP-ADC/DAC test software OK Connector definition for Power supply OK | Orcad layouts of Flight Model Electronics for DDR Detailed list of command review Definition of Harness pin out ACTEL FGA tools provided (Leonardo). CEA VHDL analysed with success MAC QM1 Board DSP : Arctangent calculations and optical encoder signals acquisition OK |
| 3. Problem Areas | Remedial Action |
| Interface with CEA generic communication FPGA to be validated Size of electronics board to be validated Mechanical and thermal design of the mechanical mountings boards to be validated | Definition of interfaces with CEA : meeting 29/11/2001 |
| 4. Engineering Activities |
| Robust Control control system for digital controller under investigation with SUPELEC |
| 5. Design Changes |
| MCU Boards temperature acquisition under investigation |
| 6. PA/QA Activities |
| PA/QA engineer appointed : Gérard Rousset PA plan for call for tender to be written |
| 7. Subsystem Management Issues |
| / |
| 8. Actions Requiring Immediate Attention |
| MCU Call for tender : under writing. 1st contact with Austrian Aerospace Mechanical and thermal design of the mechanical mountings boards to be validated following visit from Austrian Aerospace |
| 9. Status of Previous Actions |
| / |
| 10. Activities Yet to be Achieved |
| Updating of docs following DDR Tests of MAC QM1 to be completed : EEPROM implementation, Boot mechanism, Encoder interface to be done | List of components : passive parts for Tecnologica SMECm simulator hardware procurement under progress (DSPACE based compact system) SMECm CQM, DM + spare LVDT’s procurement |
| 11. Milestones | Status |
| 01/03/2002 01/09/2002 | MAC QM1 model ready (internal milestone) Delivery of QM1 to CEA/SAp |  |
| 13. Schedule Changes |
| None identified since DDR |

Work Package:	SMECm

| 1. Subsystem Progress Since Project Inception |
| --- |
| Prototypes: GSFC1 and 2 tested with commercial actuator and optical encoder Control loop performances using GSFC prototypes and dSpace done : mechanical modes identified Actuator Specifications written Position sensors Preliminary cryogenic tests on a prototype successful Position sensor with LVDT's investigated : 2 implemented for absolute position and 2 implementable if necessary Launch latch Under design, based on the commercial product |
| 2. Subsystem Progress This Month |
| DDR passed in October STM design finalised Synchronisation device material chosen Actuator specifications written Studies at BE System reinitiated with STM/flight design Test set up for sub components (LVDT and Actuator) in progress – preliminary tests done |
| 3. Problem Areas | Remedial Action |
| Mass allocation insufficient | Action on system team (DDR?) |
| 4. Engineering Activities |
| BE System finite element analysis Lifetests test-setup to be designed |
| 5. Design Changes |
| None |
| 6. PA/QA Activities |
| PA/QA engineer appointed : Gérard Rousset |
| 7. Subsystem Management Issues |
| SMECm subsystem WPs and detailed schedule is to be updated |
| 8. Actions Requiring Immediate Attention |
| Mass budget to be updated (harness) |
| 9. Status of Previous Actions |
| Call for tender postponed till beginning 2002 (no need for the STM and CQM) |
| 10. Activities Yet to be Achieved |
| Pivots to be designed by BE System Prototype actuator and launch latch(es) to be built and tested Flight designed optical encoder to be cryogenically tested LVDT to be tested |
| 11. Milestones | Status |
| June 2002 | SMECm STM delivered to RAL |  |
| 13. Schedule Changes |
| None identified |

Work Package:	Mirrors

| 1. Subsystem Progress Since Project Inception |
| --- |
| Optical design: Frozen Mirror manufacture Successful discussion with MECASEM for optical surface machining. (Minor problems) Alignment tools design Under progress |
| 2. Subsystem Progress This Month |
| Big off-axis mirror prototype manufactured and controlled : undulations detected 3 sets of blanks for the small axi-symetric mirrors done at LAM, except interface finish |
| 3. Problem Areas | Remedial Action |
| Mirror mounting procedure during surface machining | Correction in progress |
| 4. Engineering Activities |
| Manufacturing tool for off axis mirrors to be modified |
| 5. Design Changes |
| None |
| 6. PA/QA Activities |
| PA/QA engineer appointed : Gérard Rousset |
| 7. Subsystem Management Issues |
| Mirrors subsystem WPs and detailed schedule to be updated |
| 8. Actions Requiring Immediate Attention |
| The mounting procedure |
| 9. Status of Previous Actions |
| / |
| 10. Activities Yet to be Achieved |
| Small blanks interface to be finished 3 sets of Off axis and big axi-symetric blanks to be manufactured All mirrors optical surface to be manufactured All mirrors to be cleaned, controlled, bake-outed Alignment tools to be manufactured |
| 11. Milestones | Status |
| 13. Schedule Changes |
| None identified |