Notes on project managers teleconference                       SPIRE-RAL-MOM-001044

3/12/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin | X |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain |  |
| Don Peterson | X |
| Bruce Swinyard |  |
| Ken King | X |
| Dominique Pouliquen | X |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark | X |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |
| Fredericke Pinsard | X |

General

Subsystem reports

IFSI  (Riccardo) – DPU

Not present

CEA Grenoble  (Lionel) – Cooler

All cooler parts inspected and identified.

Parts sent for welding, structure this week.

Development on gold plating has been carried out.  Gold plating will be done out after brazing.

USK. (Don)  - Shutter

ECR in preparation  for no latch indicator, and harness update.

Inputs to structure DDR.

Concerns over high current have been resolved.

Inputs to DDD to Doug.

Finish on shutter vane will be sent to Cardiff.

Cardiff. (Peter)  Filters, calibrators

300mK development continuing, good results of interface tests.

Present samples are not totally representative.

Supports for bus bars nearly ready.

Filter supports are being manufactured for test.

Optics modules ready for shipping to JPL.

ATC  (Ian)  -  BSM

Not present

JPL  (Jerry)  - Detectors

JPL will need to make arrangements for import of  the optics unit from Cardiff.

Identify what filters are needed at JPL, action Jamie.

Fabrication of all BDA parts nearly complete.

Still waiting final harness definition doc, ECS to chase John.

Info on components required from Sap.

Financial problems are being worked on.

MSSL ( Chris) – Structure

DDR held last week, all docs and presentations on web site.

Dichroic mounts in manufacture.

Secondary optics bench to go out for manufacture this week.

LAM.  (Dominique)  - Mirrors, SMEC

Meeting with CEA, DRCU ICD will be regarded as the interface, harness issues discussed, word format finalised.  MCU interface required by LAM.

PA engineer employed.

SAp (Frederick)   -  DRCU

Connectors on DRCU, three 37 way connectors will not fit.

System team to asses and respond to Sap as soon as possible.

RAL,  (Dave) -  AIT

Not present.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |