|  | HERSCHEL SPIRE | Ref: SPIRE-RAL-DOC-001049 Author: D.L. Smith | Page: 1 Issue: 2.0 Date: 08-July-2004 |
| --- | --- | --- | --- |
| SPIRE CQM Instrument Level Test Plan |

| Prepared by: |  |  |
| --- | --- | --- |
|  | D.L. Smith (RAL) | Date |
| Checked: |  |  |
|  | B.M. Swinyard (RAL) | Date |

| Approval: |  |  |
| --- | --- | --- |
|  | E. Sawyer (RAL) | Date |

Distribution

| RAL | Ken King |
| --- | --- |
|  | Eric Sawyer |
|  | Bruce Swinyard |
|  | Eric Clark |
|  | John Delderfield |
|  | Doug Griffin |
|  | Tanya Lim |
|  | Sunil Sidher |
| Cardiff | Matt Griffin (PI) |
|  | Peter Hargrave |
| CEA | Laurent Vigroux (Co-PI) |
|  | Lionel Duband |
|  | Jean-Louis Augueres |
| JPL | Jerry Lillienthal |
|  | Jamie Bock |
| LAM | Dominique Pouliquen |
|  | Kjetel Dohlen |
| MSSL | Berend Winter |
|  | Chris Brockley-Blatt |
| ATC | Ian Pain |
| USK | Don Peterson |
| IFSI | Riccardo Cerulli-Irelli |
|  | Anna Di Giorgio |

| Host system | Windows 2000 SP2 |
| --- | --- |
| Word Processor | Microsoft Word 2000 SR1 |
| File | CQM Test Plan 2.0.Doc |

# Document Change Record

| Date | Index | Affected Pages | Changes |
| --- | --- | --- | --- |
| 11-Jan-2002 | 0.1 | All | First Draft |
| 15-May-2002 | 1.0 | 5 7 9 10, 11 14 | Updates to document list Correction to CQM detector specification Definition of test campaigns and activities Identified inspection points in flowchart Cross references to CQM performance test specification and EMC control plan included |
| 08-July-2004 | 2.0 | All | Updated to reflect changes to actual CQM AIV planning |
|  |  |  | Update to instrument build standard |
|  |  |  | No exchange of detector arrays included |
|  |  |  | Cryogenic vibration test added |
|  |  |  | Modifications to thermal hardware added Resource requirements updated to reflect present SPIRE project setup |

Contents

1	Scope of Document	5

2	Documents	5

2.1	Applicable Documents	5

2.2	Reference Documents	5

3	CQM AIV Requirements	6

3.1	CQM Definition	6

3.2	CQM Qualification Requirements	9

3.2.1	Mechanical	9

3.2.2	Thermal	9

3.2.3	Optical	9

3.2.4	Electrical	9

3.2.5	Performance	9

3.2.6	Operations Modes	10

4	CQM AIV Flowchart	11

5	Task List	15

6	Test Procedure List	19

6.1	CQM structure Mechanical Integration (CQM_ILT_INTG)	19

6.2	CQM Thermal Verification Procedures (CQM_ILT_VER)	19

6.2.1	ILT Thermal Balance Test Procedure (ILT_THER)	19

6.2.2	ILT Performance Test Procedures (ILT_PERF)	19

6.3	Cryogenic Vibration Procedure (CQM_ILT_VIB)	19

6.4	General Procedures	19

6.4.1	Cryostat integration procedures	19

6.4.2	Cryostat operations procedures	19

6.4.3	Contamination Control and Monitoring Procedures	19

6.4.4	ILT Functional Test Procedures	19

7	Organisation	21

8	Resource Requirements	22

8.1	Manpower	22

8.1.1	AIV Team	22

8.1.2	Specialist Support	23

8.1.3	SPIRE Project Team	23

8.1.4	External Support	23

8.2	Facilities	25

8.2.1	Cryogenic Test Facility	25

8.2.2	Assembly Clean Rooms	25

8.2.3	Cryogenic Vibration Facility	25

8.3	EGSE	26

8.4	OGSE	27

8.4.1	Alignment Tools	27

8.4.2	Telescope Simulator	27

8.4.3	Cold Blackbody	27

8.4.4	Fourier Transform Spectrometer	27

8.4.5	Hot Blackbody	27

8.4.6	FIR Laser	27

8.4.7	Beam Monitor	27

8.5	MGSE	28

8.5.1	Transportation Container	28

8.5.2	Integration Frame	28

8.5.3	HOB Simulator	28

8.5.4	Support Trolley	28

# Scope of Document

This document describes in detail how the SPIRE CQM AIV will be implemented.  It describes the step-by-step sequence of activities, high-level procedures, organisation, resources and facilities required.

# Documents

## Applicable Documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| AD 1 | SPIRE Instrument Qualification Requirements | B. Swinyard | SPIRE-RAL-PRJ-000592 Issue 1.1 | 29-Mar-2001 |
| AD 2 | SPIRE Instrument CQM Requirements | B. Swinyard | SPIRE-RAL-NOT-000389 Issue 1.0 | 18-April-2000 |
| AD 3 | Instrument AIV Plan | B. Swinyard | SPIRE-RAL-PRJ-000410 Issue 3D | May 2003 |
| AD 4 | Instrument Integration Plan | B. Winter | SPIRE-MSS-PRJ-000652 Issue 0.1D | Apr-2001 |
| AD 5 | SPIRE Calibration Requirements | B. Swinyard | SPIRE-RAL-PRJ-001064 Issue 0.1D | 3-Jan-2002 |
| AD 6 | SPIRE CQM Performance Test Specification | T. Lim | SPIRE-RAL-DOC-001123 Issue 0.3 | 28-Feb-2002 |
| AD 7 | SPIRE EMC Control Plan | D. Griffin | SPIRE-RAL-PRJ-852 Issue 0.2 | 3-Feb-2002 |
| AD 8 | CQM Thermal Balance Test Specification | A.S.Goizel | SPIRE-RAL-DOC-002077 Draft 3 | 29-Jan-2004 |
| AD 9 | SPIRE Optical Alignment Verification Plan | K. Dohlen | SPIRE-LAM-PRJ-000445 Issue 3 | 10-Apr-2001 |
| AD 10 | SPIRE Product Assurance Plan | D. Kelsh | SPIRE-RAL-PRJ-000017 Issue 1.0 | 11-Apr-2001 |
| AD 11 | Cleanliness Plan | B. Swinyard | SPIRE-RAL-PRJ-001070 Issue 1.0 | 9-Jan-2002 |
| AD 12 | SPIRE Alignment Tools Specification | K. Dohlen, A. Origne | LOOM.YA.SPIRE.2002.001.05 | August 2002 |

## Reference Documents

|  | Title | Author | Reference | Date |
| --- | --- | --- | --- | --- |
| RD 1 | SPIRE STM Instrument Level Test Plan | D.L. Smith | SPIRE-RAL-PRJ-001048 Issue 1.0 | 15-May-2002 |
| RD 2 | SPIRE Test Facility Requirements Specification | D.L. Smith | SPIRE-RAL-PRJ-000463 Issue 1.3 | 2-April-2001 |

# CQM AIV Requirements

## CQM Definition

Figure 1: Flow chart showing the logical association of the SPIRE CQM model within the SPIRE development programme.

| Unit /component | Build Standard |
| --- | --- |
| HSFPU |  |
| Structure/baffles/standoffs etc | STM |
| L0 straps | Either GSE or flight type |
| Mirrors | STM (as used for alignment model) |
| Filters | CFIL-1 – CQM PFIL-2 – CQM PFIL-3 – CQM PDIC-1 – TBD PDIC-2 – TBD Spectrometer filters not fitted |
| Beam steering mirror | STM |
| 3He Cooler | CQM |
| 300 mK thermal straps and supports | CQM |
| 300 mK Thermal control system | Not Fitted |
| Photometer LW array | CQM |
| Photometer MW array | Unsuspended STM |
| Photometer SW array | Unsuspended STM |
| SMEC | STM |
| Spectrometer SW array | Unsuspended STM |
| Spectrometer LW array | Unsuspended STM |
| Photometer Calibrator | CQM |
| Spectrometer Calibrator | CQM |
| FPU RF Filters | CQM |
| Thermometry | CQM |
| FPU internal harnesses | CQM/FS |
| HSJFP |  |
| JFET Structure | CQM/FS |
| JFET Modules | 2 CQM 5 STM |
| JFET box RF filter modules | CQM/FS |
| JFET Backharness | CQM/FS |
| JFET/FPU Harness | Only PLW All others GSE |
| HSJFS |  |
| JFET Structure | CQM/FS |
| JFET Modules | STM |
| JFET box RF filter modules | TBD |
| JFET Backharness | TBD |
| JFET/FPU Harness | TBD |

| Subsystem /component | Requirement |
| --- | --- |
| HSDCU |  |
| DCU Structure | Form and fit |
| Electrical Interfaces | Form; fit and function |
| Functionality | I/F – functional; non redundant DAQ – functional; non redundant Bias-P – functional; non-redundant Bias-S – not required LIA-P – 48 channels functional LIA-S – no requirement |
| Electrical Component Level | Commercial |
| HSFCU |  |
| FCU Structure | Form and fit |
| MCU |  |
| Electrical Interfaces | Form; fit and function |
| Functionality | Back up mode (direct current command) function only |
| Electrical Component Level | Commercial |
| SCU |  |
| Electrical Interfaces | Form; fit and function |
| Functionality | Full functionality but no redundancy required |
| Electrical Component Level | Commercial |
| PSU |  |
| Electrical Interfaces | Form and function Fit desirable – else GSE to be provided |
| Functionality | Full functionality but no redundancy required |
| Electrical Component Level | Commercial |
| HSDPU |  |
| DPU Structure | Form and fit |
| Electrical Interfaces | Form;fit and function |
| Functionality | Full functionality but no redundancy required |
| Electrical Component Level | commercial |
| On Board Software |  |
| Functionality | Full functionality but no autonomy required |
| HSWIH |  |
| Length/Connector type | Form and fit |
| Electrical Interfaces | Form; fit; function |
| Functionality | Full functionality on prime side only |
| Electrical Component Level | Commercial |

The CQM thermal verification tests will be performed with the development model DPU and QM1 DRCU as specified in AD 2.  EMC tests will require the full QM warm electronics.

## CQM Qualification Requirements

The qualification requirements are presented in detail in the SPIRE instrument qualification requirements AD 2 and are summarised below for completeness.

### Mechanical

A qualification level vibration test will be performed on the CQM instrument at cryogenic temperatures to verify the mechanical design of the FPU structure.  The input levels will be defined by MSSL and will be based on those specified in the IIDA.  To confirm that the instrument has survived the qualification levels, optical alignment and thermal performance tests will be performed before and after the vibration test. The proposed sequence will be:

Configure Instrument

Vibration test for each axis

Low-level survey

Sine test

Random test

Low-level survey

Post vibration inspection

Any susceptibility of the detector signals to micro-phonic vibrations will be investigated to verify that the instrument can operate within the Herschel environment, and that the operation of the instruments mechanisms does not affect the performance.

### Thermal

A series of thermal verification tests will be performed to demonstrate that all parts of the instrument will run at the correct temperatures and will function correctly at the predicted environment conditions. The test conditions will be specified in the thermal test plan, AD 8.

### Optical

The CQM mirrors will have been installed and aligned as part of the AM program.  The optical integration will be completed and further alignment checks made.  The CQM will allow the far-infrared and sub-mm optical performance to be characterised, in particular the stray-light performance will be evaluated.

### Electrical

The CQM tests will be the first opportunity to run the SPIRE instrument as a complete system and to test all electrical interfaces.  Throughout the test program, attention will be given to any possible electrical interference from the instrument subsystems on the detector performance with a view to remedying any problems.

An EMC test will be conducted to demonstrate that the proposed method of providing the Faraday cage will be sufficient to protect against radiated EMI in a laboratory environment.  The test will be limited in that the test environment will be very different to the Herschel cryostat.  Conducted susceptibility tests will also be performed.

### Performance

The CQM will allow the scientific performance of the instrument to be tested.  The performance checks will cover:

- Detector performance and characterisation

- Performance and characterisation of the photometer optics

- BSM performance

- Calibrator performance and characterisation

### Operations Modes

The CQM will present an opportunity to evaluate the operations modes of the instrument and test the ground segment concept with ‘real’ instrument data.

# CQM AIV Flowchart

The AIV phase is broken down into a series of ‘activities’ and ‘test campaigns’.

‘Activities’ include integration of the FPU, preparation for a test campaign, single test or task within a campaign and other tasks.

A ‘test campaign’ covers a complete test period from the test readiness review to the completion of the test activities.

Each test campaign will start with a test readiness review, at which all test procedures must be ready and the EGSE configuration will be ‘frozen’.   A formal post-test review will be held at the end of the test campaign after which the instrument can proceed with the next activity.

The test campaign will be broken down into ‘activities’ and ‘tests’, see Figure 2.  Activities include pump-down, cool-down, warm-up, and let-up.  Each ‘Test’ within the campaign will comprise a series of ‘test cases’. For example, a functional test will include test cases to checkout individual mechanisms, i.e. the cooler, BSM, SCAL etc.  The test campaign will be controlled by a master procedure that references the specific test procedures, e.g. functional test procedure.  The test procedure will identify the necessary EGSE test sequences and pass-fail criteria.

Figure 2:  Definition of AIV Phase, Test Campaign, Tests and Test Case.  (Note: the example given does not represent the actual SPIRE AIV)

The flowchart in this section is based on the flowchart presented in the SPIRE AIV Plan (AD 3) but expanded slightly to show each test campaign with the facilities and test equipment required to perform the activities.

Each test campaign will start with a test readiness review, at which all test procedures must be ready and the EGSE configuration will be ‘frozen’.   A formal post-test review will be held at the end of the test campaign after which the instrument can proceed with the next activity.

Figure 3: Legend for CQM AIV Flow Chart. Key Inspection Points are indicated by (K), Mandatory Inspection Points are indicated by (M).

# Task List

The following table defines the step-by-step sequence of activities for the SPIRE CQM AIV.  The table will form the basis of the CQM AIV master procedure.

| Step | Activity | Identifier | Brief Description | Instrument Requirement |
| --- | --- | --- | --- | --- |
| CQM 1 | CQM FPU Integration | CQM_ILT_INTG |  |  |
| CQM 1-1 | Verify alignment of optical components | ILT_ALIGN |  | VRD-06, VRD-07 VRD-10, VRD-11 |
| CQM 1-2 | Photometer detector box integration | DET_INTG | Install fully functional long-wavelength photometer array and thermally and mechanically representative BDAs in the other locations. | VRD-06, VRD-10 VRD-11 |
| CQM 1-3 | Spectrometer detector box integration | DET_INTG | Install fully functional long-wavelength spectrometer array and thermally and mechanically representative BDAs in the short wavelength location. | VRD-06, VRD-10 VRD-11 |
| CQM 1-4 | Detector box integration into FPU structure | ILT_INTG | Integrate detector boxes into structure and verify the alignment. | VRD-06, VRD-10 VRD-11 |
| CQM 1-5 | Subsystem Integration | ILT_INTG | Install instrument subsystems, filters and baffles. | VRD-04, VRD-05 |
| CQM 2 | CQM FTB Integration | CQM_ILT_INTG |  |  |
| CQM 2-1 | Inspect JFET modules on arrival | FTB_INTG | Visual inspection of JFET modules | VRD-04, VRD-05 |
| CQM 2-2 | Mount JFET modules into box structures | FTB_INTG | Integrate JFET Boxes | VRD-04, VRD-05 |
| CQM 2-3 | Perform warm functional test | FTB_WFT | Check function of JFET modules at room temperature. | VRD-24 |
| CQM 3 | CQM FPU/FTB Integration | CQM_ILT_INTG |  |  |
| CQM 3-1 | Mount JFET Boxes on HOB simulator and connect to FPU | CQM_ILT_INTG |  | VRD-04, VRD-05 |
| CQM 3-2 | Connect to Warm Electronics units | CQM_ILT_INTG |  | VRD-04, VRD-05 |
| CQM 3-3 | Perform warm functional test | ILT_WFT |  | VRD-21, VRD-24 VRD-27, VRD-28 VRD-29 |
| CQM 3-4 | Perform optical alignment check | ILT_ALIGN |  | VRD-06, VRD-07 VRD-10, VRD-11 |
| CQM 4 | CQM Cold Thermal Verification - 1 | CQM_ILT_VER |  |  |
| CQM 4-1 | Integrate SPIRE onto support frame | CQM_ILT_INTG | Bolt down covers, secure structure to HOB simulator. Lift instrument onto MGSE and build up support frame. |  |
| CQM 4-2 | Transfer SPIRE to Cryolab | CQM_ILT_INTG | Bag up the FPU and HOB simulator and transfer to cryolab. |  |
| CQM-4-3 | Integrate SPIRE into cryostat | CRY_INTG | Move instrument into cryostat, connect thermal straps, harness. Close up radiation shields, making light tight. |  |
| CQM-4-4 | Perform warm functional test - includes redundancy tests | ILT_WFT |  | VRD-21, VRD-24 VRD-27, VRD-28 VRD-29 |
| CQM-4-5 | Test Readiness Review |  |  |  |
| CQM-4-6 | Pump Down | CRY_PUMP |  |  |
| CQM-4-7 | Cool Down to operational temperatures | CRY_COOL |  | VRD-12, VRD-14 |
| CQM-4-8 | Perform cold functional tests - includes redundancy tests | ILT_CFFT |  | VRD-16, VRD-17 VRD-21, VRD-24 VRD-27 to 42 |
| CQM-4-9 | Verify thermal performance | CQM_ILT_THER |  | VRD-12, VRD-14 |
| CQM-4-10 | Measure optical alignment | CQM_ILT_ALIGN |  | VRD-06, VRD-07 VRD-10, VRD-11 |
| CQM-4-11 | Perform cold functional tests - includes redundancy tests | ILT_CFFT |  | VRD-16, VRD-17 VRD-21, VRD-24 VRD-27 to 42 |
| CQM-4-12 | Post Test Review |  |  |  |
| CQM-4-13 | Warm up | CRY_WARM |  |  |
| CQM-4-14 | Let up to air | CRY_LETUP |  |  |
| CQM-4-15 | Perform warm functional test | ILT_WFT |  | VRD-21, VRD-24 VRD-27, VRD-28 VRD-29 |
| CQM-4-16 | Remove from cryostat | CRY_DEINT | Disconnect FPU from cryostat, remove HOB simulator from cryostat and install on MGSE. |  |
| CQM-5 | CQM Cold Vibration | CQM_ILT_VIB |  |  |
| CQM-5-1 | Prepare SPIRE for shipping to CSL | CQM_ILT_INTG | Bag up the FPU and HOB simulator and transfer to cryolab. Remove from support frame and lift into transport container. |  |
| CQM-5-2 | Ship to CSL |  |  |  |
| CQM-5-3 | Unpack SPIRE and inspect on arrival at CSL | ILT_INSP | Visual inspection of the SPIRE structure following transportation. | VRD-10 |
| CQM-5-4 | Transfer SPIRE to vibration rig | CQM_ILT_INTG | Transfer FPU to vibration fixture. |  |
| CQM-5-5 | Test Readiness Review |  |  |  |
| CQM-5-6 | Perform vibration tests | CQM_ILT_VIB CSL_VIB | 3 axis vibration of FPU structure at cryogenic temperatures. | VRD-01 VRD-02 |
| CQM-5-7 | Inspect structural integrity | ILT_INSP | Visual inspection of the SPIRE structure following vibration test. | VRD-02 |
| CQM-5-8 | Post test review |  |  |  |
| CQM-5-9 | Prepare SPIRE for shipping to RAL | CQM_ILT_INTG | Remove from vibration fixture and install into transportation container on HOB simulator. |  |
| CQM-5-10 | Ship to RAL |  |  |  |
| CQM-5-11 | Unpack SPIRE and inspect on arrival at RAL | ILT_INSP | Perform detailed inspection of the SPIRE instrument following vibration test | VRD-02, VRD-10 |
| CQM-6 | Reconfigure Thermal Architecture | CQM_ILT_INTG |  |  |
| CQM 6-1 | Remove STM thermal hardware | CQM_ILT_INTG |  |  |
| CQM-6-2 | Integrate CQM thermal hardware | CQM_ILT_INTG | Replace MK1 300mK, 1.7K and 4K thermal links with improved design. |  |
| CQM-7 | CQM Cold Thermal Verification - 2 | CQM_ILT_VER |  |  |
| CQM-7-1 | Integrate SPIRE onto support frame | CQM_ILT_INTG | Bolt down covers, secure structure to HOB simulator. Lift instrument onto MGSE and build up support frame. |  |
| CQM-7-2 | Transfer SPIRE to Cryolab | CQM_ILT_INTG | Bag up the FPU and HOB simulator and transfer to cryolab. |  |
| CQM-7-3 | Integrate SPIRE into cryostat | CRY_INTG | Move instrument into cryostat, connect thermal straps, harness. Close up radiation shields, making light tight. |  |
| CQM-7-4 | Perform warm functional test | ILT_WFT |  | VRD-21, 24, 27, 28, 29 |
| CQM-7-5 | Test Readiness Review |  |  |  |
| CQM-7-6 | Pump Down | CRY_PUMP |  |  |
| CQM-7-7 | Cool Down to operational temperatures | CRY_COOL |  | VRD-12, VRD-14 |
| CQM-7-8 | Perform cold functional tests - includes redundancy tests | ILT_CFFT |  | VRD-16, 17, 21, 24, 27 - 42 |
| CQM-7-9 | Verify thermal performance | ILT_THER |  | VRD-12, VRD-14 |
| CQM-7-10 | Micro phonics Susceptibility | ILT_PERF | Measure susceptibility of detector signals to low-level vibration inputs. | VRD-15 |
| CQM-7-11 | Cold EMC Tests | ILT_EMC | Conducted susceptibility AD 7 | VRD-23, VRD-25 VRD-26 |
| CQM-7-12 | Measure instrument performance characteristics | ILT_PERF | Detector performance and characterization Photometer optics characterization, spectrometer performance, BSM performance, Calibrator performance and characterization (Defined in AD 6) | VRD-06, 07, 08, 09, 11, 12, 15, 16, 17, 18, 19, 20, 22, 24, 25, 27, 28, 29, 30, 43-49 |
| CQM-7-13 | Perform cold functional tests - includes redundancy tests | ILT_CFFT |  | VRD-16, 17, 21, 24, 27 - 42 |
| CQM-7-14 | Post Test Review |  |  |  |
| CQM-7-15 | Warm up | CRY_WARM |  |  |
| CQM-7-16 | Let up to air | CRY_LETUP |  |  |
| CQM-7-17 | Perform warm functional test | ILT_WFT |  | VRD-21, 24, 27, 28, 29 |
| CQM-7-18 | Remove from cryostat | CRY_DEINT | Disconnect FPU from cryostat, remove HOB simulator from cryostat and install on support trolley. |  |
| CQM-8 | CQM Delivery to ESA |  |  |  |
| CQM-8-1 | Prepare SPIRE for shipping to ESA |  |  |  |
| CQM-8-2 | Pre-delivery review |  |  |  |
| CQM-8-3 | Ship to ESA |  |  |  |
| CQM-8-4 | Unpack SPIRE and inspect on arrival at ESA |  |  |  |
| CQM-8-5 | Perform warm functional test | ILT_WFT |  | VRD-21, 24, 27, 28, 29 |
| CQM-8-6 | Acceptance review |  |  |  |

# Test Procedure List

This section lists the main test procedures to be used for the CQM AIV.  For each major step there is a high level procedure that references other standard procedures such as those for operating the facilities.

## CQM structure Mechanical Integration (CQM_ILT_INTG)

This procedure will describe the integration of the CQM subsystems into the instrument (ILT_ALIGN), and preparation of the instrument for thermal verification and delivery to ESTEC.  The mechanical integration will also include optical alignment checks (ILT_ALIGN).

## CQM Thermal Verification Procedures (CQM_ILT_VER)

Master procedure for cold thermal verification tests 1 and 2 .  The procedure will call up sub-procedures for specific test activities, i.e. thermal performance, instrument performance, calibration and operating mode tests.

### ILT Thermal Balance Test Procedure (ILT_THER)

This procedure will define all instrument level thermal performance tests.  The procedure will define the test conditions, all instrument operations to be performed (e.g. cooler recycling), data analysis and all success/failure criteria.

### ILT Performance Test Procedures (ILT_PERF)

This procedure will describe all instrument performance tests to be performed during cold thermal verification.  The procedure will define the EGSE test scripts, data analysis, test conditions, all instrument operations and all success/failure criteria.

## Cryogenic Vibration Procedure (CQM_ILT_VIB)

The procedure will be based on the cryogenic vibration test plan and will define the input levels, the instrument functional tests, optical alignment checks and all success failure criteria.

## General Procedures

The following are more general procedures that will be called up by the main test procedures.

### Cryostat integration procedures

SPIRE test facility procedure describing the steps to prepare and install SPIRE into the test cryostat (CRY_INT) and removal of SPIRE from the test cryostat (CRY_DEINT)

### Cryostat operations procedures

This will be a set facility procedures describing the safe operation of the calibration cryostat. The procedures will cover the sequence for pumping down (CRY_PUMP), cryogenic cool-down (CRY_COOL), operation at test conditions, warm-up (CRY_WARM) and let-up to air (CRY_LETUP).

### Contamination Control and Monitoring Procedures

These define how the contamination control process is to be implemented and describes the process to monitor the contamination levels in the facility during integration.

### ILT Functional Test Procedures

To ensure that the instrument subsystems are performing correctly, functional tests will be executed at the various stages of the AIV phase.  The test procedures will identify the EGSE test scripts that are to be used, the instrument configuration and all success criteria.  The following test levels are proposed:

#### Warm Functional Test (ILT_WFT)

#### This will be a basic test performed at room temperature to check the integrity of the electrical interfaces.

#### Cold Full Functional Test (ILT_CFFT)

An end-to-end test verifying all instrument subsystem functions will be exercised and where applicable will be repeated for redundant units.  This test will be performed during the cold verification campaigns.

#### Cold Short Functional Test (ILT_CSFT)

The minimum level of tests required for checking that the instrument subsystems are functioning correctly.

# Organisation

Figure 4: CQM AIV Organisation

# Resource Requirements

## Manpower

This section describes the roles and responsibilities of the personnel required to support the CQM integration and test activities.  The roles defined are specific to the CQM AIV activities and do not necessarily reflect overall roles and responsibilities within the SPIRE project.  The majority of the team will be from RAL, but specialists from the SPIRE subsystem providers will also be required to support the AIV activities.

### AIV Team

#### AIV Manager

- Planning and coordinating the AIV verification tests and calibration.

- Responsible for obtaining agreement, prior to the commencement of any activity, of test plans and procedures.

- Responsible for decisions requiring work-around plans, modification of test procedures, repeat tests etc arising from non-conformance reports.

- Co-ordinate activities of technical experts, technicians during AIV testing.

- Reports to Instrument Development Manager

#### Calibration Scientist

- Definition of the instrument calibration, performance and operations modes tests.

- Preparation analysis software

- Execution of calibration tasks

- Real-time assessment of the test results using QLA

- Detailed analysis of test data.

- Preparation of calibration report.

- Preparation of the instrument calibration database and associated documentation.

#### Instrument Specialist

- Preparation of instrument test sequences on EGSE

- Execution and analysis of instrument functional tests

- Maintenance and development of EGSE

- On-board software maintenance

- Definition of instrument flight operations procedures

#### Cryostat Engineer

- Preparation of cryostat for instrument tests

- Operation of cryostat during instrument tests

- Ensure supply of cryogens

- Clean room maintenance

#### Technicians

- Mechanical integration of instrument

- Test support

- Preparation of instrument for testing and transport

### Specialist Support

#### Optics Specialist

- Optical alignment verification

#### Thermal Engineer

- Thermal modeling and analysis

- Thermal test plan

- Support for thermal testing.

### SPIRE Project Team

#### SPIRE Project Manager

- SPIRE Project Management

- UK SPIRE Management

#### Instrument Development Manager

- Subsystem Development

- Subsystem Deliveries

- Instrument Deliveries

- PFM integration management

#### Instrument Scientist

- Instrument performance

- Verification Matrix

- Calibration Plan

- Optical Straylight Analysis

#### Systems Engineer

- Systems engineering

- System thermal design

- Parts procurement

#### PA Manager

- Product assurance

- Quality assurance

- Acceptance data packages

### External Support

Support from the instrument subsystem providers will be required during the AIV activities.  They will not be expected to perform the integration tasks but rather be on hand to provide technical support when needed.

#### MSSL

- Support mechanical integration.

#### LAM

- Support optical alignment activities.

- Support the integration and testing of the SMEC.

#### Cardiff

- Support integration of the SCAL, PCAL, 300mK strap system, optical filters

- Support the cold thermal verification and instrument performance tests.

#### JPL

- Support integration and alignment of detector modules, and integration of JFET units.

#### ATC

- Support integration and testing of the BSM units.

#### Grenoble

- Support integration of the cooler systems and thermal verification tests.

#### UofL

- Setup and operation of the SPIRE test equipment

- Maintenance of TFTS system

- Support instrument test activities

- Preparation of test sequences to be run on EGSE

- Support of EGSE and Warm Electronics Testing

## Facilities

The following facilities will be used for the SPIRE CQM AIV activities.

### Cryogenic Test Facility

The SPIRE dedicated cryostat facility will be used for the cold optical alignment and thermal verification tests [RD 2]. The instrument and cryostat will be in a class 1000 clean area.  Access to the clean room will be limited to key personnel to minimise any potential contamination of the optics.

### Assembly Clean Rooms

Mechanical and electrical integration of the SPIRE FPU will be conducted in Clean Room 2 within building R25 at RAL.  The room comprises

- Main area: 12m x 7m class 10,000

- Horizontal laminar flow unit: 5m x 3m at class 100

- 2 laminar flowbenches: 1m x 0.5m at class 100

- Central changing room: lockers for up to 20 people

- Cleaning facility: Ultrasonic bath, fume cupboards

### Cryogenic Vibration Facility

The SPIRE CQM Instrument will be vibrated at cryogenic temperatures at the CSL facility.

## EGSE

The full EGSE-ILT configuration will be required for the CQM test campaign, Figure 5.  The main components that are required are: -

- TFCS

- TFTS

- CDMS simulator

- Packet Router

- SCOS-2000

- Test Control

- RTA

- MIB

- HCSS

- QLA

- OBSM

Figure 5: EGSE-ILT Configuration

At the start of each test campaign (e.g. Thermal Verification), the EGSE configuration will be ‘frozen’ and will be run continuously until the completion of the test campaign, i.e. when the cryostat has fully warmed up.  The only breaks in operation will be for routine maintenance or troubleshooting as agreed by the AIV manager. All changes to the EGSE configuration shall be through a formal change request to ensure that any changes do not have any negative impact on the test campaign. Changes to the EGSE configuration that are not essential to the success of the test campaign may have wait before implementation. The main priority throughout the test campaign will be the safety of the instrument, and it is therefore vital that the thermal environment and instrument status is monitored and logged continuously.

## OGSE

### Alignment Tools

A Suite of dedicated alignment tools will be provided by LAM as defined in AD 12.

### Telescope Simulator

The telescope simulator will reproduce the Herschel telescope f8.68 beam, such that a point source is imaged at the SPIRE input focal plane. Many of the test & calibration procedures will require this beam to be steered & focused over the field-of-view range of the instrument, in order to check or measure such properties as pixel response, spatial resolution and image scale.  A beam control system will use a series of movable mirrors to steer & focus the beam according to geometric 'control laws'.

### Cold Blackbody

A 4K-20K-blackbody source provided by Cardiff University will be used as an absolute radiance standard.  This will be mounted within the 4K enclosure of the cryostat and viewed via a relay mirror.

### Fourier Transform Spectrometer

The Test Fourier Transform Spectrometer (TFTS) provided by University of Lethbridge, Canada will allow the spectral response measurements to be performed

### Hot Blackbody

An ISOTEC Pegasus hot, 1000°C blackbody with wavelength coverage over 200µm to 700µm will be used to back illuminate a point source at the input of the telescope simulator.

### FIR Laser

An Edinburgh Instruments PR5 gas FIR laser with lines from 30µm to 1000µm and power up to 100mW will be used.

### Beam Monitor

The output of the telescope simulator (i.e. input signal to SPIRE) will be picked off by a beam splitter and measured using a Golay cell. The output of the detector will be logged by the TFCS to allow correlation with the SPIRE measurements.

## MGSE

### Transportation Container

A purpose built transportation container provided by MSSL will be used whenever SPIRE is to be moved between facilities (i.e MSSL, RAL, CSL, ESTEC).

### Integration Frame

A framework provided by MSSL mounted on the HOB simulator will be used to support the SPIRE FPU during integration.

### HOB Simulator

The HOB simulator will be the primary mechanical interface between the SPIRE FPU and the calibration cryostat.  It will have a number of optical references to enable optical alignment measurements to be performed.   To ensure that optical alignment between the references on the SPIRE optical bench and the HOB are maintained throughout integration and testing, the HOB simulator will act as the main integration plate and will travel with the instrument in the transportation container.

### Support Trolley

SPIRE will be mounted on the HOB simulator with the +X axis up during mechanical integration and transport.  However, because the SMEC cannot work against gravity the instrument has to be rotated by 90° so that the +Y axis is up.  A purpose built support trolley will be provided to rotate the integrated FPU and JFET units on the HOB simulator about 90° in a controlled manner.  The trolley will also allow the instrument to be moved between the AIV clean rooms and the cryogenic test facility.

# Footnotes

Extracted from RAL document ISO9:SPAP/AIV/000