# Minutes of SPIRE Project Team Meeting 17

# SPIRE-RAL-MOM-000???

# RAL 15 October  2001

# Present:      Matt Griffin, Eric Sawyer, Bruce Swinyard, Peter Hargrave, Berend Winter, Ken King

Topics.

IBDR preparations

# Review of outstanding actions from previous meetings

| No. PT-04-0570 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | KJK | Write WE integration and test plan | High | Oct. 2001 | Still Open. Needed for IBDR. |

| No. PT-10-0682 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 04 | MJG | Arrange for QMW to evaluate filter suppression. | Medium | May 31 | Open, not yet documented in the SSRD |

| No. PT-12-0726 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 02 | EC KJK | Update the document management plan to reflect the new scheme for interaction of institute PMs with the documentation configuration control system. |  | June 29 | Still open, action being taken This is an action on Ken |

| No. PT-13-0772 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 04 | BMS DKG | Bruce and Doug to talk to John and distribute a draft list of documents showing approval status. |  | 3/8/01 | In progress |
| 06 | MJG | Matt to meet with Ken to discuss the outstanding MOUs |  | 3/8/01 | Open, Matt to have at least a contents list ready for Ken’s return. |
| 07 | DKG JD | Check scope for increasing the thermal load on the detector box JD to look at the fraction of the 2-K load that is due to the 2-K box |  | 27/7/01 | Closed, |
| 11 | ECS | Outline new document scheme to the consortium |  |  | Open, check new proposals, and circulate note. |
| 12 | KJK | Ask for copy of PACS MOU |  | 31/7/01 | closed |
| 13 | ECS | Seek confirmation of DDR dates |  | 27/7/01 | Open, Structure and DPU not finalised |

| No. PT-14-0797 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 03 | Peter Hargrave | define detector filter and incorporate into the filter ICD. |  | This to be defined before the BDA review. | Closed, ICDs to be formally signed off. |

| No. PT-15-0824 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | MJG | Combine Matt and Kens comments on partnership agreement and send to Alcatel |  | 12/9/01 | closed |
| 02 | ECS | Review product tree |  | 12/9/01 | Open |
| 05 | ECS | ES to let JB know that current version of the DDD is not to be updated until the IBDR. |  | 30/8/01 | Open |
| 07 | BMS DG | Circulate first DDR draft report and amend as a result of the wrap up review. |  | 21/8/01, stage 1 30/8/01, stage 2 | closed |
| 10 | MJG | Matt to contact CEA regarding lack of contact recently. |  | 30/8/01 | closed |
| 12 | BMS JD | Produce a list of critical information that’s ill-defined or incomplete in the IID-A and IID-B that we need to know about before holding the IBDR. |  | 30/8/01 | Done for B |

Actions raised during this meeting

| No. PT-16-0862 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | DG | Doug to inform consortium that 1030 Cernox is the baseline temperature sensor |  | 20/9/01 | Open |
| 02 | BMS | RAL (Bruce) to write a DRCU reliability spec at the channel level which also defines a failure. |  | 20/9/01 | Open |
| 03 | MJG | Investigate supply by Cardiff, of equipment to measure cooler temperatures in the absence of a DRCU |  | 20/9/01 | Closed, available on request with the appropriate planning |
| 04 | ECS | Send costs of cold vibration tests to LAM and CEA. |  | 30/9/01 | Open |
| 05 | JD | Investigate pumpdown time before cooling at spacecraft level. |  | 30/9/01 | closed |
| 06 | ECS | DRCU, FM harness is not shown in the milestone list, check it in the deliverable list. |  | 30/9/01 | Closed, yes |
| 07 | SH | Thermal model required by CEA. Sam to send cooler model to Lionel |  | 30/9/01 | It is a big job to extract the cooler from the overall SPIRE model and could not be started for at least 2 months. The information is contained within SPIRE-RAL-PRJ-000560 |
| 08 | CEA/ SAp | CEA to check when harness information is required. |  | 30/9/01 | Open |
| 09 | RAL | FPU simulator, RAL to check if there is a requirement for a delivery of two units. |  | 30/9/01 | Closed, we need two, CEA to be informed. |
| 10 | RAL | Warm interconnect harness. (DRCU to DPU) One delivered with QM1, is another harness required for QM2? RAL to clarify |  | 30/9/01 | Open |
| 11 | BMS | Put on Livelink The version of the BDA SSSD, taken by Matt from JPL |  | 30/9/01 | Open |
| 12 | MG | Set up telecon with JPL week 17/9/01, Sap are invited |  | 17/9/01 | Closed |
| 13 | ECS | Investigate making PM telecons more effective. |  | 30/9/01 | Closed. Telecons will continue as a quick (~30 min) forum for managers to raise important issues and make contact with each other and the Project Team. The PI regards JPL and CEA participation as particularly important. |
| 14 | ECS | ECS to propose review panel members for warm electronics DDR. Date 10 and 11 December proposed |  | 15/10/01 | Closed |
| 14 | MSSL | MSSL to update schedule and identify milestones, before the meeting on 25th. |  | 24/9/01 | Closed |
| 15 | SAp | Provide provisional mass breakdown for the meeting on 25/9/01 |  | 24/9/01 | Open |
| 16 | MJG | Clarify with KJK when the ICC workpackages will be defined |  | 30/9/01 | Open |
| 17 | JD | Check general robustness of P/LW photometer array and take this into account in harness partitioning |  |  | Open |

# Project Management Issues

## IBDR preparations

Proposed dates for the IBDR (the next major project review in front of ESA) are March 5, 6.  Venue RAL (TBC).  SPIRE's will be the last of the five Hershel/Planck instrument IBDRs.

ESA have proposed a format and set of objectives which has been modified following our comments.

Action:  MJG to draft a proposed set of documents and draft agenda.  This will be iterated and agreed by MJG, KJK, ECS and BMS before being distributed to the consortium.

## Management Reporting and Control

Arrangements for management of the DCU development programme are being drawn up by SAp and JPL.

## Document change and configuration control

## PA

## Business Agreements

## Schedule:

# Instrument Issues

## Structure

## Mirrors

## Detectors

## OBS and Instrument Control

## DPU

## DRCU and related issues (Sap)

# ICC Issues

# Meetings:

## Detailed design Reviews

### DDR summary

- Mirrors:						Complete

- FTS:								22/23 Nov 2001.

- DRCU/WIH 				10/11 December.

- Structure/thermal straps 			29 Nov 2001

- DPU:  						Not decided yet, aim for Nov

- AIV							6/9/01, delta review required, to include egse.

- EGSE:				 		TBD, see above

- BDAs:/JFETs				Complete

- Filters/calibs:				18/9/01,Complete

- BSM: 						30/7/01 not all issues closed out, delta review on 23/8/01, complete

- OBS							Requirements review required. Probably Nov

- Shutter PDR: 				July 17,  Almost a DDR, some aspects still open.

- Cooler						Complete, some RIDs to be signed off.

- DRCU simulator			TBD, awaiting spec from Sap.

IBDR

# Progress on Open Issues

# AOB

Next meeting