Notes on project managers teleconference                       SPIRE-RAL-MOM-001056

10/12/2001

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter | X |
| Chris Brockley-Blatt |  |
| Matt Griffin | X |
| Peter Hargrave |  |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain | X |
| Don Peterson | X |
| Bruce Swinyard | X |
| Ken King | X |
| Dominique Pouliquen | X |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith | X |
| Eric Clark | X |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |
| Fredericke Pinsard |  |

General

IBDR preparation

DDr documentation to be updated

Subsystem reports

IFSI  (Riccardo) – DPU

Not present

CEA Grenoble  (Lionel) – Cooler

Parts sent for welding, structure last week.

Development on gold plating has been carried out.  Gold plating will be done out after brazing.

Contamination budget is defined by ESA, plan is being written. Requirements will not be stringent.

USK. (Don)  - Shutter

No news to report

Cardiff. (Peter)  Filters, calibrators

Not present

ATC  (Ian)  -  BSM

Lab movements causing delays on prototype activities.

Flex pivot meeting held, awaiting costs.

FEA quote received, too expensive.

Similink work continuing.

Aluminium coils planned by Zeiss

PCAL interface rotated.

JPL  (Jerry)  - Detectors

Assembly of QM started.

CQM to start soon.

Bolometers being fabricated, due 11/1/02.

7 bolometer runs planned, each of 3 years

Harness definition is still outstanding.

Drawings to be released next week.

Orientation of arrays, JPL to check if this is possible (FM and FS only)

MSSL ( Chris) – Structure

(Report supplied)

Both the harness and the photometer 2K box detailing continue to progress

Detailing of Photometer cover and entry baffle underway

Secondary Optical bench has been ordered from Thrust engineering

Manufacture of the Dichroic mounts is in progress

Received quote for mirror mounts and hoping to get manufacture underway by 12 December

Documentation required for IBDR in progress, ETA 15 December.

LAM.  (Dominique)  - Mirrors, SMEC

BE systems analysis due.

STM design complete

Two actuator prototypes available next April.

Harness 130gms/m

Length of harness required, requirement for backshells open.

BSM interface may be one connector for prime and redundant, Two cards may be requested from SAP.

Rooftop vs corner cubes to be assessed by LAM.

SAp (Frederick)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Cryostat work progressing.

Details of cold link interfaces  required from MSSL.

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |