# Minutes of SPIRE Project Team Meeting 20

# SPIRE-RAL-MOM-001062

# RAL 19 December 2001

# Present:      Matt Griffin, Eric Sawyer, Bruce Swinyard, Ken King, Berend Winter, John Delderfield (part time)

Topics.

IBDR preparations

JPL activities

ICC meeting

# Review of outstanding actions from previous meetings

| No. PT-04-0570 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | KJK | Write WE integration and test plan | High | Oct. 2001 | Still Open. Needed for IBDR. In progress |

| No. PT-10-0682 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 04 | MJG | Arrange for QMW to evaluate filter suppression. | Medium | May 31 | Closed, Matt to send Bruce correct version of note |

| No. PT-12-0726 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 02 | EC KJK | Update the document management plan to reflect the new scheme for interaction of institute PMs with the documentation configuration control system. |  | June 29 | Still open, action being taken This is an action on Ken |

| No. PT-13-0772 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 04 | BMS DKG | Bruce and Doug to talk to John and distribute a draft list of documents showing approval status. |  | 3/8/01 | closed |
| 06 | MJG | Matt to meet with Ken to discuss the outstanding MOUs |  | 3/8/01 | Open. JPL, in progress Canada, draft proposed Others, no progress |
| 11 | ECS | Outline new document scheme to the consortium |  |  | Closed |

| No. PT-15-0824 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 02 | ECS | Review product tree |  | 12/9/01 | Open |

| No. PT-16-0862 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 01 | DG | Doug to inform consortium that 1030 Cernox is the baseline temperature sensor |  | 20/9/01 | Closed |
| 02 | BMS | RAL (Bruce) to write a DRCU reliability spec at the channel level which also defines a failure. |  | 20/9/01 | Closed |
| 04 | ECS | Send costs of cold vibration tests to LAM and CEA. +JPL |  | 30/9/01 | Open |
| 08 | CEA/ SAp | CEA to check when harness information is required. |  | 30/9/01 | Closed |
| 10 | RAL | Warm interconnect harness. (DRCU to DPU) One delivered with QM1, is another harness required for QM2? RAL to clarify |  | 30/9/01 | Closed, Two required |
| 11 | BMS | Put on Livelink The version of the BDA SSSD, taken by Matt from JPL |  | 30/9/01 | Open |
| 15 | SAp | Provide provisional mass breakdown for the meeting on 25/9/01 |  | 24/9/01 | Open |
| 16 | MJG | Clarify with KJK when the ICC workpackages will be defined |  | 30/9/01 | Open, will be available end Jan |
| 17 | JD | Check general robustness of P/LW photometer array and take this into account in harness partitioning |  |  | Closed, Included in latest interface definition doc. |

| No. PT-19-1060 | Actionee | Description | Priority | Deadline | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | ECS | Define the build standard of all STM subsystems. |  |  | Open |

# Project Management Issues

## IBDR preparations

Preparation workshop planned for Friday 4 Jan at RAL.

DOCUMENT STATUS

| No. and Priority | Document | Responsible | Current Status | Plan |
| --- | --- | --- | --- | --- |
| Top-level requirements documents |
| 1 P3 | Science requirements document | Matt | No significant update planned. |  |
| 2 P2 | Instrument Requirements Document | Bruce + Matt | Needs various updates. To be done by ECRs. | ECRs issued, doc not updated yet Finalise by: Jan 18 Matt and Ken to sign. All subsystem managers must also sign. |
| 3 P1 | Calibration Requirements Document | Bruce + Matt | Being written. | Part complete, Draft by 20 Dec Finalise by: Jan. 18 |
| Instrument Design Description and Development Plan |
| 4 P2 | SPIRE Design Description Document | Doug (+ Bruce and Matt) | To be updated following DDRs (just basic updates) | Send Sap a word version to update. Matt to update over Christmas. Doug to send Matt a word version. DDR docs to be put on CDs Finalise by: Jan. 18 |
| 5 P1 | Instrument Development Plan | Ken/Eric | To be updated. Will be in the same format as for the IIDR. | Review by: Jan. 18 |
| 6 P2 | EMC control plan. | Doug | Draft exists. Being reviewed by ESA. Frequency plan needs to be incorporated. | Frequency plan now available from SAP. Finalise by: Jan. 18 |

| IID-B and related documents |
| --- |
| 7 P3 | IID-B | John D. | Under Alcatel control - we’ll provide status report and list of important items/issues from our point of view. | Maintain document through normal work with ESA/Alcatel ECS contact ESA to clarify position. |
| 8 P2 | Thermal Model | Sam | To be updated based on latest available information at end of November. | No cryostat model available yet Thermal model will not be updated for the IBDR documentation. |
| 9 P1 | FPU Mechanical Model | Berend | To be produced | Will be produced by MSSL 18 Jan |
| 10 P3 | Harness Definition Document | John D. | Exists. Minor revisions possible. | Keep updated and present the latest version. JD to confirm JPL interface, this is ongoing. Confirmation from SAP required. Layout required from MSSL, target 8/1/02. Check status of RAL supplied harness. Temperature sensor location to be defined. |
| 11 P2 | Stray light model | Tony R. | To be updated. Inputs expected from ASEF. Input needed from ASED (but not expected). | Use existing model/report do not wait for updates from ASEF and ASED. |
| 12 P1 | Budgets spreadsheets | Doug | To be updated after DRCU review. | Info from DRCU is now available. Keep updated (JD) and present the latest version as of info from Dec. 20. |
| 13 P2 | Optical error budget | Kjetil | New version exists | To be reviewed by Bruce. Finalise by Jan 18. |
| On-Board Software |
| 14 P1 | OBS URD | Anna | Exists. Won’t be updated. | There will be unclosed change requests. |
| 15 P1 | OBS Architectural Design | Riccardo | In progress. IFSI need to produce some additional technical notes. Ken to liase with Riccardo. | To be finalised at OBS DDR (Dec. 6, 7) A note has been written, but needs refining into a proper document. Comments to DDR presentation to be sent to IFSI by Ken. Matt to contact Renato and Paulo expressing our concern about progress of docs. Still open needs progressing, Ken to draft. |
| 16 P2 | Operating Modes Document | Bruce, Matt, Sunil | To be updated. Needs a 1-day meeting between Matt, Bruce, Sunil. | Meeting: Dec. 3 held. Draft. By Dec. 20 Finalise by: Jan. 15 Note on parallel mode to be written by Matt Target after Christmas, a further review will be required. |
| 17 P3 | Operating the Instrument Document | Sunil | In progress. Needs DRCU ICD. Not high priority for IBDR. | Draft: Dec. 10 Finalise by: Jan. 18 Use whatever is available at the time of the IBDR |
| 18 P1 | SPIRE Data ICD | Ken | To be written. Needs DRCU ICD for completion. | Draft: Dec. 20 Finalise by: Jan. 18 Info from SAP received, iterations required. Draft version partly completed, only a draft will be available for the IBDR |
| AIV Plan |
| 19 P1 | Warm Electronics integration plan | Ken and Eric | Scope to be discussed by Eric and Ken. Document to be written by Eric. | Finalise by: Jan. 18 |
| 20 P1 | FPU integration plan | Berend | To be written | New version dated 21/12/01 available, some extra info required, but its almost good enough. |
| 21 P2 | Alignment Plan and Alignment Procedures | Kjetil | Docs. being reviewed. | Alignment plan complete to be checked by Bruce. Alignment procedure, use what exists at the time of the review. |
| 22 P1 | Instrument-Level Test Plan | Dave Smith | Being written. | Finalise by: Jan. 18 ECS to chase Dave. |
| 23 P3 | Manufacturing Flow Chart | Dave Smith | We assume that this is at instrument level. May be incorporated in AIV Plan. | Finalise by Dec. 10 |
| GSE |
| 24 P1 | GSE Overview | Ken/Bruce | Brief overview with pointers to DDR data packs for the details. May be incorporated into the AIV plan. | Draft: Dec. 20 Finalise: Jan 15 |

| PA |
| --- |
| 25 P1 | FMECA | Bruce | Subsystem DDRs include FMECAs. Instrument-level FMECA to be based on * key results of subsystem FMECAs * analysis of harness/end-to-end channel redundancy * scientific impact of failure modes | Draft by: Jan. 18 Finalise by: Jan. 28. Bruce to tackle top level analysis in Jan Clarification received from ESA Top level only will be done for IBDR documentation, further progress before March, consider extra effort from outside the system team e.g. contractor. |
| 26 P3 | Worst Case Analysis | Bruce/Matt | Warm Electronics DDRs should include this. DDRs to do it. Clarification has been requested on what is required at instrument level. | TBD. May have to wait until January. Matt to do top level analysis based on instrument sensitivity. |
| 27 P3 | HW/SW interaction analysis | Ken | To be written (control loops?). Clarification has been requested. on what is required at instrument level. | TBD. May have to wait until January. |
| 28 P1 | FDIR | Bruce | To be written. Clarification needed from ESA on what's required. Will be based on two levels of parameter anomaly: serious - switch off now and not-so-serious - raise an anomaly report. | Draft: Dec. 10 Finalise by: Jan. 18 Philosophy only for documentation pack. |
| 29 P2 | Cleanliness Control Plan | Bruce | Exists. To be updated. | Finalise: Dec. 20 Draft available, to be finalised by 18/1/02 |
| 30 P2 | EEE Parts list | Eric Clark | To be collated from DDR data packs. | Finalise: Dec. 10 |
| 31 P1 | Verification Matrices | Eric S. | Exist. To be collated. | Finalise: Dec. 20 |
| 32 P1 | Configured Items Data List | Eric Clark | List of all configured documents. | Finalise: Dec. 10 |
| 33 P3 | Critical Items List |  | Need clarification from ESA | Out put from FMECA |
| 34 P3 | Change Requests and Waivers List | Eric Clarke | Exists - just needs to be printed out. | Finalise: Jan. 15 |
| Additional Documentation to be available for the Panel |
| 35 etc. P3 | All DDR Document sets All DDR Review Board Reports All agreed Interface Control Documents Technical notes and papers as deemed appropriate by the Project Team |  | Some need to be updated and placed on Livelink. | To be placed on Livelink and on the CD. |

## Management Reporting and Control

## Document change and configuration control

## PA

## Business Agreements

## Schedule:

# Instrument Issues

## Structure

## Mirrors

## Detectors

Budget problems still exist.

Agreement on no delay of CQM programme.

Staggered delivery not desirable, but will be assessed by system team.

Can JFET be delivered with detectors rather than before?  This prevents early testing of the cryo test harness.

JPL to propose changes to their programme, system team to asses impacts.

## OBS and Instrument Control

## DPU

## DRCU and related issues (Sap)

# ICC Issues

# Meetings:

## Detailed design Reviews

### DDR summary

- Mirrors:						Complete

- FTS:								22/23 Nov 2001.

- DRCU/WIH 				12/13 December.

- Structure/thermal straps 			29/30 Nov 2001

- DPU:  						6/7 Dec

- AIV							6/9/01, delta review required, to include egse.

- EGSE:				 		TBD, see above

- BDAs:/JFETs				Complete, ICD, FMECA and PA map outstanding

- Filters/calibs:				18/9/01,Complete

- BSM: 						30/7/01 not all issues closed out, delta review on 23/8/01, complete

- OBS							Requirements review required. Probably Nov

- Shutter PDR: 				July 17,  Almost a DDR, some aspects still open.

- Cooler						Complete, some RIDs to be signed off.

- DRCU simulator			TBD, awaiting spec from Sap.

# Progress on Open Issues

# AIT

# AOB

Next meeting