Notes on project managers teleconference                       SPIRE-RAL-MOM-001084

14/01/02

Chair:		Eric Sawyer

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin |  |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain | X |
| Don Peterson |  |
| Bruce Swinyard |  |
| Ken King |  |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |
| Fredericke Pinsard |  |

General

Progress reports for December required, than you to those who have already supplied one.

DDR documents on Livelink, subsystem managers to check and update if necessary.

IBDR documents required very soon.

Subsystem reports

IFSI  (Riccardo) – DPU

Not present

CEA Grenoble  (Lionel) – Cooler

Some distortion occurred on welding.

STM and CQM coolers will be modified before qualification.

FM will have a small design modification.

ECR response still awaited, RAL to chase.

USK. (Joe)  - Shutter

Cleanliness plan underway

Funding still in flux, but not stopping work yet.

Cardiff. (Peter)  Filters, calibrators

Harness interference being addressed.

ICD to be circulated next week.

Filter FMEC complete.

300mK strap supports (MK 1) ready this week,  MK 2 parts ready in 3 weeks.

Shutter info received from USK

ATC  (Ian)  -  BSM

Material and parts list underway.

Meeting planned with MSSL to discuss harness.

Hysterisis analysis complete.

SRON have been contacted regarding flex pivots.

JPL  (Jerry)  - Detectors

EM wafer run complete.

First QM BDA complete this week.

All ICD docs being reviewed at JPL, release soon.

Laboratory certification end of the month.

BODAC certified later.

JFET characterisation underway.

MSSL ( Chris) – Structure

2K box, clamshells, A frames out for quote.

Some milestones missed, remedial action being taken.

Major milestones look ok at present.

Some harness issues to be resolved.

RAL to contact LAM re harness.

LAM.  (Dominique)  - Mirrors, SMEC

Not present

SAp (Frederick)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Not present

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |
| 010326-07 | Issue an updated shutter SSSD | Don | 31/7/01 | This will be produced after the review next week (DDR). | Open |
| 010509-10 | Provide draft of an instrument operations document | Sunil | 30/6/01 | Status not known | Open |
| 010509-12 | Specify date of the DRCU Simulator DDR | Goran | 19/5/01 |  | Open |
| 010530-01 | Clarify whether an MCU-BSM ICD is available or planned to be written | Dominique | 15/6/01 | Planned to be complete by 31/7/01 | Open |
| AI-MAN-0753-03 | Review cost of cold vibration tests | Eric S | 20/7/01 | ongoing | Open |
| AI-MAN- 0820-01 | Ensure progress reports are sent to RAL (Eric Sawyer) each month. | ALL | Monthly | Thank you to those PMs who did send a report | open |
| AI-MAN- 0820-02 | Confirm that Dates listed in the major milestone list are acceptable | All | ASAP |  | open |
| AI-MAN-0865-02 | Confirm to JPl proposed return date of CQM BDA. | ECS | 30/9/01 |  | open |