Work Package:	BSM                                                                      SPIRE-ATC-REP-001159

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype tests in progress. Prep for IBDR underway. |
| 2. Subsystem Progress This Month |
| Detailed 2 axis prototype testing continues - linearity of chop and jiggle sensor confirmed, indicating look up tables not required. Infineon position sensors received. Purchase Order for sub-con of random response FEA placed. Magnetic modelling underway at MPIA. Options identified for cryo-harness connectors; pursuing details. |
| 3. Problem Areas | Remedial Action |
| development model has been released for manufacture 6 weeks late. Prototype tests are running one month late. Cryo-harness connectors found to have been omitted from CPPA request Cost of FEA vibration analysis | Effort surge will be required in new year to recoup slippage - effort does appear to be available. Looking at alternate procurement, discussing options for late insertion of request with RAL. Planning to re-cost budget and look for alternates before mid-Jan.02 |
| 4. Engineering Activities |
| Flexitape for Jiggle frame sensor - samples received from Tayco. C-Flex bearings have been approached for alternate flex pivot supply. |
| 5. Design Changes |
| Revised motor space envelopes received from MPIA - small increase in space to accommodate robust attachment point: will need to study this carefully to accommodate,. Good news is that Aluminium coil windings have been selected, which will help with power budgets. |
| 6. PA/QA Activities |
| Material and fasteners procured. Monthly dedicated PA meetings commenced. CTD scheme modified to improve traceability. BSM PA plan up-issued. Monitoring cleanliness having moved to new lab - not yet up[ to DM standard as builder' tidy up continues. |
| 7. Subsystem Management Issues |
| 8. Actions Requiring Immediate Attention |
| ATC-SW_19Nov01.01 - I.Pain/D.Griffin : Confirm common parts procurement (i.e. that items we have requested have indeed been ordered). ATC-SW_23Aug01.08 - I.Pain/P.D'Argent : confirm Launch latch Space envelope - awaiting space envelope update |
| 9. Status of Previous Actions |
| ATC-116 - M.Griffin/R.Carvell - Talk to Mike Sandford about costs of use of RAL cold vibration facility- ongoing ATC SX_23AUG01.12 -MJG/BMS - Revise micro-vibration susceptibility number (at next Alcatel meeting) - complete ATC-159 - BG characterise the flux of the BSM magnets/motors. - Write up pending ATC SX_23AUG01.05 - BMS - Check spec. on FoV requirements. issue as formal change request to the IRD - complete ATC SX_23AUG01.07 - BMS - Check specification on FoV of 126 arc secs. - complete |
| 10. Activities Yet to be Achieved |
| Test rig for cryo/warm screening of pivots designed, but needs to be detailed. |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| Report on sensor stability to LAM | 07 Jul 00 | 21 Jun 01 | 30.Jul.01 |  |
| Prototype Detail design release | 24 Jan 01 | 30 May 01 | 30May01 |  |
| Update ICD structure | 24 Oct 00 | 13 Jun 01 | 13 Jun 01 |  |
| 20K test dewar available | N/A | Mar.02 |  |  |
| SPIRE Intermediate Instrument Design Review (IIDR) | TBD | 23-24Apr.01 | 23-24Apr.01 |  |
| Integrate Prototype (in place of DM 2) to LAM | 30 Mar 01 | Jan.02 |  |  |
| Internal ATC review | new | 3 Jul 01 | 2.Jul.01 |  |
| Detailed Design Review | 30 Jan 01 | 31 Jul 01 | 30.Jul.01 |  |
| DM release for manufacture | Oct.01 | Nov.01 | Dec.01 |  |
| 2 axis prototyping at ATC complete | N/A | Jan.02 |  |  |
| SPIRE IBDR | N/A | Mar.02 |  |  |
| DM tests complete | N/A | 22 Mar 02 |  |  |
| BSM STM del'y to RAL | 01 Feb 00 | 01 Jul 02 |  |  |
| BSM CQM delivery to LAM | N/A | Jul.02 |  |  |
| BSM CQM del'y to RAL | 13 Mar 02 | Under review |  |  |