Work Package	PCAL                                                                   SPIRE-UCF-REP-001160

| 1. Subsystem Progress Since Project Inception |
| --- |
| Haller-Beeman thermal source evaluated - meets SPIRE requirements for power dissipation vs photometric power. Design needs modification to meet speed requirement. Detailed design of housing in progress. Prototype housing complete to enable tests of light pipe coupling to proceed. Tests show there is no significant reduction in light output when using the prototype light pipe coupled to the illuminator. Design almost complete in run-up to DDR |
| 2. Subsystem Progress This Month |
| Updating ICD HB7 source design nearing completion (with Jeff Beeman). |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| Telecon needed with ATC to revise delivery dates for DM and STM |
| 5. Engineering Activities |
| none |
| 6. Design Changes |
| Minor design changes are in progress following suggestions from DDR panel. These will not affect any interface to other subsystems |
| 7. PA/QA Activities |
| PA database under development. |
| 8. Actions Requiring Immediate Attention |
| Completion of ICD |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones – NB. These are common with SCAL | Status |
| Tue 05/12/00 Tue 03/04/01 Fri 30/03/01 Tue 22/05/01 Wed 17/10/01 Wed 27/03/02 Thu 20/06/02 Thu 13/12/01 Fri 22/03/02 Fri 18/10/02 Tue 04/02/03 Wed 14/05/03 Wed 01/10/03 Wed 03/09/03 Tue 09/12/03 | QMW Source Design review Prototype source testing complete Final Interface definition from ATC Calibrators design review (Internal) DM PCAL Delivery to ATC SCAL STM delivery to RAL CQM SCAL design review CQM PCAL design review CQM PCAL to ATC CQM SCAL to RAL PFM calibrators design review PFM PCAL to ATC PFM SCAL to RAL FS PCAL to ATC FS SCAL to RAL | Complete Tests continuing – not driving schedule Complete Complete Late – re-scheduled for TBD On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |
| DM PCAL delivery to ATC – 17/10/01 slip to TBD |

Work Package	SCAL

| 1. Subsystem Progress Since Project Inception |
| --- |
| SCAL completely redesigned – photometric modelling showed inability to match telescope spectrum with previous design. New design almost complete. Thermal model validated design. |
| 2. Subsystem Progress This Month |
| Updating ICD New drawings for prototype components submitted for manufacture |
| 3. Problem Areas | Remedial Action |
| None |  |
| 4. Subsystem Management Issues |
| None |
| 5. Engineering Activities |
| New thermal/mechanical prototypes in manufacture |
| 6. Design Changes |
| Minor design modifications are in progress following suggestions from DDR panel. These will not affect any interface to other subsystems |
| 7. PA/QA Activities |
| PA database under development. |
| 8. Actions Requiring Immediate Attention |
| Completion of ICD Agreement on revised electrical interface. |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones – NB. These are common with PCAL | Status |
| Tue 05/12/00 Tue 03/04/01 Tue 22/05/01 Wed 27/03/02 Thu 20/06/02 Fri 22/03/02 Fri 18/10/02 Wed 14/05/03 Wed 03/09/03 | QMW Source Design review Prototype source testing complete Calibrators design review (Internal) SCAL STM delivery to RAL CQM SCAL design review CQM SCAL to RAL PFM calibrators design review PFM SCAL to RAL FS SCAL to RAL | Complete Tests continuing – not driving schedule Complete On schedule On schedule On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |
| None |

Work Package	Filters

| 1. Subsystem Progress Since Project Inception |
| --- |
| SPIRE filtering scheme finalised. Prototyping in progress. Filter SSSD updated for DDR. Slight change of MW band for commonality with HFI band. |
| 2. Subsystem Progress This Month |
| Prototyping of dichroics and beam dividers 300mK filter interface components in manufacture Copper evaporation problems solved |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| 300mK filter interface components in manufacture |
| 6. Design Changes |
| 7. PA/QA Activities |
| PA database under development. |
| 8. Actions Requiring Immediate Attention |
| 9. Status of Previous Actions |
| None |
| 10. Activities Yet to be Achieved |
| 11. Budgets |
| 12. Milestones | Status |
| Wed 21/11/01 Wed 19/06/02 Tue 14/10/03 Wed 15/09/04 TBD TBD TBD | STM filters to RAL CQM Delivery to RAL PFM delivery to RAL FS delivery to RAL 300mK CQM filters to JPL 300mK PFM filters to JPL 300mK FS filters to JPL | Late – need to re-work schedule with MSSL and RAL On schedule On schedule On schedule Need info. From JPL Need info. From JPL Need info. From JPL |
| 13. Schedule Changes |
| STM filters to RAL – due 21/11/01 - need to re-work schedule with MSSL and RAL |

Work Package	300mK straps

| 1. Subsystem Progress Since Project Inception |
| --- |
| Thermal test dewar ready Thermal interface tests in progress |
| 2. Subsystem Progress This Month |
| Thermal conductivity and thermal interface tests continuing. Design validation prototypes in manufacture for “loo roll” suspension concept. Mark 2 support in manufacture. |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| This system has the full attention of the Cardiff SPIRE team, and will be treated as the highest priority work package |
| 5. Engineering Activities |
| Design validation prototypes in manufacture for “loo roll” suspension concept – overdue - expected within 2 days Mark 2 support in manufacture – expected completion 3 weeks |
| 6. Design Changes |
| 7. PA/QA Activities |
| None |
| 8. Outside Agency Interfaces |
| MSSL for drawings and hardware |
| 9. Actions Requiring Immediate Attention |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| 12. Budgets |
| 13. Milestones | Status |
| Mon 12/02/01 Thu 25/01/01 Tue 27/02/01 Wed 09/05/01 Wed 28/02/01 Thu 12/04/01 Tue 29/05/01 Wed 11/07/01 Thu 02/08/01 Thu 23/08/01 Thu 23/08/01 Fri 24/08/01 Mon 10/12/01 Mon 28/01/02 Tue 23/04/02 Wed 03/09/03 Wed 29/10/03 | He-7 fridge shield ready GRTs from Lakeshore Test dewar ready Interface study complete Design Review - LBDR1 LBP1 to QMW (2 off) Design Review - LBDR2 LBP2 to Cardiff (2 off) Design report Light baffle design complete Prototype light baffle design Design Review - CSDR1 Cold strap prototypes - Test Report STM design review - CSDR2 STM/CQM straps ready for integration PFM straps ready for integration FS straps ready for integration | Complete Complete Complete Late Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) Development plan to be re-defined (see above) On schedule On schedule On schedule On schedule On schedule |
| 14. Schedule Changes |
| Development plan to be re-defined |

Work Package	AIV participation

| 1. Subsystem Progress Since Project Inception |
| --- |
| Cryogenic black body & flip mirror/shutter concept produced – approved at AIV review Conceptual design presented at AIV DDR. |
| 2. Subsystem Progress This Month |
| None |
| 3. Problem Areas | Remedial Action |
| None | . |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| none |
| 6. Design Changes |
| 7. PA/QA Activities |
| None |
| 8. Outside Agency Interfaces |
| RAL for design changes & interface definition. |
| 9. Actions Requiring Immediate Attention |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| Production of CBB & flip mirror module. Provision of reference detector Provision of FTS |
| 12. Budgets |
| 13. Milestones | Status |
| 31/5/02 31/5/02 TBD TBD | CBB to RAL AIV Filters to RAL FTS to RAL Reference detector to RAL | On schedule On schedule |
| 14. Schedule Changes |
| None |

Work Package	JPL BDA test support

| 1. Subsystem Performance Progress Since Project Inception |
| --- |
| Optics modules designed manufactured Test cryostats at JPL Fridge #1 at JPL Fridge #2 at JPL Optics modules shipped |
| 2. Subsystem Progress This Month |
| Cryostat filters in production. Additional components in manufacture. |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| 5. Engineering Activities |
| Filters in production. Additional components in manufacture – (baffles) |
| 6. Design Changes |
| 7. PA/QA Activities |
| None |
| 8. Outside Agency Interfaces |
| Janis Cryogenics for test dewars. Chase research for fridges. Tekdata for wiring harnesses. Symons mirror technology for mirrors. Deteronics (TBC) for connectors (hermetic). TMC for machining work (optics module) |
| 9. Actions Requiring Immediate Attention |
| 10. Status of Previous Actions |
| None |
| 11. Activities Yet to be Achieved |
| To be defined |
| 12. Budgets |
| 13. Milestones | Status |
| 14. Schedule Changes |
| None |