# Staffing

No changes.

# Meetings and their Conclusions

| Date | Location | Meeting | Comments |
| --- | --- | --- | --- |
| 6-7 Feb | IC | ICC definition team meeting |  |
| 18-19 Feb | RAL | SPIRE OBS Meeting | Discussions with Sergio Molinari (IFSI) regarding the SPIRE OBS architecture and its implementation |
| 28 Feb | SRON | HGSSE meeting # 17 | Attended by Sunil Sidher and Matthew Graham |

# Activities

## General

- Definition of SPIRE ICC work packages, including QLA

- QLA prototyping

- ICC IA Use Case Analysis

- HCSS development work

- HCSS Use Cases consolidation

- IA commonality meeting preparation

## Training

None this month.

## Work during month on HCSS activities

| WP | Days Worked (to Feb) | Days Worked (Feb) | Days Worked (Total) | Days Planned (Total) |
| --- | --- | --- | --- | --- |
| 22410.EP2 ILT system | 19 | 3 | 22 | 40 |
| 22420.EP2 ILT integration | 3 |  | 3 | 30 |
| 22430.EP2 HGSSE | 14 | 3 | 17 | 15 |
| 22440.EP2 System Eng | 4 | 1.5 | 5.5 | 15 |
| 24250.EP2 Data frame | 6 |  | 6 | 20 |
| 24370.EP2 SPIRE IA | 25 |  | 25 | 50 |
| 24510.EP2 TM I/F AA/prot | 34 |  | 34 | 50 |
| 24520.EP2 TM I/F imp | 12.5 |  | 12.5 | 110 |
| 24610.EP2 TC Hist AA/prot | 29.5 | 1 | 30.5 | 60 |
| 24620.EP2 TC History imp |  |  |  | 70 |
| 24630.EP2 OOL AA/prot | 8.5 | 2 | 10.5 | 60 |
| 24640.EP2 OOL imp |  |  |  | 70 |
| 25500.EP2 Consultancy |  |  |  | 5 |
| 27000.EP2 Coordination |  |  |  | 15 |
| 29000.EP2 Review | 34.5 | 6 | 40.5 | 15 |
| 2B000.EP2 Contingency | 9 |  | 9 |  |

# Critical Areas, Concerns, Upcoming Events

## Critical Areas

- HCSS 0.09 due end of March

- QLA-AVM due beginning of June

Logica say that they have almost completed development of the TC History/OOL cache access package. It will be ready for installation either at IC or RAL on 7 March at the earliest and requires S2K v.2.1.1e. A CD-ROM from ESOC of this release has only just been received at RAL.

## Concerns

Work on QLA has again been less than planned due to other work being given a higher priority, in this case preparation for the IA commonality meetings. This will remain a concern during March.

## Upcoming Events

| Date | Location | Event | Comments |
| --- | --- | --- | --- |
| 5-6 Mar | MPE | IA commonality meeting |  |
| 5-6 Mar | RAL | SPIRE IBDR |  |
| 7 Mar | IC | ICC definition team meeting |  |
| 8 Mar | IC | ICC Software Development Team Meeting | First meeting of the ISDT (developing QLA) |
| 19-20 Mar | SRON | IA commonality meeting |  |
| 26-27 Mar | RAL | IA commonality meeting |  |
| 4 Apr | ESTEC | IA commonality report |  |
| 17 Apr | ESTEC | CSDT#14 |  |

SG/SDS, 4th March 2002