Work Package:	BSM                                                                    SPIRE-ATC-REP-001202

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype tests in progress. Prep for IBDR underway. |
| 2. Subsystem Progress This Month |
| Detailed 2 axis prototype testing continues. Mechanical design changes to DM completed & released for manufacture. Flex pivot discussions held with Ray Carvell and UK industry : technically feasible but probably costly. Infineon position sensors re-ordered. Responses to RFQ for sub-con of random response FEA received: at £25K these are ~£20K over funds available for this. Magnetic modelling underway at MPIA. Options identified for cryo-harness connectors; pursuing details.. |
| 3. Problem Areas | Remedial Action |
| development model has been released for manufacture 6 weeks late. Prototype tests are running one month late. Cryo-harness connectors found to have been omitted from CPPA request Cost of FEA vibration analysis | Effort surge will be required in new year to recoup slippage. Looking at alternate procurement, discussing options for late insertion of request with RAL. Planning to re-cost budget and look for alternates before mid-Jan.02 |
| 4. Engineering Activities |
| Electronics work concentrated on sensors and flexitape for Jiggle frame (possible solution - Tayco. BS has worked on motor torque tests, Sensor tests, sensor calibration against optical reference. ). Doug Griffin at RAL is taking on an overview on harness standards to ensure commonality between subsystems, and help reduce potential duplicate work by the BSM team. Test rig for cryo/warm screening of pivots designed, but needs to be detailed. |
| 5. Design Changes |
| Launch latch re-positioned on DM. PCAL space envelope rotated 180degrees and ICD change required. Numerous DM mods incorporated, especially to jiggle axis sensor positions and addition of thermal shrouds and revised wiring pins on motors. |
| 6. PA/QA Activities |
| Material and fastener suppliers obtained. Monthly dedicated PA meetings organised. Move to new lab provides opportunity to enhance cleanliness and reduce access (secure lab). |
| 7. Subsystem Management Issues |
| Some time loss due to prep for move of lab, & Pro E setup problems. Ken Wilson ( project technician) has been off sick for 3 weeks, and this will continue until new year. Tom Baillie (another experienced technician) is available to stand in but learning curve applies. |
| 8. Actions Requiring Immediate Attention |
| ATC-116 - M.Griffin/R.Carvell - Talk to Mike Sandford about costs of use of RAL cold vibration facility ATC SX_23AUG01.12 -MJG/BMS - Revise micro-vibration susceptibility number (at next Alcatel meeting) |
| 9. Status of Previous Actions |
| ATC -187 - BG to order additional position sensors - complete ATC-159 - BG characterise the flux of the BSM magnets/motors. - Write up pending ATC SX_23AUG01.03 - BMS - Provide a traceable document with the optical scaling factor. -complete ATC SX_23AUG01.05 - BMS - Check spec. on FoV requirements. issue as formal change request to the IRD -ongoing ATC SX_23AUG01.07 - BMS - Check specification on FoV of 126 arc secs. -ongoing |
| 10. Activities Yet to be Achieved |
| PA plan up-issue delayed by effort shortfall : impacts DPL/DML/FMECA provision . Going to try to roll these out before Xmas |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| Report on sensor stability to LAM | 07 Jul 00 | 21 Jun 01 | 30.Jul.01 |  |
| Prototype Detail design release | 24 Jan 01 | 30 May 01 | 30May01 |  |
| Update ICD structure | 24 Oct 00 | 13 Jun 01 | 13 Jun 01 |  |
| 20K test dewar available | N/A | Mar.02 |  | +5 months |
| SPIRE Intermediate Instrument Design Review (IIDR) | TBD | 23-24Apr.01 | 23-24Apr.01 |  |
| Integrate Prototype (in place of DM 2) to LAM | 30 Mar 01 | Jan.01 |  | +1 month |
| Internal ATC review | new | 3 Jul 01 | 2.Jul.01 |  |
| Detailed Design Review | 30 Jan 01 | 31 Jul 01 | 30.Jul.01 |  |
| DM release for manufacture | Oct.01 | Nov.01 | Dec.01 | + 6 weeks |
| 2 axis prototyping at ATC complete | N/A | Jan.01 |  | +1 month |
| SPIRE IBDR | N/A | Mar.02 |  |  |
| DM tests complete | N/A | 22 Mar 02 |  |  |
| BSM STM del'y to RAL | 01 Feb 00 | 01 Jul 02 |  |  |
| BSM CQM delivery to LAM | N/A | Jul.02 |  |  |
| BSM CQM del'y to RAL | 13 Mar 02 | Under review |  |  |