Work Package:	DPU                                                                       SPIRE-IFS-REP-001205

| 1. Subsystem Progress Since Project Inception |
| --- |
| 2. Subsystem Progress This Month |
| The first set of DPU boards have been delivered by CGS to IFSI after a partial acceptance test at CGS due to a failure in the IFSI provided SS I/F simulators. At IFSI the problem with the SS simulator have been fixed and a number of extensive tests have been performed on the boards. During our tests a number of problems, possibly located in the socket mounted FPGA, have arisen and we are in close contact with CGS in order to solve it. DPU SPIRE documentation have been written/updated and provided to the project for the December DPU DDR. |
| 3. Problem Areas | Remedial Action |
| 4. Engineering Activities |
| 5. Design Changes |
| 6. PA/QA Activities |
| 7. Subsystem Management Issues |
| None |
| 8. Actions Requiring Immediate Attention |
| None |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Milestones | Status |
| 28/06/01 15/6/01 28/6/01 1/10/01 2/4/02 15/11/01 22/4/02 2/1/03 20/12/02 15/9/03 1/3/04 24/2/04 | DRCU simulator at IFSI CDMS (S/C I/F) at IFSI EGSE at IFSI DPU-AVM Board at IFSI DPU-AVM delivery to RAL QM author. To proceed DPU-QM Board at IFSI DPU-QM delivery to RAL FM author. To proceed DPU-FM Board at IFSI DPU-FM delivery to RAL FS ready for delivery | Late – expected completion 30/9/01 Late – Proto SW arrived on 21/8/01 Late – SCOS 2000 arrived on 20/8/01 Late – new date 15/01/02 Late – new date 16/04/02 Late - new date 15/01/01 On schedule On schedule On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |
| None |