Work Package:	SPIRE AIV Facilities                                  SPIRE-RAL-REP-001208

| 1. Subsystem Progress Since Project Inception |
| --- |
| Cryostat preliminary design completed – August 2001 Building work on cryolab completed – End June 2001 Cryolab clean room completed – 03-Aug-2001 AIV Facilities DDR held on 6th-September-2001 Cryostat outer-vacuum vessel manufacture started – Nov 2001 Cryoharness ordered – Nov 2001 |
| 2. Subsystem Progress This Month |
| Cryolab: All decoration work on the laboratory has been completed. Two 3-phase power supply points have been installed for the cryostat vacuum system. Cryostat: The detailed engineering drawings for the outer vacuum vessel have been approved and manufacture has started. Detailed drawings for the cryogenic vessels have been produced and have been reviewed. A few minor corrections are required but should not affect the procurement of parts. A design of the HOB simulator and support frame has been produced and is under review. A thermal analysis of the cryostat to so that the design of the HOB simulator can be optimised. Drawings for the filter mounts have been produced and manufacturers are being approached. The cryostat vacuum system has been delivered. Cryoharness: A requisition order has been raised for the cryoharness manufacture to ensure delivery by next August. The 128 way vacuum feedthroughs and connectors have been ordered for delivery in March 2002. Telescope Simulator: The telescope-imaging mirror has been delivered to RAL and is currently undergoing 3D metrology. Laser: The laser has been moved back into the clean-room and the services have been reconnected and checked out. Damaged and worn components have been replaced. The wiring for the laser interlock system has been moved and an additional door switch has been included. TFCS: A draft version of the User Requirements Document has been produced. Thermometer monitoring units have been ordered from Lakeshore and should be available by mid December. |
| 3. Problem Areas | Remedial Action |
| 4. Subsystem Management Issues |
| A revised milestone list was issued for approval on 17th October and is awaiting formal approval by the Project Team. |
| 5. Activities to be achieved in next reporting period. |
| Cryolab: Specify furniture for the control room. Cryostat: Materials for cryostat should be arriving at Stainless Metalcraft and AS Scientific. Identify manufacturer and costs for instrument support frame and HOB simulator. Order external vacuum window. Cryoharness: Contract placed with harness supplier. Telescope Simulator: Final components for focus control ordered. Optical benches delivered. Laser: Laser commissioned. TFCS: URD Completed. Prototyping for cryostat monitoring system started. |
| 6. Design Changes |
| An additional port for a vacuum gauge head on the cryostat has been requested. |
| 7. PA/QA Activities |
| None at present. |
| 8. Actions Requiring Immediate Attention |
| Respond to DDR report. |
| 9. Status of Previous Actions |
| Some action items have been addressed. |
| 10. Budgets |

| 12. Milestones | Status |
| --- | --- |
| 08/01/01 01/11/01 30/01/02 01/04/02 01/03/02 01/07/01 21/12/01 31/12/01 30/04/02 01/09/02 02/12/01 30/10/01 01/03/02 08/06/01 01/03/02 | Cryostat Design Complete Cryostat Manufactured Cryostat Integrated Cryostat Commissioned Cryoharness Delivered Cryolab Available Telescope Simulator Delivered TFCS Cryostat Monitoring TFCS Complete FTS Delivered Cold BB Delivered Reference Detector Hot BB Delivered FIR Laser Beam Monitor | Completed 08-Jan-2001 Delayed 5 months to 15/05/02 Delayed 4 months to 04/06/02 Delayed 4 months to 27/07/02 Aug-2002 Completed 03-Aug-2001 Feb-2002 April-2002 Aug-2002 Jan-2003 May 2001 (TBC) No change No change Delayed to Early December 2001 No change |
| 13. Schedule Changes |
| Laser is expected to be on-line by early December. |