Work Package:	BSM

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype tests in progress. IBDR underway. |
| 2. Subsystem Progress This Month |
| Detailed 2 axis prototype warm testing completed, including control loop tests. Preparation for cryo tests started. Kick-off meeting on random response FEA held. Magnetic modelling underway at MPIA, but delayed by effort availability. Representative Zeiss/PACS motors received. Development model manufacture in progress. Cryo-upscreen rig design complete and placed with workshop for manufacture. Brazed CuBe pivots (chop axis type) order placed with C-Flex. |
| 3. Problem Areas | Remedial Action |
| Representative (ESA type) wire needed for DM harness design. ICD, design description updates running late | Requested RAL assistance (Doug Griffin) Post to Livelink as soon as available. |
| 4. Engineering Activities |
| Sub-System Specification up-issued. Note change to schop throw of 2.53° (was 2.4°). Studying revised motor space envelopes. |
| 5. Design Changes |
| Change request (on connector position received and handled in ATC CTD 01-26. Rotation of harness connectors by 90° combined with 45 degree angled backshell required to allow min bend radius by MSSL. Development model design updated and ICD document change in progress |
| 6. PA/QA Activities |
| Monitoring cleanliness having moved to new lab - may be a problem area and remedial action could be required. DCL, DML, EEE up-issued. FMECA updated and issued. |
| 7. Subsystem Management Issues |
| Development plan up-issued. Project cost estimate updates underway. Bottleneck in mechanical design for STM/OGSE. Possible cost savings on pivots, offset by actual in-house manufacture costs. Delayed prototype Launch Latch from LAM will require BSM tests with a dummy. |
| 8. Actions Requiring Immediate Attention |
| ATC-SW_19Nov01.01 - I.Pain/D.Griffin : Confirm common parts procurement (i.e. that items we have requested have indeed been ordered). |
| 9. Status of Previous Actions |
| ATC-SW_23Aug01.08 - I.Pain/P.D'Argent : space envelope update received. ATC-116 - M.Griffin/R.Carvell - Talk to Mike Sandford about costs of use of RAL cold vibration facility- ongoing ATC SX_23AUG01.12 -MJG/BMS - Revise micro-vibration susceptibility number (at next Alcatel meeting) - complete ATC-159 - BG characterise the flux of the BSM magnets/motors. - Write up pending ATC SX_23AUG01.05 - BMS - Check spec. on FoV requirements. issue as formal change request to the IRD - complete ATC SX_23AUG01.07 - BMS - Check specification on FoV of 126 arc secs. - complete |
| 10. Activities Yet to be Achieved |
| Test rig for cryo/warm screening of pivots designed, but needs to be detailed. |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| Report on sensor stability to LAM | 07 Jul 00 | 21 Jun 01 | 30.Jul.01 |  |
| Prototype Detail design release | 24 Jan 01 | 30 May 01 | 30May01 |  |
| Update ICD structure | 24 Oct 00 | 13 Jun 01 | 13 Jun 01 |  |
| 20K test dewar available | N/A | Apr.02 |  | +1 month |
| SPIRE Intermediate Instrument Design Review (IIDR) | TBD | 23-24Apr.01 | 23-24Apr.01 |  |
| Integrate Prototype (in place of DM 2) to LAM | 30 Mar 01 | Mar.02 |  | +2 months |
| Internal ATC review | new | 3 Jul 01 | 2.Jul.01 |  |
| Detailed Design Review | 30 Jan 01 | 31 Jul 01 | 30.Jul.01 |  |
| DM release for manufacture | Oct.01 | Nov.01 | Dec.01 |  |
| 2 axis prototyping at ATC complete | N/A | Feb.02 |  | +4 weeks |
| SPIRE IBDR | N/A | Mar.02 |  |  |
| DM tests complete | N/A | 30.Apr 02 |  | +5 weeks |
| BSM STM del'y to RAL | 01 Feb 00 | 01 Jul 02 |  |  |
| BSM CQM delivery to LAM | N/A | Jul.02 |  |  |
| BSM CQM del'y to RAL | 13 Mar 02 | Under review |  |  |