Work Package:	DPU                                                                      SPIRE-IFS-REP-001212

| 1. Subsystem Progress Since Project Inception |
| --- |
| 2. Subsystem Progress This Month |
| Box mechanical design completed, the AVM box is manufactured. Intensive software tests related to the S/C interface are progressing. The ASI Review Change Board has evaluated the ECP3 in answer to CGS ECP3 (minimum MIL-C quality for QM components), the financial/contractual aspects still to be approved by the ASI Administration Board. The VM Compiler/Simulator is in progress (80% ready) |
| 3. Problem Areas | Remedial Action |
| HW problems with fast I/F has been solved while the slow speed I/F is still under investigation. | On week 4-9 Feb IFSI representatives will be at CGS to help solve the problem. |
| 4. Engineering Activities |
| 5. Design Changes |
| 6. PA/QA Activities |
| 7. Subsystem Management Issues |
| As stated in the Jan 25 mail of P. Saraceno to K. King, the responsible for SPIRE OBS is now Sergio Molinari. |
| 8. Actions Requiring Immediate Attention |
| None |
| 9. Status of Previous Actions |
| 10. Activities Yet to be Achieved |
| 11. Milestones | Status |
| 28/06/01 15/6/01 28/6/01 1/10/01 2/4/02 15/11/01 22/4/02 2/1/03 20/12/02 15/9/03 1/3/04 24/2/04 | DRCU simulator at IFSI CDMS (S/C I/F) at IFSI EGSE at IFSI DPU-AVM Board at IFSI DPU-AVM delivery to RAL QM author. To proceed DPU-QM Board at IFSI DPU-QM delivery to RAL FM author. To proceed DPU-FM Board at IFSI DPU-FM delivery to RAL FS ready for delivery | Late – expected completion 30/2/02 Late – Proto SW arrived on 21/8/01 Late – SCOS 2000 arrived on 20/8/01 Late – new date 15/02/02 Late – new date 16/04/02 Late - new date 15/02/01 On schedule On schedule On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |
| None |