# Notes on project managers teleconference                       SPIRE-RAL-MOM-001237

08/04/02

Chair:		Eric Sawyer

Present:

| Lionel Duband |  |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt |  |
| Matt Griffin |  |
| Peter Hargrave | X |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain |  |
| Don Peterson |  |
| Bruce Swinyard |  |
| Ken King |  |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin |  |
| Dave Smith |  |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |
| Fredericke Pinsard |  |
| Viktor Zilinskis | X |

General

Please get  monthly reports to RAL as soon as possible.

Subsystem reports

IFSI  (Riccardo) – DPU

Not present

CEA Grenoble  (Lionel) – Cooler

Unavailable, apologies sent

USK. (Victor)  - Shutter

Small contract with Comdev  to keep work going.

PA info requested from RAL, response this week.

Cardiff. (Peter)  Filters, calibrators

Milestones restructured.

P cal, modelling being carried out to optimise performance.

S cal, manufacture still underway, some delay but no major impact.

Connectors and temperature sensors required for CQM, RAL to chase.

300mK filters received at  JPL,

These are test filters only and will not be used for CQM or FM.

300 mK strap interface will be finalised in the next few days.

Prototype steppers received for test mechanisms.

Cryostat model required from RAL, ECS to chase.

ATC  (Ian)  -  BSM

Not present

JPL  (Jerry)  - Detectors

Vibration test on EM, Kevlar string failed.

Kevlar was damaged during assembly, stress concentration and damage has been estimated to reduce strength by factor 4.

Modifications incorporated and retest planned for tomorrow.

Detectors due for completion in 8 weeks.

JFET manufacture to start soon, as soon as analysis is complete.

On track for on time CQM delivery.

MSSL ( Chris) – Structure

Unavailable, apologies sent

LAM.  (Dominique)  - Mirrors, SMEC

Not present

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Not present (Envisat commissioning)

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |