# Notes on project managers teleconference                       SPIRE-RAL-MOM-001261

29/04/02

Chair:		Ken King

Present:

| Lionel Duband | X |
| --- | --- |
| Ben Parvin |  |
| Berend Winter |  |
| Chris Brockley-Blatt | X |
| Matt Griffin |  |
| Peter Hargrave |  |
| Jerry Lilienthal | X |
| Joe Taylor | X |
| Ian Pain |  |
| Don Peterson |  |
| Bruce Swinyard |  |
| Ken King | X |
| Dominique Pouliquen |  |
| Gary Parks |  |
| Jean-Louis Auguerres |  |
| Doug Griffin | Part |
| Dave Smith |  |
| Eric Clark |  |
| John Delderfield |  |
| Didier Ferrrand |  |
| Riccardo Cerulli-Irelli |  |
| Renato Orfei |  |
| Brian Stobie |  |
| Fredericke Pinsard |  |
| Viktor Zilinskis | X |

General

Detector Summit held at JPL – minutes available

Instrument Simulator discussion held at ESOC

Subsystem reports

IFSI  (Riccardo) – DPU

- Not present

CEA Grenoble  (Lionel) – Cooler

- Problem with subcontractor led to failure on 2 of 4 heat switches during braising – agreed that the subcontractor will replace the 2 failures. Different subcontractor will provide future switches. SBT will qualify switches from new manufacturer if necessary

- All structures for coolers are at SBT - STM Cooler  has been pressure tested

- Will use old switches to test thermal properties of this cooler, should have real switches  after this

- Vibration test of STM coolers at end May – beginning of June

- Algorithm for cooler control remains as in Lionel’s note.

USK. (Victor)  - Shutter

- ComDev shipped a sample vane to Cardiff last week

- CSA have given ComDev an time extension to complete the work

- Decision on further funding will be made after S/C PDR.

Cardiff. (Peter)  Filters, calibrators

- Updated Cardiff  schedule available – new deliveries dates to ATC agreed

- PCAL – modelling should allow finishing of design in next two weeks

- SCAL – should get parts in next few days

- Shutter Vane received from ComDev and will be used for qualification of ‘QMW Black’ as it is a large area to be coated. Vibration test mount is in manufacture  - shouldbe available in two weeks

- Cardiff have manufactured two sets of filters for BODAC, but JPL are only using one BODAC now. So Cardiff will only send one set. Light baffles have also been manufactured – will be sent in a few days

- Set of 300mK filters were sent to JPL some time ago with a request for comments on the mount design – nothing received, so assumption is that the design is OK.

- Dates for 300mK filters have been specified by Cardiff – Jerry to say if these fit in with JPL schedule

- STM Filters and CQM 300mK filters now in manufacture.

- Interfaces for 300mK straps now more-or-less agreed. There will be a meeting at Cardiff of tiger team on 1st May to discuss outstanding design and plan for the DDR to be held in ~two weeks.

- AIV – testing and cleaning of stepper motors for use in fold mirror is ongoing

- Filters for cryostat have been ordered. There is a problem with the 77K filter as it is too big for the usual supplier. Cardiff are looking for new supplier.

ATC  (Ian)  -  BSM

Not Present

JPL  (Jerry)  - Detectors

- Detector Summit was held last week

- Currently assembling 2nd and 3rd units so will have 3 available by the middle of May.

- Analysis of fatigue life ahs been made and looks to be sufficient

- JFET membranes still in test

- Harness – minutes of telecon needed  - Chris will send her notes

- Doug asked for a sample of 10 m of 12-ax cable

MSSL ( Chris) – Structure

- Finishing detail design of optical bench – in particular photometer box and SCAL box

- Outer covers are being pocketed

- Optical bench will be manufactured in 2 weeks

- Integration (fit check)  starts early June (and July) at MSSL. In August the parts will be sent to RAL for cleaning. Reassembly will take place in September

- Routing of internal harnesses should be out in couple of weeks

- Outstanding item is the thermal bussbar – will be discussed at 300mk tiger team meeting

- Chris and Berend will be away 10-31st May – John Coker will be point of contact for this time

LAM.  (Dominique)  - Mirrors, SMEC

Not present

SAp (Jean-Louis)   -  DRCU

Not present

RAL,  (Dave) -  AIT

Not present

| No. | Action | Who | Due date | Response/Comment | Status |
| --- | --- | --- | --- | --- | --- |