Work Package:	Structure                                                             SPIRE-MSS-REP-001277

| 1. Subsystem Progress Since Project Inception |
| --- |
| Several concepts evaluated for the structure. Base line design decided upon in June 2000. Working on the system implications and implementation since first half of 2001. Continuing to close interfaces with the various subsystems. Started with production drawings in February 2001. The concept of the suspension has been analysed and decided on implementation. Hardware produced and tested, meets specifications. Detailed design continuing and manufacture has started. |
| 2. Subsystem Progress This Month |
| Subsystem interfaces still open are thermal busbar, thermistors, RF filters and SMEC. Detailed design for MGSE nearly completed. Minor changes to documentation have been implemented. Delivery of STM still in Early August with current manufacturing deadlines. Harness routing continuing. Production of second optical bench nearly completed and the production of the photometer 2K box and covers has started. Several sets of mirror mounts and the dichroic mounts have been completed. Detail drawings of spectrometer 2K box are underway. |
| 3. Problem Areas | Remedial Action |
| -Difficult to close interface definitions. Also other subsystems have problems with them. Thermal busbar suspension has strong non-linear responses Bend radii of proposed cabling is making the harness routing a longer task than originally anticipated | -Most interfaces are closed. The outstanding ones include the RF filters, JFETS and the SMEC. - Development team has been set up to redefine design. Final design was chosen on 25 February 2002 and was the Cardiff “Loo Roll” Design. Now working to implement design without effecting the schedule. Continuing design work and closer co-operation with RAL. |
| 4. Engineering Activities |
| Analysis and alignment reports |
| 5. Design Changes |
| - |
| 6. PA/QA Activities |
| - |
| 7. Subsystem Management Issues |
| - |
| 8. Actions Requiring Immediate Attention |
| - |
| 9. Status of Previous Actions |
| - |
| 10. Activities Yet to be Achieved |
| Close the I/F with JPL for the RF filters only. Close out interface with SMEC. Finish harness routing. Detail design drawings for spectrometer side cover and spectrometer 2K box. |
| 11. Milestones | Status |
| February 2002 13-08-2002 01-02-2002 10-06-2003 01-10-2002 6-01-2004 | Interfaces defined and reported STM delivery to RAL CQM FTB enclosure to RAL PFM delivery to RAL PFM FTB enclosure to RAL FS delivery to RAL | On going On schedule On schedule On schedule On schedule |
| 13. Schedule Changes |
| Due to the proposed design and improved manufacturing deadlines, we are lagging 0.5 months behind on original schedule. |