Work Package:	BSM                                                                  SPIRE-ATC-REP-OO1347

| 1. Subsystem Progress Since Project Inception |
| --- |
| Baseline design accepted at Delta-PDR, including digital electronics control by MCU. CPP parts requested. Single axis prototyping complete. DDR held. 2 axis prototype tests complete. IBDR complete (report pending). Development Model testing |
| 2. Subsystem Progress This Month |
| Reviewed schedule and model philosophy. Agreed to re-work DM-1 as the STM and OGSE. Manufacture of DM-2 progressed in workshop, but impacted by staff holidays. New test engineer (David McNeill) has started work and ramping up to speed |
| 3. Problem Areas | Remedial Action |
| Full checks on repeatability/linearity in dewar not possible due to problem with multiple reflections on cryostat window | high efficiency anti-reflection coating window received and tested warm. Will test further in conjunction with DM-2. |
| 4. Engineering Activities |
| Launch Latch relocated on design and problem noted with DM-2 motor wiring. Change to proposed ATC mounting in hand - will need to tie up with LAM. Re-test of sensor linearity and commencement of a check out of proposed life-test protocols as part of training for new test engineer. Work on sensor gain tests with DM-2 type cores and flight type electronics started. |
| 5. Design Changes |
| Flexi-tape design complete, will place order shortly. Design for refurbishment of DM-1 as STM starting. |
| 6. PA/QA Activities |
| Working through CTD's and NCR's, but progress slowed by other priority activities. General lab cleanliness being monitored daily with several procedural changes being made to improve particle count. BeCu pivots received and inspected. Some variability in braze fillet profiles will need check out as part of up-screen. |
| 7. Subsystem Management Issues |
| Re-costing complete and indicates all deliverables can still be met on a success-oriented schedule. |
| 8. Actions Requiring Immediate Attention |
| IP/D.Griffin : ATC Need MSSL definition of harness run and back-shells to procure harness. (critical path STM ). IP Configured Items Data List is required SW11MAR02.02 (IP) Place contract for Zeiss motors |
| 9. Status of Previous Actions |
| No change |
| 10. Activities Yet to be Achieved |
| STM specific ICD is required. |
| 11. Milestones | Status |
| Milestone | Baseline | Scheduled | Actual | Change |
| 20K test dewar available | N/A | May.02 |  |  |
| Integrate Prototype (in place of DM 2) to LAM | 30 Mar 01 | Apr.02 |  |  |
| DM release for manufacture | Oct.01 | Nov.01 | Dec.01 |  |
| DM-2 release for manufacture | N/A | Apr.02 | Apr.02 |  |
| 2 axis prototyping at ATC complete | N/A | Mar.02 | Apr.02 |  |
| SPIRE IBDR | N/A | Mar.02 | Mar.02 |  |
| DM-2 tests complete | 30.Apr 02 | End Jun.02 |  | +1 month |
| BSM STM del'y to RAL | 01 Feb 00 | 01 Jul 02 |  |  |
| BSM CQM delivery to LAM | Jul.02 | Sep.02 |  |  |
| BSM CQM del'y to RAL | 13 Mar 02 | Jan.03 |  |  |