Meeting of Integration and AIV Planning Team at RAL

Thursday 18 July 2002

Present

Chris Brockley-Blatt	MSSL

Eric Sawyer		Rutherford Appleton Laboratory

Dave Smith		Rutherford Appleton Laboratory

# Discussions

This was the first meeting of the Integration and AIV Planning Team, consisting of Eric Sawyer, Chris Brockley-Blatt and Dave Smith.  The meetings will be a forum to discuss and plan the logistics of the forthcoming integration and AIV of Spire STM and CQM models.  They will be held once a fortnight, either at MSSL or at RAL.

Preciding to the meeting, CBB presented the current MSSL schedule and manufacturing difficulties.  The current plan is for the Optical Bench design to be finished by and released on 2 August 2002, so that the bench can be manufactured by the end of August.  This is the critical path for the MSSL schedule.  The current proposed MSSL integration Plan is shown in Figure 1.

Figure 1 – MSSL Integration Schedule

# Delivery Dates

It was deemed necessary to have realistic delivery dates so that a realistic integration and AIV could be produced.   MSSL currently need the filters’ thickness in order to finish the dichroic mounts (ACTION 1).  The current delivery date for parts to RAL for MSSL is 7 October 2002 but theses parts need to be cleaned and baked out before final assembly.  This is due to finish on 26 November, as it currents stands.

It was agreed to get realistic delivery dates form the rest of the subsystems before actually notifying them of the last deadlines for delivery, in order to maintain or improve upon the AIV schedule. (ACTION2).

# MGSE

From looking at the MSSL and the RAL integration plans, it looks like that both institutions require the HOB simulator at the same time.  RAL will need to order a second HOB simulator to ensure that there is no delay to the current schedule (ACTION 3).

RAL to check the height of the test area, as there was concern expressed about the height of the lifting equipment as designed by MSSL (ACTION 4).

MSSL to check the number of sets of MGSE that will be supplied. (ACTION 5).

# Schedule

With the delivery of the Cryostat estimated at 18 September 2002 and the MSSL delivery dates, the integration and AIV plan is currently 2 months behind previously envisaged.  Looking at the RAL and MSSL plans together, it seems that some of the tasks can be concurrent or even merged.  This needs to be investigated further and RAL need to replan these activities (ACTION 6).

MSSL to plan out their clean and bake out plans and advise RAL which parts need to be baked out at RAL (ACTION 7).  .  RAL to then quoted for use of eth clean and bake out facilities (ACTION 8).

MSSL still needs data on where the Cardiff blacking is to go on the structure.  MSSL need to chase Bruce Swinyard and Tony Richards. (ACTION 9).

# Next Meeting

Next meeting is scheduled for Thursday 1 August 2002 at MSSL.  DS already has given his apologies as he will be on leave.

# Actions

| Action Number | Name and Description | Owner | Progress | Deadline |
| --- | --- | --- | --- | --- |
| 1 | Check with Peter Hargrave when will the dichroic filters be ready and when will thickness be available. | CBB | Post meeting – Pete emailed on 19 July to say that the CQM filter were scheduled for 15 October but he could let MSSL have thickness before mid September | 19 July 2002 |
| 2 | Contact the subsystems and request realistic delivery dates | ES |  | 1 August 2002 |
| 3 | Order a second Hob Simulator | DS |  | 1 August 2002 |
| 4 | Check the height of the test facitity. | DS |  | 1 August 2002 |
| 5 | Check the number of sets of MGSE that will be delivered to RAL. | CBB | Post meeting -Only one set will be delivered | 19 July 2002 |
| 6 | Revise the integration and AIV plan for STM and CQM to get realistic dates for activities | DS |  | 1 August 2002 |
| 7 | Plan out which parts of the structure are getting cleaned and baked out where. | CBB | Post Meeting - Current listing is available. | 26 July 2002 |
| 8 | Quote for the use of the RAL clean and bake out facilities | ES |  | 16 August 2002 |
| 9 | Chase Bruce Swinyard and Tony Richards for details of where the blacking goes on the structure | CBB |  | 1 August 2002 |