Meeting of Integration and AIV Planning Team at MSSL

Thursday 1 August 2002

Present

Chris Brockley-Blatt	MSSL

Eric Sawyer		Rutherford Appleton Laboratory

# Discussions

This was the second meeting of the Integration and AIV Planning Team.  Dave Smith was unable to attend as he was on leave.

# Minutes of last meeting

The minutes of last meeting were deemed acceptable and the status of the actions is given in the table below.

# MSSL Schedule

The plan is for the Optical Bench design to be finished by and released on 2 August 2002 is still on track.

# Delivery Dates

The current delivery date for parts to RAL for MSSL is 7 October 2002 for cleaning and baked out before final assembly, still holds.  The Cardiff black still needs to be applied but unsure of when; definitely before bake out but before cleaning?  This needs to be discussed at a meeting proposed for September on Cardiff Black, after the qualification testing of the black.

# MGSE

Both MSSL and RAL require the HOB simulator at the same time. It was reiterated that RAL will need to order a second HOB simulator to ensure that there is no delay to the current schedule (ACTION 3).

RAL to check the height of the test area, as there was concern expressed about the height of the lifting equipment as designed by MSSL (ACTION 4).

Who makes the Vibration plate?  ES and CBB to check (ACTION 11)

It looks like that the JFETs will have to be lifted at the same time as the main FPU during space craft integration.  Need to produce a design for JFET lifting gear with the FPU – this needs to be discussed with BW when he gets back.

# Schedule

RAL have re-planned their activities.  ES to send CBB a copy (ACTION 10) .

MSSL will start trial integration in mid August.  300mK busbar supports are due to MSSL at the start of September, so final integration cannot start until after these have arrived and been tested.

# LAM

LAM has requested that there should be an optical cube at the telescope axis during alignment.  This would mean a plate bolted to the feet of the instrument that has the cube mounted to it.  It is proposed that this should be light and only be used as an alignment tool.  MSSL need to review this when BW gets back.

# Lubrication

To be discussed at next meeting.

# Next Meeting

Next meeting is scheduled for Thursday 15 August 2002 at RAL.

# Actions

| Action Number | Name and Description | Owner | Date Raised | Progress | Deadline |
| --- | --- | --- | --- | --- | --- |
| 1 | Check with Peter Hargrave when will the dichroic filters be ready and when will thickness be available. | CBB | 18 July 2002 | Post meeting – Pete emailed on 19 July to say that the CQM filter were scheduled for 15 October but he could let MSSL have thickness before mid September | 19 July 2002 CLOSED |
| 2 | Contact the subsystems and request realistic delivery dates | ES | 18 July 2002 | Dave has supplied to Eric required delivery dates by which the subsystems must deliver by. Eric will send these out | 15 August 2002 |
| 3 | Order a second Hob Simulator | DS | 18 July 2002 |  | 15 August 2002 |
| 4 | Check the height of the test facitity. | DS | 18 July 2002 |  | 15 August 2002 |
| 5 | Check the number of sets of MGSE that will be delivered to RAL. | CBB | 18 July 2002 | Post meeting -Only one set will be delivered | 19 July 2002 CLOSED |
| 6 | Revise the integration and AIV plan for STM and CQM to get realistic dates for activities | DS | 18 July 2002 |  | 1 August 2002 CLOSED |
| 7 | Plan out which parts of the structure are getting cleaned and baked out where. | CBB | 18 July 2002 | Post Meeting - Current listing is available. | 26 July 2002 CLOSED |
| 8 | Quote for the use of the RAL clean and bake out facilities | ES | 18 July 2002 | Quote was submitted to MSSL | 16 August 2002 CLOSED |
| 9 | Chase Bruce Swinyard and Tony Richards for details of where the blacking goes on the structure | CBB | 18 July 2002 | Tony has sent a list to MSSL and Cardiff of required areas. CBB proposed a meeting in September for all parties to discuss the practicalities. | 1 August 2002 CLOSED |
| 10 | Send CBB a copy of subsystem delivery dates and itegration plan | ES | 1 August 2002 |  | 15 August 2002 |
| 11 | Check who is contracted to make the vibration plate. MSSL or RAL? | ES/CBB | 1 August 2002 |  | 15 August 2002 |