# Meeting of Integration and AIV Planning Team –

# Telecon between RAL and MSSL

### Thursday 29 August 2002

Present

Chris Brockley-Blatt	MSSL

Berend Winter		MSSL

John Coker 		MSSL (Part time)

Eric Sawyer		Rutherford Appleton Laboratory

Dave Smith		Rutherford Appleton Laboratory

# Discussions

This was the fourth meeting of the Integration and AIV Planning Team.

# Minutes of last meeting

The minutes of last meeting were deemed acceptable and the status of the actions is given in the table below.

# MSSL Schedule

The Optical Bench was released on Friday 16 August 2002.

# Delivery Dates

The current delivery date for parts to RAL for MSSL is 7 October 2002 for cleaning and baked out before final assembly looks in doubt.  The optical Bench is due on 16 September 2002, leaving about 2 weeks for fit check and helicoil installation.  Chris asked if this delivery date could now be 15 October.  Ideally the Cardiff black needs to be applied  before cleaning and bakeout.  This needs to be confirmed with Cardiff Black. (ACTION 15).

The parts are needed at RAL for clean and bake as soon as available, CBB to investigate sending batches to RAL for processing (ACTION 16).

# MGSE

Both MSSL and RAL require the HOB simulator at the same time. It was reiterated that RAL will need to order a second HOB simulator to ensure that there is no delay to the current schedule (ACTION 3).  CBB to send the latest issue 16 drawing on Friday 30 August (ACTION 17).

It looks like that the JFETs will have to be lifted at the same time as the main FPU during space craft integration.  Need to produce a design for JFET lifting gear with the FPU – this needs to be discussed at the alignment meeting on 3 September, together with the proposal from LAM on the HOR plate. (ACTION 12)

# Integration

GMT from RAL to send quote for cleaning and baking. (ACTION 18)

RAL need a procedure for the vibration testing.  MSSL will provide this and that BW will write it.  It was felt that a meeting with the RAL test department would be necessary before the specification can be written. (ACTION 19)

The RAL MGSE parts are now available and are being fit checked, as well as the vacuum system is being checked.  The cryostat is till set for delivery at the end of September.

# NCR

An NCR has been raised on the second photometer cover wall.  This is coded as NCR-001.  The recovery plan has been accepted by RAL on the basis that:

- It will be used for STM/CQM only.

- The recovery is a screwed on plate.

- No stray light or EMC issues raised and that MSSL are happy with solution on a structural basis.  MSSL confirmed that they are.

The decision was taken to proceed with recovery plan and to send the NCR to RAL for signing off. (ACTION 20)

# Mass Thermal Dummies

CBB to quote for producing a fully assembled structure as use for a thermal mass dummy. (ACTION 21)

# Next Meeting

Next meeting is scheduled for Thursday 19 September 2002 at MSSL.

# Actions

| Action Number | Name and Description | Owner | Date Raised | Progress | Deadline |
| --- | --- | --- | --- | --- | --- |
| 2 | Contact the subsystems and request realistic delivery dates | ES | 18 July 2002 | Dave has supplied to Eric required delivery dates by which the subsystems must deliver by. Eric will send these out | 29 August 2002 CLOSED |
| 10 | Send CBB a copy of subsystem delivery dates and itegration plan | ES | 1 August 2002 |  | 28 August 2002 CLOSED |
| 11 | Check who is contracted to make the vibration plate. MSSL or RAL? | ES/CBB | 1 August 2002 |  | 19 September 2002 |
| 12 | Discuss JFET lifting and LAM request for plate on FPU feet for a HOR | CBB | 15 August 2002 | To be discuss at the alignment meeting on 3 September at RAL | 19 September 2002 |
| 13 | MSSL to list what tools and clean room equipment is needed | CBB | 15 August 2002 | In Progress | 19 September 2002 |
| 14 | MSSL to provide vibration test procedure? | CBB | 15 August 2002 | BW will provide the vibration test procedure. Will need a meeting with RAL test department before hand. | 19 September 2002 |
| 15 | Confirm with Cardiff the actual sequence of when the Cardiff Black can be applied to the parts | CBB | 29 August 2002 |  | 19 September 2002 |
| 16 | Investigate when the parts can go to RAL | CBB | 29 August 2002 |  | 19 September 2002 |
| 17 | Issue ICD drawing issue 16 | CBB | 29 August 2002 |  | 30 August 2002 |
| 18 | GMT to send hard copy of quote to MSSL for cleaning and baking so CBB can raise an order | GMT | 29 August 2002 |  | 5 September 2002 |
| 19 | Set up meeting with test department to discuss the vibration procedure | ES | 29 August 2002 |  | 19 September 2002 |
| 20 | Send NCR to RAL for signing off | CBB | 29 August 2002 |  | 30 August 2002 |
| 21 | Produce a quote for a complete structure for a thermal mass dummy | CBB | 29 August 2002 |  | 5 September 2002 |